## RPM
RPM Facilitation
Requests and Open Topics
Updated August 5, 2011
ID | Request/Topic | Status | Notes | Applicable Link | Request Date | Closed Date
1 | EAS revenue offsets for the reference CC and CT using RT LMPs versus DA LMPs | Completed | posted under the 6/29/11 MRC RPM | MRC | 2011-06-28 | 2011-06-29
2 | question raised about the 16-hour block that a CC must be economic under in energy revenue calculation as opposed to a shorter time period no specific request made however PJM is performing analysis to determine typical minimum run-times for CCs | In Process |  |  | 2011-06-29
3 | list of OATT references to the NEPA section of the OATT (section 5.14.c) was requested | Completed | information from following references shared on 7/7/11 telephone call of MRC: Attachment DD, Section 6.8.a - Capital Expenditures and Project Investment section of the Avoidable Cost Definition section Multi-Year Pricing Option Attachment DD-1 Section M.4 - EE resources section | N/A | 2011-06-29 | 2011-07-07
4 | new capacity and uprates to capacity for all delivery years in MW by EMAAC and MAAC cumulative offer price numbers for new capacity and uprates to capacity | In Process | RPM team working on this request |  | 2011-07-13
5 | who are the FRR entities, when were their elections made, and when are they eligible to move back to RPM? | Completed | answered here: AEP elected in 2007, may terminate FRR 2 months in advance of a BRA Duke elected in 2011, may move back for 2016/17 delivery year ATSI an FRR entity for transitional years - 2011/12 and 2012/13 | N/A | 2011-07-11 | 2011-08-02
6 | suggested documenting what the status quo is in column A of the proposed solution for FRR | Completed | included in the FRR matrix for 7/21/11 and going forward | MRC | 2011-07-11 | 2011-07-21
7 | explain original purpose of the FRR features and why they are limitations to self supply | Completed | posted Andy's comments for FERC technical conference | Comments to FERC | 2011-07-21 | 2011-07-22
8 | better define wholesale metering | Completed | additional educational material posted under 7/21/11 meeting date | MRC | 2011-07-21 | 2011-08-02
9 | add status quo to all matrices | Completed | added to matrices | MRC | 2011-07-21 | 2011-08-02
10 | How big a difference is there with all DA versus all RT prices being used? What is the impact on Net CONE? What difference would that change have made in the auction? | In Process |  |  | 2011-08-05
11 | Investigate dispatch of CTs and CCGTs with regard to day-ahead and real-time prices. | In Process |  |  | 2011-08-05
12
13
14
15
16
17
18