## Issue Tracker
Special Session of the Markets and Reliability Committee – Gas/Electric Market Timeline Alignment
Last Updated 06/02/2015
# | Category | Stakeholder Feedback | Action/Timeline
1 | Request | -PJM issue longer term problem statement on DA/Gas-Electric timeline. | Consider next steps when compliance filing effort is complete.
2 | Request | -PJM should consider linking intraday offers with the compliance filing related to timing of the DA market. | Compliance filing is focused on timing of the DA market. There's a new work effort within PJM regarding intraday offers. Work effort approved at April MRC.
3 | Request | -Can PJM provide the membership better insight into the different processes involved in clearing the DA market. -PJM commit to continue to improve DA market solve time. | -PJM shared additional information at the May MRC regarding processing time and historical statistics. -PJM is committed to continuing to improve the DA process.
4 | Request | -Price discovery, making sure gas is still available, and seams are all issues. Real problem is DA timing. -Can PJM file extension with FERC? | PJM and stakeholders need sufficient time to implement any DA market changes no later than April 1, 2016.
5 | Request | -Reach out to the pipes to see if they plan to implement FERC Order 809 before April 1 2016. | PJM Gas-Electric Team will reach out to the pipelines prior to June 10th meeting.
6 | Request | -Create excel spreadsheet to track comments/concerns. -Come up with survey to see what’s most important to stakeholders. -Rank each proposal and present for discussion at next meeting. | This spreadsheet will continue to be updated and posted with meeting materials.
7 | Request | -Possible individual session to discuss moving the DA Mid-June. | Discussion on next steps will occur at the May MRC.
8 | Discussion | -DA Posting Deadline <3hrs -Bid submission deadline closer to timely nom cycle (price certainty).
9 | Discussion | -Consider gas liquidity when determining when offers are due.
10 | Discussion | -Be aware of DA pricing issues between ISO/RTO seams.
11 | Discussion | -Continue to decrease DA posting window even after compliance filing. -Specifically concerned about emergency days and meeting an ambitious posting deadline.
12 | Discussion | -Insufficient natural gas price certainty at 0930.
13 | Discussion | -Shrink DA window as much as possible; meeting posting deadline 80% of the time is acceptable.
14 | Discussion | -Shorten DA turnaround (from bid submission deadline to posted results).
15 | Discussion | -PJM should Post DA Results as soon as available rather than a specified time.
16 | Discussion | -The smaller the solve time for the DA solve time, the more flexibility you have for when offers are due and results are posted
17 | Discussion | -Reconsider rebid period to incorporate RAC. The 3 1/2 hours should include the rebid and RAC run.
18 | Discussion | -Concerned with the communication of RAC run results after ID2 deadline. ID2 is 1530 Eastern, which is the last nom cycle in firm transport with bumpable rights.
19 | Discussion | -Post DA Results as soon as available.
20 | Discussion | -Dive deep to improve data input and validity checks, pre-identify constraints, contingencies. -Potentially identify ways to speed up this process.
21 | Discussion | -Capture what stakeholders want: Crunch time, base offers off of time it occurs, post results as soon as possible. Okay to run late with posting of DA results. Commitment from PJM that we think we can do this.
22 | Discussion | -Concern of how we can alleviate issues with gen’s buying gas through holidays and weekends. -FERC Order 809 does not address weekend procedures.
23 | Discussion | -If pipeline is running the weekly nomination, then weekend needs to nominate by Friday, that becomes an operations issue and an issue of how pipelines administer their tariffs.
24 | Discussion | -Concerned with putting offers into the DA market when there is a large bid/ask spread of natural gas prices. -Would like to understand what members are being measured against.
25 | Discussion | -If PJM had to do DA assessment in 2 hours, how would they do it? Would they limit bid amounts and Virtuals and by how much (i.e. 50%)?
26 | Discussion | -Attempt to maintain sequential clearing with NYISO. This is only for wheel transactions.
27 | Discussion | -The later we close the bid window the better information we have before running the DA market. Load is more accurate.
28 | Request | -Show PJM DA Market completion times in Weekdays vs. Holidays vs. Weekends. Would also like to see pre and post September 8th . | -Will be presented at June MRC Special Session
29 | Request | -Would like DA Market Timeline details if available. Need more transparency for DA market timelines. | -Will be presented at June MRC Special Session
30 | Discussion | - LSE – perspective, the earlier in the day we have to put in load bids the less accurate it will be
31 | Discussion | - Annual meeting – we talked about taking out financial bids. If you take out financials how fast does that speed up just the physical solution? Maybe we should do a step or phased solution to shift the times for the day ahead market meaning not try to tackle it all at once.
32 | Discussion | - Weather forecast balloons go up at 0835 and 1030, the 1030 one is more accurate so we will have better load data.
33 | Request | - Would like to see inside the Black box called the DA Market | -Will be presented at June MRC Special Session
34 | Discussion | - Rebid period is very challenging and we should look at ways to lengthen 30 minutes to an hour.
35 | Discussion | -It is important to get the DA results earlier in order to have more time to purchase gas on tight days.