## Current List
Region | Upgrade ID | Description | Transmisison Owner | Required In Service Date | Revised Required In Service Date | Status | TEAC Cost | TEAC Date | Latest TEAC Date | Database Notes | Board Date | Initial Issue Assessment | Final Assessment
PJM MA | b3757 | Convert existing Medford 69kV Straight bus to Seven breaker ring bus, , construct a new 230/69kV transformer at Cox's Corner and a new line from Cox's Corner to Medford. | PSEG | 2027-06-01 |  | PL | 101.5 | 2022-10-13 | 2022-11-17 |  |  | New Upgrade | New Upgrade
PJM MA | b2496 | Replace Franklin 115/34.5 kV transformer #2 with 90 MVA transformer | JCPL | 2015-06-01 | 2021-06-01 | On Hold | 3 | 2014-06-24 |  | Immediate Need (TO Criteria Violation) | 2014-11-05 | Cancelled in Database | Cancelled
PJM WEST | b2967 | Convert the existing 6 wire Butler - Shanor Manor - Krendale 138 kV Line into two separate 138 kV lines. New lines will be Butler - Keisters and Butler - Shanor Manor - Krendale 138 kV | APS | 2022-06-01 | 2020-06-01 | On Hold | 6.96 | 2017-11-02 | 2018-06-07 | 2017_1-10C | 2017-12-05 | Cancelled in Database | Cancelled
PJM WEST | b3005 | Reconductor 3.1 mile 556 ACSR portion of Cabot to Butler 138 kV with 556 ACSS and upgrade terminal equipment. 3.1 miles of line will be reconductored for this project. The total length of the line is 7.75 miles. | APS | 2021-06-01 |  | On Hold | 4.5 | 2018-06-07 | 2018-06-07 | DAVIS BESSE 1,PERRY 1,BEAVER VALLEY 1,BEAVER VALLEY 2 | 2018-07-31 | Cancelled in Database | Cancelled
PJM WEST | b3010 | Replace terminal equipment at Keystone and Cabot 500 kV buses. At Keystone, bus tubing and conductor, a wavetrap, and meter will be replaced. At Cabot, a wavetrap and bus conductor will be replaced. | APS | 2021-06-01 |  | On Hold | 0.28 | 2018-06-07 | 2018-06-07 | DAVIS BESSE 1,PERRY 1,BEAVER VALLEY 1,BEAVER VALLEY 2 | 2018-07-31 | Cancelled in Database | Cancelled
PJM WEST | b3011.1 | Construct new Route 51 substation and connect 10 138 kV lines to new substation | APS | 2021-06-01 |  | On Hold | 26.202 | 2018-06-07 | 2020-05-12 | DAVIS BESSE 1,PERRY 1,BEAVER VALLEY 1,BEAVER VALLEY 2 | 2018-07-31 | Cancelled in Database | Cancelled
PJM WEST | b3011.6 | Upgrade remote end relays for Yukon –Allenport – Iron Bridge 138 kV line | APS | 2021-06-01 |  | On Hold | 0.71 | 2018-06-07 |  | DAVIS BESSE 1,PERRY 1,BEAVER VALLEY 1,BEAVER VALLEY 2 | 2018-07-31 | Cancelled in Database | Cancelled
PJM WEST | b3012.1 | Construct two new 138 kV ties with the single structure from APS’s new substation to DUQ’s new substation. The estimated line length is approximately 4.7 miles. The line is planned to use multiple ACSS conductors per phase. | APS | 2021-06-01 |  | On Hold | 23.1 | 2018-06-07 | 2020-05-12 | DAVIS BESSE 1,PERRY 1,BEAVER VALLEY 1,BEAVER VALLEY 2 | 2019-07-29 | Cancelled in Database | Cancelled
PJM WEST | b3012.3 | Construct a new Elrama - Route 51 138 kV No.3 line: reconductor 4.7 miles of the existing line, and construct 1.5 miles of a new line to the reconductored portion. Install a new line terminal at APS Route 51 substation. | APS | 2020-06-01 |  | On Hold | 18.1 | 2019-05-16 |  |  | 2019-07-29 | Cancelled in Database | Cancelled
PJM WEST | b3013 | Reconductor Vasco Tap to Edgewater Tap 138 kV line. 4.4 miles. The new conductor will be 336 ACSS replacing the existing 336 ACSR conductor. | APS | 2021-06-01 |  | On Hold | 4.99 | 2018-06-07 |  | DAVIS BESSE 1,PERRY 1,BEAVER VALLEY 1,BEAVER VALLEY 2 | 2018-07-31 | Cancelled in Database | Cancelled
PJM MA | b3014 | Replace the existing Shelocta 230/115 kV transformer and construct a 230 kV ring bus | PENELEC | 2021-06-01 |  | On Hold | 4.77 | 2018-06-07 |  | DAVIS BESSE 1,PERRY 1,BEAVER VALLEY 1,BEAVER VALLEY 2 | 2018-07-31 | Cancelled in Database | Cancelled
PJM WEST | b3015.8 | Upgrade terminal equipment at Mitchell for Mitchell – Elrama 138 kV line | APS | 2021-06-01 |  | On Hold | 2 | 2019-09-12 | 2020-05-12 |  | 2020-02-10 | Cancelled in Database | Cancelled
PJM WEST | b3064.3 | Upgrade line relaying at Piney Fork and Bethel Park for Piney Fork – Elrama 138 kV line and Bethel Park – Elrama 138 kV line. | APS | 2021-06-01 |  | On Hold | 0.6 | 2019-09-12 | 2020-05-12 |  | 2020-02-10 | Cancelled in Database | Cancelled
PJM WEST | b3066 | Reconductor the Cranberry - Jackson 138 kV line (2.1 miles), reconductor 138 kV bus at Cranberryand replace 138 kv line switches at Jackson | ATSI | 2022-06-01 |  | On Hold | 3.44 | 2018-11-08 |  | MANSFIELD 1,MANSFIELD 2,MANSFIELD 3,EASTLAKE 6,SAMMIS DIESEL,SAMMIS 5,SAMMIS 6,SAMMIS 7 | 2019-02-12 | Cancelled in Database | Cancelled
PJM WEST | b3067 | Reconductor the Jackson - Maple 138 kV line (4.7 miles), replace line switches at Jackson 138 kV and replace the line traps and relays at Maple 138 kV | ATSI | 2022-06-01 |  | On Hold | 7.86 | 2018-11-08 |  | MANSFIELD 1,MANSFIELD 2,MANSFIELD 3,EASTLAKE 6,SAMMIS DIESEL,SAMMIS 5,SAMMIS 6,SAMMIS 7 | 2019-02-12 | Cancelled in Database | Cancelled
PJM WEST | b3068 | Reconductor the Yukon - Westraver 138 kV line (2.8 miles), replace the line drops and relays at Yukon 138 kV and replace switches at Westraver 138 kV | APS | 2022-06-01 |  | On Hold | 2.5 | 2018-11-08 |  | MANSFIELD 1,MANSFIELD 2,MANSFIELD 3,EASTLAKE 6,SAMMIS DIESEL,SAMMIS 5,SAMMIS 6,SAMMIS 7 | 2019-02-12 | Cancelled in Database | Cancelled
PJM WEST | b3069 | Reconductor the Westraver - Route 51 138 kV line (5.63 miles) and replace line switches at Westraver 138 kV | APS | 2022-06-01 |  | On Hold | 7.5 | 2018-11-08 |  | MANSFIELD 1,MANSFIELD 2,MANSFIELD 3,EASTLAKE 6,SAMMIS DIESEL,SAMMIS 5,SAMMIS 6,SAMMIS 7 | 2019-02-12 | Cancelled in Database | Cancelled
PJM WEST | b3070 | Reconductor the Yukon - Route 51 #1 138 kV line (8 miles), replace the line drops, relays and line disconnect switch at Yukon 138 kV | APS | 2022-06-01 |  | EP | 10 | 2018-11-08 |  | MANSFIELD 1,MANSFIELD 2,MANSFIELD 3,EASTLAKE 6,SAMMIS DIESEL,SAMMIS 5,SAMMIS 6,SAMMIS 7 | 2019-02-12 | Cancelled in Database | Cancelled
PJM WEST | b3071 | Reconductor the Yukon - Route 51 #2 138 kV line (8 miles) and replace relays at Yukon 138 kV | APS | 2022-06-01 |  | EP | 10 | 2018-11-08 |  | MANSFIELD 1,MANSFIELD 2,MANSFIELD 3,EASTLAKE 6,SAMMIS DIESEL,SAMMIS 5,SAMMIS 6,SAMMIS 7 | 2019-02-12 | Cancelled in Database | Cancelled
PJM WEST | b3072 | Reconductor the Yukon - Route 51 #3 138 kV line (8 miles) and replace relays at Yukon 138 kV | APS | 2022-06-01 |  | On Hold | 10 | 2018-11-08 |  | MANSFIELD 1,MANSFIELD 2,MANSFIELD 3,EASTLAKE 6,SAMMIS DIESEL,SAMMIS 5,SAMMIS 6,SAMMIS 7 | 2019-02-12 | Cancelled in Database | Cancelled
PJM WEST | b3073 | Replace the Blairsville East 138/115 kV transformer and associated equipment such as breaker disconnects and bus conductor | PENELEC | 2022-06-01 |  | On Hold | 5 | 2018-11-08 |  | MANSFIELD 1,MANSFIELD 2,MANSFIELD 3,EASTLAKE 6,SAMMIS DIESEL,SAMMIS 5,SAMMIS 6,SAMMIS 7 | 2019-02-12 | Cancelled in Database | Cancelled
PJM WEST | b3074 | Replace Substation conductor on the 345/138 kV transformer at Armstrong substation | APS | 2022-06-01 |  | On Hold | 0.5 | 2018-11-08 |  | MANSFIELD 1,MANSFIELD 2,MANSFIELD 3,EASTLAKE 6,SAMMIS DIESEL,SAMMIS 5,SAMMIS 6,SAMMIS 7 | 2019-02-12 | Cancelled in Database | Cancelled
PJM WEST | b3075 | Replace substation conductor and 138 kV circuit breaker on the #1 transformer (500/138 kV) at Cabot substation | APS | 2022-06-01 |  | On Hold | 0.5 | 2018-11-08 |  | MANSFIELD 1,MANSFIELD 2,MANSFIELD 3,EASTLAKE 6,SAMMIS DIESEL,SAMMIS 5,SAMMIS 6,SAMMIS 7 | 2019-02-12 | Cancelled in Database | Cancelled
PJM WEST | b3076 | Reconductor the Edgewater - Loyalhanna 138 kV line (0.67 miles) | APS | 2022-06-01 |  | On Hold | 2 | 2018-11-08 |  | MANSFIELD 1,MANSFIELD 2,MANSFIELD 3,EASTLAKE 6,SAMMIS DIESEL,SAMMIS 5,SAMMIS 6,SAMMIS 7 | 2019-02-12 | Cancelled in Database | Cancelled
PJM WEST | b3077 | Reconductor the Franklin Pike - Wayne 115 kV line (6.78 miles) | PENELEC | 2022-06-01 |  | On Hold | 15 | 2018-11-08 |  | MANSFIELD 1,MANSFIELD 2,MANSFIELD 3,EASTLAKE 6,SAMMIS DIESEL,SAMMIS 5,SAMMIS 6,SAMMIS 7 | 2019-02-12 | Cancelled in Database | Cancelled
PJM WEST | b3078 | Reconductor 138 kV bus and replace the line trap, relays at Morgan Street. Reconductor 138 kV bus at Venango Junction | PENELEC | 2022-06-01 |  | On Hold | 1 | 2018-11-08 |  | MANSFIELD 1,MANSFIELD 2,MANSFIELD 3,EASTLAKE 6,SAMMIS DIESEL,SAMMIS 5,SAMMIS 6,SAMMIS 7 | 2019-02-12 | Cancelled in Database | Cancelled
PJM WEST | b3079 | Replace the Wylie Ridge 500/345 kV transformer #7 | APS | 2022-06-01 |  | On Hold | 6.37 | 2018-11-08 |  | MANSFIELD 1,MANSFIELD 2,MANSFIELD 3,EASTLAKE 6,SAMMIS DIESEL,SAMMIS 5,SAMMIS 6,SAMMIS 7 | 2019-02-12 | Cancelled in Database | Cancelled
PJM WEST | b3080 | Reconductor 138 kV bus at Seneca | ATSI | 2022-06-01 |  | On Hold | 0.07 | 2018-11-08 |  | MANSFIELD 1,MANSFIELD 2,MANSFIELD 3,EASTLAKE 6,SAMMIS DIESEL,SAMMIS 5,SAMMIS 6,SAMMIS 7 | 2019-02-12 | Cancelled in Database | Cancelled
PJM WEST | b3081 | Replace 138 kV breaker and substation conductor at Krendale | ATSI | 2022-06-01 |  | On Hold | 1 | 2018-11-08 |  | MANSFIELD 1,MANSFIELD 2,MANSFIELD 3,EASTLAKE 6,SAMMIS DIESEL,SAMMIS 5,SAMMIS 6,SAMMIS 7 | 2019-02-12 | Cancelled in Database | Cancelled
PJM WEST | b3082 | Construct a 4-breaker 115 kV ring bus at Franklin Pike | PENELEC | 2022-06-01 |  | On Hold | 7 | 2018-11-08 |  | MANSFIELD 1,MANSFIELD 2,MANSFIELD 3,EASTLAKE 6,SAMMIS DIESEL,SAMMIS 5,SAMMIS 6,SAMMIS 7 | 2019-02-12 | Cancelled in Database | Cancelled
PJM WEST | b3083 | Replace substation conductor at Butler (138 kV) Replace substation conductor and line trap at Karns City (138 kV) | APS | 2022-06-01 |  | On Hold | 2 | 2018-11-08 |  | MANSFIELD 1,MANSFIELD 2,MANSFIELD 3,EASTLAKE 6,SAMMIS DIESEL,SAMMIS 5,SAMMIS 6,SAMMIS 7 | 2019-02-12 | Cancelled in Database | Cancelled