## 2018 WORK PLAN
DER Subcommittee - Current Issues | [15 empty] | 2018
Wholesale DER (W-DER) Market Participation
Ancillary Services
Energy
Capacity
Interconnection Queue Process
DER Aggregation | [15 empty] | On hold pending FERC action in RM18-9
Wholesale Market Participation Agreement - Operational Requirements
Non-wholesale DER observability (BtMG)
Triennial Review Timing | 2012-07-01 | 2012-08-01 | 2012-09-01 |  | 2012-10-01 | 2012-11-01 | 2012-12-01 | 2013-01-01
üProvide Education
üProblem Investigation
üProposal Development
üBuild Consensus
üFirst Read @ MRC | [5 empty] | 2012-11-29
üVote at MRC | [6 empty] | 2012-12-20
üVote at MC
Multi-Year Pricing Mechanism | 2012-07-01 | 2012-08-01 | 2012-09-01 |  | 2012-10-01 | 2012-11-01 | 2012-12-01 | 2013-01-01 | 2013-02-01 | 2013-03-01
üProvide Education
üRefine Interests
üDevelop & Refine Design Components | bar: 2012-10-01
üDevelop & Refine Component Options | bar: 2012-10-01 to 2012-12-01
üDevelop & Refine Solution Packages | bar: 2012-11-01 to 2012-12-01
üBuild Consensus | bar: 2013-01-01
üFirst Read @ MRC |  |  |  |  | 2013-01-01: 2013-01-31
Vote at MRC |  |  |  |  | 2013-02-01: 2013-02-28
Vote at MC |  |  |  |  | 2013-02-01: 2013-02-28
FERC Filing |  |  |  |  | 2013-03-01: 2013-03-01
Updated: November 30, 2018
Detailed Work Plan -- Wholesale DER Ancillary Services | 6.26 | 7.17 | 7.31 | 8.9 | 8.26 | 8.28 | 9.9 | 9.18 | 9.24 | 9.26 (MRC) | DERS 01.5.18 | DERS 01.31.18 | DERS 03.02.18 | DERS 03.26.18 | DERS 04.25.18 | DERS 06.08.18 | DERS 06.29.18 | DERS 07.30.18 | DERS 08.27.18 | DERS 10.4.18 | DERS 10.31.18 | DERS 11.30.18
Create Subcommittee Charter and Approval |  | x | x | x | bar: 2012-11-01 to 2012-12-01
Provide Education |  |  | x | [13 empty] | x
Document Interests |  |  |  | x | bar: 2012-11-01 to 2012-12-01
Develop & Refine Design Components | [17 empty] | x | bar: 2012-11-01 to 2012-12-01; 2013-02-01
Develop & Refine Component Options | [10 empty] | x | x | x |  |  |  | x | x | x
Develop & Refine Solution Packages | [12 empty] | x | x |  |  |  |  | x | x | x | x
Build Consensus | [20 empty] | x | x
Subcommittee Vote | [21 empty] | x
Detailed Work Plan -- Interconnection Queue Process | [10 empty] | DERS 01.5.18 | DERS 01.31.18 | DERS 03.02.18 | DERS 03.26.18 | DERS 04.25.18 | DERS 06.08.18 | DERS 06.29.18 | DERS 07.30.18 | DERS 08.27.18 | DERS 10.4.18 | DERS 10.31.18 | DERS 11.30.18
Provide Education | [17 empty] | x | x | x | x
Document Interests | [18 empty] | x | x
Develop & Refine Design Components | [20 empty] | x | x
Develop & Refine Component Options | [21 empty] | x
Develop & Refine Solution Packages
Build Consensus
Subcommittee Vote
Detailed Work Plan -- WMPA Operational Requirements | [10 empty] | DERS 01.5.18 | DERS 01.31.18 | DERS 03.02.18 | DERS 03.26.18 | DERS 04.25.18 | DERS 06.08.18 | DERS 06.29.18 | DERS 07.30.18 | DERS 08.27.18 | DERS 10.4.18 | DERS 10.31.18 | DERS 11.30.18
Provide Education | [18 empty] | x | x | x | x
Document Interests
Develop & Refine Design Components
Develop & Refine Component Options
Develop & Refine Solution Packages
Build Consensus
Subcommittee Vote
Detailed Work Plan -- non-Wholesale DER Observability (BtMG) | [10 empty] | DERS 01.5.18 | DERS 01.31.18 | DERS 03.02.18 | DERS 03.26.18 | DERS 04.25.18 | DERS 06.08.18 | DERS 06.29.18 | DERS 07.30.18 | DERS 08.27.18 | DERS 10.4.18 | DERS 10.31.18 | DERS 11.30.18
Provide Education | [10 empty] | x | x
Document Interests | [13 empty] | x | x
Develop & Refine Design Components | [13 empty] | x | x
Develop & Refine Component Options | [13 empty] | x | x
Develop & Refine Solution Packages | [15 empty] | x
Build Consensus | [15 empty] | x | x | x
Subcommittee Vote | [17 empty] | x
COMPLETED

## 2019 WORK PLAN
DER Subcommittee - Current Issues | [14 empty] | 2019 |  |  |  |  | 2020
Updated: January 28, 2020
Interconnection Queue Process - Complete
DER Aggregation - Postponed | [9 empty] | On hold pending FERC action in RM18-9
Triennial Review Timing | 2012-07-01 | 2012-08-01 | 2012-09-01 | 2012-10-01 | 2012-11-01 | 2012-12-01 | 2013-01-01
üProvide Education
üProblem Investigation
üProposal Development
üBuild Consensus
üFirst Read @ MRC |  |  |  |  | 2012-11-29
üVote at MRC | [5 empty] | 2012-12-20
üVote at MC
Multi-Year Pricing Mechanism | 2012-07-01 | 2012-08-01 | 2012-09-01 | 2012-10-01 | 2012-11-01 | 2012-12-01 | 2013-01-01 | 2013-02-01 | 2013-03-01
üProvide Education
üRefine Interests
üDevelop & Refine Design Components | bar: 2012-10-01
üDevelop & Refine Component Options | bar: 2012-10-01 to 2012-12-01
üDevelop & Refine Solution Packages | bar: 2012-11-01 to 2012-12-01
üBuild Consensus | bar: 2013-01-01
üFirst Read @ MRC |  |  |  | 2013-01-01: 2013-01-31
Vote at MRC |  |  |  | 2013-02-01: 2013-02-28
Vote at MC |  |  |  | 2013-02-01: 2013-02-28
FERC Filing |  |  |  | 2013-03-01: 2013-03-01
Utility Microgrids - Active
Detailed Work Plan -- Utility Microgrids | [9 empty] | DERS 02.04.19 | DERS 03.04.19 | DERS 04.15.19 | DERS 05.20.19 | DERS 06.10.19 | DERS 07.15.19 | DERS 08.21.19 | DERS 09.09.19 | DERS 10.10.19 | DERS 11.18.19 | DERS 02.03.20 | DERS 05.18.20 | DERS 08.03.20 | DERS 11.02.20
Provide Education | [10 empty] | X |  | X
Document Interests | [13 empty] | X | X
Develop & Refine Design Components | [13 empty] | X | X
Develop & Refine Component Options | [14 empty] | X
Develop & Refine Solution Packages | [15 empty] | X | X |  | X | X | X
Build Consensus | [17 empty] | X |  | X | X
Subcommittee Vote | [20 empty] | X
Detailed Work Plan -- Interconnection Queue Process | [9 empty] | DERS 02.04.19 | DERS 03.04.19 | DERS 04.15.19 | DERS 05.20.19 | DERS 06.10.19 | DERS 07.15.19 | DERS 08.21.19 | DERS 09.09.19 | DERS 10.10.19 | DERS 11.18.19
Provide Education | [9 empty] | X - 2018
Document Interests | [9 empty] | X - 2018
Develop & Refine Design Components | [9 empty] | X - 2018
Develop & Refine Component Options | [9 empty] | X | X |  | X | X | X
Develop & Refine Solution Packages | [9 empty] | X | X |  |  |  | X | X | X
Build Consensus | [16 empty] | X
Subcommittee Vote | [16 empty] | X | APPROVED & COMPLETED