## DRAFT WORK PLAN
DRAFT New Subcommitte Workplan (combination of DRS and DIRS)
Area | PS/IC | Item | 2003-01-01 | 2003-02-01 | 2003-03-04 | 2003-04-04 | 2003-05-05 | 2003-06-05 | 2003-07-06 | 2003-08-06 | 2003-09-06 | 2003-10-07 | 2003-11-07 | 2003-12-08
DR | Y - approved | Capacity measurement and verification for weather sensitive loads | bar: 2003-01-01 to 2003-09-06
DR | Y - in progress | ResidentialCustomer Measurement and Verification for Demand Response | bar: 2003-01-01 to 2003-10-07
DR | N | New Load Management and PRD Test procedures and system changes | bar: 2003-01-01 to 2003-04-04
DR | N | Typical DR updates (processes and systems), reminders and reporting | bar: 2003-01-01 to 2003-12-08
DIRS | N | Develop 2222 conforming Manual changes | bar: 2003-01-01 to 2003-12-08
DIRS | N | 2222 implementation and associated system changes for BRA participation | bar: 2003-10-07 to 2003-12-08