## October 2020 update (hidden)
2020 Planning Committee Work Plan
|  | January - March |  |  | April - June |  | July - September | October - December
PC Subgroups/ Issues | Market Efficiency Process Enhancement Task Force
Critical Infrastructure Stakeholder Oversight
Effective Load Carrying Capability - Being worked through new MRC, Capacity Capability Senior Task Force (CCSTF)
Storage As Transmission Asset
Phasor Measurement Unit RTEP integration
PC FERC Orders | FERC Order No. 845
PC Manual Reviews | Manual 14A : New Service Request Process (3 YEARS) | Next cover to cover review 2021
| Manual 14B: Regional Transmission Planning Process (2 YEARS) | Next cover to cover review 2021
| Manual 14C: Generation & Transmission Interconnection Facility Construction (2 YEARS) | Cover to cover review Q4 2020, next 2022
| Manual 14E: Additional Information for Upgrade & Transmission Interconnection Projects (3 YEARS) | Next cover to cover review 2021
| Manual 14F: Competitive Planning Process (2 YEARS) | Cover to cover review completed Q1 2020, next 2022
| Manual 14G: Generation Interconnection Requests (3 YEARS) | Next cover to cover review 2021
| Manual 19: Load Forecasting & Analysis (2 YEARS) | Next cover to cover review 2021
| Manual 20: Resource Adequacy Analysis (2 YEARS) | Next cover to cover review 2021
| Manual 21: Rules & Procedures for Determination of Generating Capability (2 YEARS) | Next cover to cover review 2021
| Manual 22: Generator Resource Performance Indices (3 YEARS) | Cover to cover review completed Q1 2020, next 2023
PC Recurring Items | Review of PC Charter
Transmission Expansion Advisory Committee (TEAC) and Sub-regional RTEP (SRRTEP) Meeting Information
Model Build Activity Update
Reliability Compliance Update
Review and endorsement of IRM (or RRS) and FPR
Review and endorsement of Load Model Selection
Review of Annual PJM Load Forecast
MOD-032 Data Requirements & Procedures document
Planning Resilience
PJM Interconnection Queue Status Update (presented at the close of each queue)
Attachement M-3 Update (semi-annual Jan/Jul)
Transmission & Substation Subcommittee Update (May/Dec)
PC Subcommittees | Designated Entity Design Standards Subcommittee (DEDSS) - bienniel review of Minimum standards. Last reviewed and endorsed Nov, 2017. Next review to be initiated Sept, 2019 | Yes | Yes | Yes | Yes
Resource Adequacy Analysis Subcommittee (RAAS)
| Transmission and Substation Subcommittee (TSS) (ANNUAL) |  |  |  |  | Yes
Relay Testing Subcommittee (RTS)
Relay Subcommittee (RS)
Load Analysis Subcommittee (LAS)
Reliability Standards and Compliance Subcommittee (RSCS)
| Review of PC Charter |  |  | Complete
| Transmission Expansion Advisory Committee (TEAC) and Sub-regional RTEP (SRRTEP) Meeting Information |  | Ongoing | In-Progress
| Model Build Activity Update |  | Ongoing | Planned
| Reliability Compliance Update |  | Ongoing
Review and endorsement of IRM (or RRS) and FPR
Review and endorsement of Load Model Selection
Review of Annual PJM Load Forecast
MOD-032 Data Requirements & Procedures document
Planning Resilience
PJM Interconnection Queue Status Update (presented at the close of each queue)
Attachement M-3 Update (semi-annual Jan/Jul) starting July 2020
Transmission & Substation Subcommittee Update (May/Dec)
Legend
Adhoc changes
Cover to Cover
14A (last cover to cover 7/26/2018, due 7/26/2021 – 3 years)
14B (last cover to cover 2/21/2019, due 2/21/2021 – 2 years)
14C (last cover to cover 8/23/2018, overdue 8/23/2020 – 2 years)
14E (last cover to cover 12/20/2018, due 12/20/2021 – 3 years)
14F (last cover to cover 12/2018 next one 12/2021 – 3 years) (last cover to cover 4/10/2020, due 4/10/2022 – 2 years)
14G (last cover to cover 7/26/2018, due 7/26/2021 – 3 years)
19 (last cover to cover 12/1/2017, overdue 12/1/2019 – 2 years)
20 (last cover to cover 3/21/2019, due 3/21/2021 – 2 years)
21 (last cover to cover 5/1/2019, due 5/1/2021 – 2 years)
22 (last cover to cover 3/26/2020, due 3/26/2023 – 3 years)
FERC Filing
Note on B39: fernaa: Charter for RAAS indicates reporting to the PC, but no frequency mentioned
Note on B41: fernaa: Charter does not indicate reporting to the PC
Note on B42: fernaa: From Charter: The RS will develop an annual plan for the following year to be forwarded to the PC in November of each year.
Note on B43: fernaa: Charter mentions the LAS shall report to the PC (no mention of frequency)
Note on B44: fernaa: Charter - no mention of periodic reporting to PC or frequency

## January 2021 update (hidden)
2021 Planning Committee Work Plan
|  | January - March |  |  | April - June |  | July - September | October - December | Notes/Questions
PC Subgroups/Issues | Critical Infrastructure Stakeholder Oversight
PC Manual Reviews | Manual 14A : New Service Request Process (3 YEARS) | Next cover to cover review 2021
| Manual 14B: Regional Transmission Planning Process (2 YEARS) | Next cover to cover review 2021
| Manual 14C: Generation & Transmission Interconnection Facility Construction (2 YEARS) | Cover to cover review Q4 2020, next 2022
| Manual 14E: Additional Information for Upgrade & Transmission Interconnection Projects (3 YEARS) | Next cover to cover review 2021
| Manual 14F: Competitive Planning Process (2 YEARS) | Cover to cover review completed Q1 2020, next 2022
| Manual 14G: Generation Interconnection Requests (3 YEARS) | Next cover to cover review 2021
| Manual 19: Load Forecasting & Analysis (2 YEARS) | Next cover to cover review 2021
| Manual 20: Resource Adequacy Analysis (2 YEARS) | Next cover to cover review 2021
| Manual 21: Rules & Procedures for Determination of Generating Capability (2 YEARS) | Next cover to cover review 2021
| Manual 22: Generator Resource Performance Indices (3 YEARS) | Cover to cover review completed Q1 2020, next 2023
PC Recurring Items | Review of PC Charter
Transmission Expansion Advisory Committee (TEAC) and Sub-regional RTEP (SRRTEP) Meeting Information
Model Build Activity Update
Reliability Compliance Update
Review and endorsement of IRM (or RRS) and FPR
Review and endorsement of Load Model Selection
Review of Annual PJM Load Forecast
MOD-032 Data Requirements & Procedures document
| Planning Resilience | [7 empty] | Aaron - does this stay?
PJM Interconnection Queue Status Update (presented at the close of each queue)
| Attachment M-3 Update (semi-annual Q1/Q3) | [7 empty] | Aaron - ok timing?
Transmission & Substation Subcommittee Update (May/Dec)
PC Subcommittees | Designated Entity Design Standards Subcommittee (DEDSS) - bienniel review of Minimum standards. Last reviewed and endorsed Nov, 2017. Next review to be initiated Sept, 2019 | Yes | Yes | Yes | Yes
Resource Adequacy Analysis Subcommittee (RAAS)
| Transmission and Substation Subcommittee (TSS) (ANNUAL) |  |  |  |  | Yes
Relay Testing Subcommittee (RTS)
Relay Subcommittee (RS)
Load Analysis Subcommittee (LAS)
Reliability Standards and Compliance Subcommittee (RSCS)
| Review of PC Charter |  |  | Complete
| Transmission Expansion Advisory Committee (TEAC) and Sub-regional RTEP (SRRTEP) Meeting Information |  | Ongoing | In-Progress
| Model Build Activity Update |  | Ongoing | Planned
| Reliability Compliance Update |  | Ongoing
Review and endorsement of IRM (or RRS) and FPR
Review and endorsement of Load Model Selection
Review of Annual PJM Load Forecast
MOD-032 Data Requirements & Procedures document
Planning Resilience
PJM Interconnection Queue Status Update (presented at the close of each queue)
Attachement M-3 Update (semi-annual Q1/Q3)
Transmission & Substation Subcommittee Update (May/Dec)
Legend
Adhoc changes
Cover to Cover
14A (last cover to cover 7/26/2018, due 7/26/2021 – 3 years)
14B (last cover to cover 2/21/2019, due 2/21/2021 – 2 years)
14C (last cover to cover 8/23/2018, overdue 8/23/2020 – 2 years)
14E (last cover to cover 12/20/2018, due 12/20/2021 – 3 years)
14F (last cover to cover 12/2018 next one 12/2021 – 3 years) (last cover to cover 4/10/2020, due 4/10/2022 – 2 years)
14G (last cover to cover 7/26/2018, due 7/26/2021 – 3 years)
19 (last cover to cover 12/2019, due 12/2021 – 2 years)
20 (last cover to cover 3/21/2019, due 3/21/2021 – 2 years)
21 (last cover to cover 5/1/2019, due 5/1/2021 – 2 years)
22 (last cover to cover 3/26/2020, due 3/26/2023 – 3 years)
Note on B33: fernaa: Charter for RAAS indicates reporting to the PC, but no frequency mentioned
Note on B35: fernaa: Charter does not indicate reporting to the PC
Note on B36: fernaa: From Charter: The RS will develop an annual plan for the following year to be forwarded to the PC in November of each year.
Note on B37: fernaa: Charter mentions the LAS shall report to the PC (no mention of frequency)
Note on B38: fernaa: Charter - no mention of periodic reporting to PC or frequency

## April 2021 update (hidden)
2021 Planning Committee Work Plan
|  | January - March |  |  | April - June |  | July - September | October - December
PC Subgroups/Issues | Critical Infrastructure Stakeholder Oversight
Capacity Interconnection Rights for ELCC Resources
Interconnection Process Reform
PC Manual Reviews | Manual 14A : New Service Request Process (3 YEARS) | Next cover to cover review 2021
| Manual 14B: Regional Transmission Planning Process (2 YEARS) | Next cover to cover review 2021
| Manual 14C: Generation & Transmission Interconnection Facility Construction (2 YEARS) | Cover to cover review Q4 2020, next 2022
| Manual 14E: Additional Information for Upgrade & Transmission Interconnection Projects (3 YEARS) | Next cover to cover review 2021
| Manual 14F: Competitive Planning Process (2 YEARS) | Cover to cover review completed Q1 2020, next 2022
| Manual 14G: Generation Interconnection Requests (3 YEARS) | Next cover to cover review 2021
| Manual 19: Load Forecasting & Analysis (2 YEARS) | Next cover to cover review 2021
| Manual 20: Resource Adequacy Analysis (2 YEARS) | Next cover to cover review 2021
| Manual 21: Rules & Procedures for Determination of Generating Capability (2 YEARS) | Next cover to cover review 2021
Manual 21A: Determination of Accredited UCAP Using Effective Load Carrying Capability Analysis
| Manual 22: Generator Resource Performance Indices (3 YEARS) | Cover to cover review completed Q1 2020, next 2023
PC Recurring Items | Review of PC Charter
Transmission Expansion Advisory Committee (TEAC) and Sub-regional RTEP (SRRTEP) Meeting Information
Model Build Activity Update
Reliability Compliance Update
Review and endorsement of IRM (or RRS) and FPR
Review and endorsement of Load Model Selection
Review of Annual PJM Load Forecast
MOD-032 Data Requirements & Procedures document
| Planning Resilience | [7 empty] | Aaron - does this stay?
PJM Interconnection Queue Status Update (presented at the close of each queue)
Attachment M-3 Update (semi-annual Q1/Q3)
Transmission & Substation Subcommittee Update (May/Dec)
PC Subcommittees | Designated Entity Design Standards Subcommittee (DEDSS) - bienniel review of Minimum standards. Last reviewed and endorsed Nov, 2017. Next review to be initiated Sept, 2019 | Yes | Yes | Yes | Yes
Resource Adequacy Analysis Subcommittee (RAAS)
| Transmission and Substation Subcommittee (TSS) (ANNUAL) |  |  |  |  | Yes
Relay Testing Subcommittee (RTS)
Relay Subcommittee (RS)
Load Analysis Subcommittee (LAS)
Reliability Standards and Compliance Subcommittee (RSCS)
| Review of PC Charter |  |  | Complete
| Transmission Expansion Advisory Committee (TEAC) and Sub-regional RTEP (SRRTEP) Meeting Information |  | Ongoing | In-Progress
| Model Build Activity Update |  | Ongoing | Planned
| Reliability Compliance Update |  | Ongoing
Review and endorsement of IRM (or RRS) and FPR
Review and endorsement of Load Model Selection
Review of Annual PJM Load Forecast
MOD-032 Data Requirements & Procedures document
Planning Resilience
PJM Interconnection Queue Status Update (presented at the close of each queue)
Attachement M-3 Update (semi-annual Q1/Q3)
Transmission & Substation Subcommittee Update (May/Dec)
Legend
Adhoc changes
Cover to Cover
Informational update to PC
14A (last cover to cover 7/26/2018, due 7/26/2021 – 3 years)
14B (last cover to cover 2/21/2019, due 2/21/2021 – 2 years)
14C (last cover to cover 8/23/2018, overdue 8/23/2020 – 2 years)
14E (last cover to cover 12/20/2018, due 12/20/2021 – 3 years)
14F (last cover to cover 12/2018 next one 12/2021 – 3 years) (last cover to cover 4/10/2020, due 4/10/2022 – 2 years)
14G (last cover to cover 7/26/2018, due 7/26/2021 – 3 years)
19 (last cover to cover 12/2019, due 12/2021 – 2 years)
20 (last cover to cover 3/21/2019, due 3/21/2021 – 2 years)
21 (last cover to cover 5/1/2019, due 5/1/2021 – 2 years)
22 (last cover to cover 3/26/2020, due 3/26/2023 – 3 years)
14B moved to 3rd quarter -- hope to have some substantial changes along with the cover to cover which delayed the cover to cover
20 moved to 3rd quarter
Note on B36: fernaa: Charter for RAAS indicates reporting to the PC, but no frequency mentioned
Note on B38: fernaa: Charter does not indicate reporting to the PC
Note on B39: fernaa: From Charter: The RS will develop an annual plan for the following year to be forwarded to the PC in November of each year.
Note on B40: fernaa: Charter mentions the LAS shall report to the PC (no mention of frequency)
Note on B41: fernaa: Charter - no mention of periodic reporting to PC or frequency

## July 2021 update (hidden)
2021 Planning Committee Work Plan
|  | January - March |  |  | April - June |  | July - September | October - December
PC Subgroups/Issues | Critical Infrastructure Stakeholder Oversight
Capacity Interconnection Rights for ELCC Resources
Interconnection Process Reform
PC Manual Reviews | Manual 14A : New Service Request Process (3 YEARS) | Cover to cover review completed Q3 2020, next 2023
| Manual 14B: Regional Transmission Planning Process (2 YEARS) | Next cover to cover review 2021
| Manual 14C: Generation & Transmission Interconnection Facility Construction (2 YEARS) | Cover to cover review completed Q1 2021, next 2023
| Manual 14E: Additional Information for Upgrade & Transmission Interconnection Projects (3 YEARS) | Cover to cover review completed Q3 2020, next 2023
| Manual 14F: Competitive Planning Process (2 YEARS) | Cover to cover review completed Q2 2020, next 2022
| Manual 14G: Generation Interconnection Requests (3 YEARS) | Cover to cover review completed Q3 2020, next 2023
| Manual 19: Load Forecasting & Analysis (2 YEARS) | Next cover to cover review 2021
| Manual 20: Resource Adequacy Analysis (2 YEARS) | Next cover to cover review 2021
| Manual 21: Rules & Procedures for Determination of Generating Capability (2 YEARS) | Cover to cover review completed Q2 2021, next 2023
Manual 21A: Determination of Accredited UCAP Using Effective Load Carrying Capability Analysis
| Manual 22: Generator Resource Performance Indices (3 YEARS) | Cover to cover review completed Q1 2020, next 2023
PC Recurring Items | Review of PC Charter
Transmission Expansion Advisory Committee (TEAC) and Sub-regional RTEP (SRRTEP) Meeting Information
Model Build Activity Update
Reliability Compliance Update
Review and endorsement of IRM (or RRS) and FPR
Review and endorsement of Load Model Selection
Review of Annual PJM Load Forecast
MOD-032 Data Requirements & Procedures document
| Planning Resilience | [7 empty] | Aaron - does this stay?
PJM Interconnection Queue Status Update (presented at the close of each queue)
Attachment M-3 Update (semi-annual Q1/Q3)
Transmission & Substation Subcommittee Update (May/Dec)
PC Subcommittees | Designated Entity Design Standards Subcommittee (DEDSS) - bienniel review of Minimum standards. Last reviewed and endorsed Nov, 2017. Next review to be initiated Sept, 2019 | Yes | Yes | Yes | Yes
Resource Adequacy Analysis Subcommittee (RAAS)
| Transmission and Substation Subcommittee (TSS) (ANNUAL) |  |  |  |  | Yes
Relay Testing Subcommittee (RTS)
Relay Subcommittee (RS)
Load Analysis Subcommittee (LAS)
Reliability Standards and Compliance Subcommittee (RSCS)
| Review of PC Charter |  |  | Complete
| Transmission Expansion Advisory Committee (TEAC) and Sub-regional RTEP (SRRTEP) Meeting Information |  | Ongoing | In-Progress
| Model Build Activity Update |  | Ongoing | Planned
| Reliability Compliance Update |  | Ongoing
Review and endorsement of IRM (or RRS) and FPR
Review and endorsement of Load Model Selection
Review of Annual PJM Load Forecast
MOD-032 Data Requirements & Procedures document
Planning Resilience
PJM Interconnection Queue Status Update (presented at the close of each queue)
Attachement M-3 Update (semi-annual Q1/Q3)
Transmission & Substation Subcommittee Update (May/Dec)
Legend
Adhoc changes
Cover to Cover
Informational update to PC
14A (last cover to cover 7/26/2018, due 7/26/2021 – 3 years)
14B (last cover to cover 2/21/2019, due 2/21/2021 – 2 years)
14C (last cover to cover 8/23/2018, overdue 8/23/2020 – 2 years)
14E (last cover to cover 12/20/2018, due 12/20/2021 – 3 years)
14F (last cover to cover 12/2018 next one 12/2021 – 3 years) (last cover to cover 4/10/2020, due 4/10/2022 – 2 years)
14G (last cover to cover 7/26/2018, due 7/26/2021 – 3 years)
19 (last cover to cover 12/2019, due 12/2021 – 2 years)
20 (last cover to cover 3/21/2019, due 3/21/2021 – 2 years)
21 (last cover to cover 5/1/2019, due 5/1/2021 – 2 years)
22 (last cover to cover 3/26/2020, due 3/26/2023 – 3 years)
14B moved to 3rd quarter -- hope to have some substantial changes along with the cover to cover which delayed the cover to cover
20 moved to 3rd quarter
Update from Lisa (6/16/21)
M14A last periodic review was published on 7/1/2020 which has a 3 year review cycle. This would be due for periodic review on 7/1/2023.
M14G last periodic review was published on 7/1/2020 which has a 3 year review cycle. This would be due for periodic review on 7/1/2023.
Note on B36: fernaa: Charter for RAAS indicates reporting to the PC, but no frequency mentioned
Note on B38: fernaa: Charter does not indicate reporting to the PC
Note on B39: fernaa: From Charter: The RS will develop an annual plan for the following year to be forwarded to the PC in November of each year.
Note on B40: fernaa: Charter mentions the LAS shall report to the PC (no mention of frequency)
Note on B41: fernaa: Charter - no mention of periodic reporting to PC or frequency

## October 2021 update (hidden)
2021 Planning Committee Work Plan
|  | January - March |  |  | April - June |  | July - September | October - December
PC Subgroups/Issues | Critical Infrastructure Stakeholder Oversight
Capacity Interconnection Rights for ELCC Resources
Interconnection Process Reform
PC Manual Reviews | Manual 14A : New Service Request Process (3 YEARS) | Cover to cover review completed Q3 2020, next 2023
| Manual 14B: Regional Transmission Planning Process (2 YEARS) | Next cover to cover review 2021
| Manual 14C: Generation & Transmission Interconnection Facility Construction (2 YEARS) | Cover to cover review completed Q1 2021, next 2023
| Manual 14E: Additional Information for Upgrade & Transmission Interconnection Projects (3 YEARS) | Cover to cover review completed Q3 2020, next 2023
| Manual 14F: Competitive Planning Process (2 YEARS) | Cover to cover review completed Q2 2020, next 2022
| Manual 14G: Generation Interconnection Requests (3 YEARS) | Cover to cover review completed Q3 2020, next 2023
| Manual 19: Load Forecasting & Analysis (2 YEARS) | Next cover to cover review 2021
| Manual 20: Resource Adequacy Analysis (2 YEARS) | Next cover to cover review 2021
| Manual 21: Rules & Procedures for Determination of Generating Capability (2 YEARS) | Cover to cover review completed Q2 2021, next 2023
Manual 21A: Determination of Accredited UCAP Using Effective Load Carrying Capability Analysis
| Manual 22: Generator Resource Performance Indices (3 YEARS) | Cover to cover review completed Q1 2020, next 2023
PC Recurring Items | Review of PC Charter
Transmission Expansion Advisory Committee (TEAC) and Sub-regional RTEP (SRRTEP) Meeting Information
Model Build Activity Update
Reliability Compliance Update
Review and endorsement of IRM (or RRS) and FPR
Review and endorsement of Load Model Selection
Review of Annual PJM Load Forecast
MOD-032 Data Requirements & Procedures document
| Planning Resilience | [8 empty] | Aaron - does this stay?
PJM Interconnection Queue Status Update (presented at the close of each queue)
| Attachment M-3 Update (semi-annual Q1/Q4) | [8 empty] | ?
Transmission & Substation Subcommittee Update (May/Dec)
PC Subcommittees | Designated Entity Design Standards Subcommittee (DEDSS) - bienniel review of Minimum standards. Last reviewed and endorsed Nov, 2017. Next review to be initiated Sept, 2019 | Yes | Yes | Yes | Yes
Resource Adequacy Analysis Subcommittee (RAAS)
| Transmission and Substation Subcommittee (TSS) (ANNUAL) |  |  |  |  | Yes
Relay Testing Subcommittee (RTS)
Relay Subcommittee (RS)
Load Analysis Subcommittee (LAS)
Reliability Standards and Compliance Subcommittee (RSCS)
| Review of PC Charter |  |  | Complete
| Transmission Expansion Advisory Committee (TEAC) and Sub-regional RTEP (SRRTEP) Meeting Information |  | Ongoing | In-Progress
| Model Build Activity Update |  | Ongoing | Planned |  |  |  |  | 9
| Reliability Compliance Update |  | Ongoing
Review and endorsement of IRM (or RRS) and FPR
Review and endorsement of Load Model Selection
Review of Annual PJM Load Forecast
MOD-032 Data Requirements & Procedures document
Planning Resilience
PJM Interconnection Queue Status Update (presented at the close of each queue)
Attachement M-3 Update (semi-annual Q1/Q4)
Transmission & Substation Subcommittee Update (May/Dec)
Legend
Adhoc changes
Cover to Cover
Informational update to PC
14A (last cover to cover 7/26/2018, due 7/26/2021 – 3 years)
14B (last cover to cover 2/21/2019, due 2/21/2021 – 2 years)
14C (last cover to cover 8/23/2018, overdue 8/23/2020 – 2 years)
14E (last cover to cover 12/20/2018, due 12/20/2021 – 3 years)
14F (last cover to cover 12/2018 next one 12/2021 – 3 years) (last cover to cover 4/10/2020, due 4/10/2022 – 2 years)
14G (last cover to cover 7/26/2018, due 7/26/2021 – 3 years)
19 (last cover to cover 12/2019, due 12/2021 – 2 years)
20 (last cover to cover 3/21/2019, due 3/21/2021 – 2 years)
21 (last cover to cover 5/1/2019, due 5/1/2021 – 2 years)
22 (last cover to cover 3/26/2020, due 3/26/2023 – 3 years)
14B moved to 3rd quarter -- hope to have some substantial changes along with the cover to cover which delayed the cover to cover
20 moved to 3rd quarter
Update from Lisa (6/16/21)
M14A last periodic review was published on 7/1/2020 which has a 3 year review cycle. This would be due for periodic review on 7/1/2023.
M14G last periodic review was published on 7/1/2020 which has a 3 year review cycle. This would be due for periodic review on 7/1/2023.
Note on B36: fernaa: Charter for RAAS indicates reporting to the PC, but no frequency mentioned
Note on B38: fernaa: Charter does not indicate reporting to the PC
Note on B39: fernaa: From Charter: The RS will develop an annual plan for the following year to be forwarded to the PC in November of each year.
Note on B40: fernaa: Charter mentions the LAS shall report to the PC (no mention of frequency)
Note on B41: fernaa: Charter - no mention of periodic reporting to PC or frequency

## Jan 2024 update
2024 Planning Committee Work Plan
|  | January - March |  | April - June | July - September | October - December
PC Manual Reviews | Manual 14A : New Service Request Process (3 YEARS) | Cover to cover review in Q3 2023, next 2026
| Manual 14B: Regional Transmission Planning Process (2 YEARS) | Cover to cover review in Q4 2023, next 2025
| Manual 14C: Generation & Transmission Interconnection Facility Construction (2 YEARS) | Cover to cover review in Q1 2023, next 2025
| Manual 14E: Additional Information for Upgrade & Transmission Interconnection Projects (3 YEARS) | Cover to cover review in Q3 2023, next 2026
| Manual 14F: Competitive Planning Process (2 YEARS) | Cover to cover review in Q2 2022, next 2024
| Manual 14G: Generation Interconnection Requests (3 YEARS) | Cover to cover review in Q3 2023, next 2026
| Manual 19: Load Forecasting & Analysis (2 YEARS) | Cover to cover review in Q4 2023, next 2025
| Manual 20: Resource Adequacy Analysis (2 YEARS) | Cover to cover review in Q3 2025
| Manual 21: Rules & Procedures for Determination of Generating Capability (2 YEARS) | Cover to cover review in Q3 2023, next 2025
| Manual 21A: Determination of Accredited UCAP Using Effective Load Carrying Capability Analysis (2 YEARS) | Cover to cover review in Q4 2025
| Manual 22: Generator Resource Performance Indices (3 YEARS) | Cover to cover review in Q1 2023, next 2026
PC Recurring Items | Review of PC Charter
*Transmission Expansion Advisory Committee (TEAC) and Sub-regional RTEP (SRRTEP) Meeting Information
*Interconnection Process Subcommittee
Model Build Activity Update
Reliability Compliance Update
Review and endorsement of IRM (or RRS) and FPR study assumptions
Review and endorsement of IRM (or RRS) study results
Review and endorsement of Load Model Selection
Review of Annual PJM Load Forecast
MOD-032 Data Requirements & Procedures document
Planning Resilience
Interconnection Process Subcommittee ( Bi-annual Updates)
Attachment M-3 Update
Transmission & Substation Subcommittee Update (May/Dec)
| Review of PC Charter |  | Complete
| Model Build Activity Update |  | In-Progress
| Reliability Compliance Update |  | Planned
Review and endorsement of IRM (or RRS) and FPR study assumptions
Review and endorsement of IRM (or RRS) study results
Review and endorsement of Load Model Selection
Review of Annual PJM Load Forecast
MOD-032 Data Requirements & Procedures document
Planning Resilience
Interconnection Process Subcommittee ( Bi-annual update)
Attachment M-3 Update
Transmission & Substation Subcommittee Update (May/Dec)