## Sheet1
Item Number | Stakeholder identifying item(s) | Action Item | Status | Date Entered | Date Closed | Age (days) | Owner
N/A | N/A | Review open questions on Planning Community | On-going | N/A | N/A | N/A | N/A
1 |  | Need to have a better understanding of what models are being used, when they change and if changed, this should be updated and communicated to all | Model attribute added to template | 2019-04-12 | 2019-10-11 | Closed
2 | Poulos | Interested in seeing some metrics put together around questions asked, responses provided, are they helpful or not, is more interaction/communication needed? | PJM posting Planning Community open questions | 2019-04-12 | 2020-02-04 | Closed | PJM
3 |  | Need to have a check in place to ensure the OA definition of a supplemental project is being adhered to | M14B language added | 2019-04-12 | 2019-08-22 | Closed
4 | Poulos | There needs to be more direct conversation/interaction between stakeholders & TO’s to clarify and provide what is needed. | Additional meetings available per the M-3 process | 2019-04-12 | 2019-10-11 | Closed
5 |  | Concerns raised that M-3 presentations occurring on PJM slides | Information no longer presented on PJM slides | 2019-04-12 | 2019-06-17 | Closed
6 |  | Develop something equivalent of a PJM Manual format for the M-3 Process | 10/11/2019 • Transmission Owners presented draft guidelines. • Stakeholders have indicated they will provide comments on the guidelines - suggesting some changes. Guidelines posted | 2019-04-12 | 2019-12-17 | Closed | TO
7 |  | Suggestion to retain the original slide and add any updated slide(s) (after questions/comments are addressed, the original slide gets replaced with the updates, and it is hard to track what changed, etc.) [7/12/2019] Some Needs statements are being modified after the Needs are presented [10/11/2019] Information removed from slides is difficult to track | PJM developed revision process to ensure tracking changes Verify all “revision control” for posted presentations and working papers | 2020-03-02 | 2020-03-02 | Closed | PJM/TO
8 |  | PJM should continue to reach out to the states as well to obtain their feedback | This is on-going | 2019-04-12 | 2019-10-22 | Closed
9 |  | Various requests to develop tracking mechanism for projects being discussed in M-3 process | Added table of M-3 process Needs | 2019-04-12 | 2019-04-12 | Closed
10 |  | Various requests for improvements to slides | Slide template improvements 1. Section introduction slides added 2. M-3 Process slide for reference 3. Bubble diagrams | 2019-04-12 | 2019-04-12 | Closed
11 |  | Stakeholders raised concerns regarding the availability of maps which show the facilities in question as the PJM maps do not have details of the lower voltage systems | Transmission Owners providing maps as required for lower voltage systems representations | 2019-04-12 | 2019-04-12 | Closed
12 |  | There is insufficient information about when a Solution is integrated into the PJM local Plan | PJM posts the Transmission Owners submission of projects for inclusion in the Local Plan and sends notices to the committee lists | 2019-07-12 | 2019-07-12 | Closed
13 | Various | TOs are presenting Needs but most are providing insufficient information to stakeholders to validate that the identified Needs are justified • Most of the TOs are not providing enough information or timely information for Stakeholders to replicate their results per FERC Show cause Orders • For condition drivers, TO’s present the number of structures and the number of open conditions, but only some provide the number of structures with open conditions • Most TOs cite the number of outages as a driver for condition/performance need, but do not provide cause of outages, and ordinarily do not have information on hand • [10/11/2019] Request that cause of outages be provided in addition to the number of outages • Some consistency needed with factors used to determine need based on performance, such as SAIDI, SAIFI and CAIDI, particularly as to # of years used to calculate and what data set is used (service to other utilities vs. vertically integrated distribution affiliate) • TOs cite age of initial line as vintage of entire line, without providing percentage of total line that is original vintage • There is no contact information on slides this creates more timing hurdles • 10-day input deadline is a deadline to fail when: 1. The proposal does not include an adequate level of information 2. Requests for information are left unanswered 3. There is no process to get answers or follow-up • Certain TOs are not providing information or appropriate granularity • Many of the criteria that are provided include poorly-defined or nonexistent criteria and no criteria thresholds • Additional transparency regarding criteria definitions requested • Many of the assumptions that are provided are overly broad or conservative, ill-defined, and/or include “catch all” statements • [10/11/2019] CAPS requests more details at the Needs meeting to add necessary value for CAPS participation in the Alternatives and Solutions phase • [10/11/2019] Some TOs providing conflicting Needs and Drivers • [10/11/2019] Needs not detailed enough in some cases for stakeholders to participate meaningfully in the process • Many Solutions address issues or assets not identified in the Needs statements • When an assumption is tied to an M3 need, please provide the quantitative value associated this assumption (ie: elevated gas levels yield x% increase in gas levels) (5/22/2020) • Where are actionable levels identified, can TO point to a criteria when they make statements along the lines of “elevated gas levels” (5/22/2020) | 4/19/21 - Items in underline italics closed following March 2021 PC M-3 update presentation with no stakeholder feedback |  | 2022-01-11 | Closed | TO
14 |  | Customers are scheduling periodic additional meetings with TOs to get detailed information on Assumptions, Needs, and Solutions. Working relatively well but entirely outside of the PJM planning process –not transparent or predictable and not consistent with the Show Cause Order | From OATT, M-3: No Limitation on Additional Meetings and Communications. Nothing in this Attachment M-3 precludes any Transmission Owner from agreeing with stakeholders to additional meetings or other communications regarding Supplemental Projects, in addition to the Subregional RTEP Committee process. | 2019-07-12 | 2019-11-15 | Closed | CLOSED
15 |  | Expectations that all questions must be presented in writing: 1. Creates access and timing issues 2. Significantly curtails the window of opportunity to discuss 3. Minimizes ability to have follow-up | QUESTIONS DOCUMENTED AS PART OF STAKEHOLDER MEETING OR PLANNING COMMUNITY TO ENSURE TRANSPARENCY. | 2019-07-12 | 2019-11-15 | Closed
16 |  | PJM not providing feedback –playing facilitator role 1. How engaged is PJM in the M-3 process? 2. It creates confusion when PJM plays such a limited role in the process. | PJM preparing M-3 Action Item list to track open issues. | 2019-07-12 | 2019-11-15 | Closed
17 | Poulos | The volume of Needs + lack of information + lateness of information when provided makes 10 day comment period unrealistic for Stakeholder comments | Covered by item 13 above | 2019-07-12 | 2019-11-15 | Closed
18 | Poulos | Some projects have received regulatory permits prior to the Need being presented | Need to determine if transmission owners can inventory projects which have already started development before M-3 process |  | 2021-04-19 | Closed | TO
19 |  | Concerns about project status not included for projects when solutions are presented | Status added to slide templates | 2019-07-12 | 2019-10-11 | Closed
20 |  | Most Transmission Owners are not providing all of the criteria, assumptions, and models 20 days prior to the assumptions meeting TO-specific models (not used by PJM) to justify “Needs” or “Solutions” are not accessible on PJM’s website (operational “snapshots”; non-PJM dispatched) | Need specific examples for cases not available. Operational dispatches will not be made available | 2020-03-02 | 2020-03-02 | Closed | PJM
21 |  | TO specific models used to identify Needs not available 20 days prior to Assumption Meetings 1. Only models made available are Power Flow models and cannot be used to replicate the process to identify a majority of “Needs”. 2. Power Flow models are not the drivers for the vast majority of these projects | Models for the planning process are the load flow, short circuit, and stability models. PJM has improved model availability and continues to develop additional capabilities through a SharePoint site | 2019-07-12 | 2019-07-12 | Closed
22 |  | Modeling files for potential solutions not being posted on PJM’s website in a timely manner | Models will only be posted on SharePoint site once development is complete in order to ensure CEII requirements met for safeguarding system representation in models | 2019-07-12 | 2019-07-12 | Closed
23 | Poulos | Most data and information requests are not addressed in timely manner or at all | M-3 ACTION ITEMS LIST | 2019-07-12 | 2019-11-15 | Closed
24 | Poulos | TO SMEs not available to respond to questions during the Meetings | PJM has seen increase in the attendance of meetings by various Transmission Owner SMEs. Will continue to monitor | 2019-07-12 | 2019-07-12 | Closed
25 |  | M-3 does not include any specified timeline between when a Need is submitted and a Solution is proposed When a credible, identified Need is identified – how long should it take to see a proposed Solution? Might Need criteria help? | PJM commits to an ongoing review of the open needs with the Transmission Owners to ensure the continuing validity of identified needs |  | 2023-03-07 | Closed | TO
26 | Poulos | Most TOs and PJM are not providing requested information about the Needs in sufficient time for other stakeholders to be able to propose alternatives | Needs provided in accordance with process time requirements. Additional action items tracking requests for transmission owners to provide additional information. | 2019-07-12 | 2019-11-15 | Closed
27 |  | Stakeholders are not notified about the finalization of Solutions and whether the finalized Solution is consistent with previously proposed Solution | PJM posts the Transmission Owners submission of projects for inclusion in the Local Plan and sends notices to the committee lists | 2019-07-12 | 2019-07-12 | Closed
28 |  | No required validation by PJM ensuring that the Solution does not cause harm to facilities not under PJM control | When the projects are posted for inclusion in the local plan, the projects have been studied and any reliability violations which may have resulted from the project are resolved and included in the solution submitted for inclusion in the local plan. If problems are indicated in the do no harm study, the stakeholders are advised through modification of project which had been originally proposed to mitigate the need | 2019-07-12 | 2019-07-12 | Closed
29 |  | PJM does not share the results of PJM’s Do No Harm analysis | When the projects are posted for inclusion in the local plan, the projects have been studied and any reliability violations which may have resulted from the project are resolved and included in the solution submitted for inclusion in the local plan. If problems are indicated in the do no harm study, the stakeholders are advised through modification of project which had been originally proposed to mitigate the need | 2019-07-12 | 2019-07-12 | Closed
30 | ODEC | Are drivers and driver details consistent across a TO’s projects? Across TO’s? Looking for more information at the needs phase Desire to have a ranking of Needs – more information at the Needs phase is desired. Desire for “ranking/prioritizing” Needs |  |  | 2022-01-11 | Closed | TO
31 | Transmission Owner | Can stakeholders present input in specific terms and or actionable requests? Generalities are not productive or constructive | No further action needed | 2019-10-11 | 2019-10-11 | Closed
32 | Transmission Owner | Transmission Owners invited closer, continued participation in the Sub-Regional meetings | No action needed | 2019-10-11 | 2019-10-11 | Closed
33 | CAPS | Responsiveness to Planning Community questions is improving but frustration continues from non-responses. Better to receive a “No or No Answer” rather than non-response. Looking for training on Planning Community concerning how to enter information | 10/11/2019 PJM to explore adding response to all questions: 1. Provided question to the applicable stakeholder 2. Slide updated to address question 3. Response posted in Planning Community 4. Other possible responses? PJM will note in Planning Community when questions have been provided to the transmission owners (if applicable), will provide a response if question is to PJM, and will update in all cases if additional information is provided PJM to set up training for Planning Community |  | 2021-04-19 | Closed | PJM
34 | ODEC | Can we add a Action Items agenda item for each Sub regional meeting to constructively improve in a more timely manner? | Adding review to each subregional and TEAC meeting | 2019-10-11 | 2020-02-04 | Closed | PJM
35 | Susan Bruce | Susan Bruce – can common understanding and expectations be provided for the “10 day” post meeting comment period? What happens within and beyond that date? | PJM has provided explanation that 10 day period does not stop ability of stakeholder to enter comments in the Planning Community | 2020-03-02 | 2020-03-02 | Closed | TO
36 | CAPS | Additional TO Sub-regional Meetings - CAPS requests that this be “teased out” | M-3 process provides for additional meetings under item 7 of Attachment M-3 | 2019-10-11 | 2020-01-16 | Closed | PJM
37 |  | M-3 meetings has a different “appearance” than other stakeholder meetings due to the construct of PJM facilitator, TO meeting owner and PJM SME (Author’s note – not sure this is a precedent e.g. the Finance Committee is comprised of PJM SMEs, Members and 2 Board Members | CLOSE - OUTSIDE SCOPE OF M-3 PROCESS / FERC FILING | 2019-10-11 | 2019-11-15 | Closed
38 | ODEC | Projects in an area being brought in a piecemeal fashion | PJM preparing next round of maps to show high level view of projects in various areas around the system SRRTEP & TEAC meeting postings of aggregate maps | 2019-10-11 | 2020-02-04 | Closed | PJM
39 | Buckeye Power | Concerns about how to identify their needs to the Transmission Owners | Stakeholders should identify their needs to their local Transmission Owner as the Transmission Owner is the entity who can construct a Supplemental Project | 2019-10-11 | 2019-10-11 | Closed
40 | Dolan | Request to add information on slides relating to other supplemental projects and baseline upgrades which may be in the electrical vicinity of the M-3 need being discussed | PJM continues the development of mapping technologies including enhancements that provide location of projects at submittal of solution. In the meantime, PJM is continuing manual efforts due to higher priorities for the capital project portfolio. | 2020-06-19
Formulas:
Age (days) = IF([Date Entered]="","",IF([Date Closed]="",TODAY()-[Date Entered],"Closed"))