## Appendix
Region | UpgradeId | Description | Transmission Owner | Immediate Need | Project Submittal Number | Drivers | Required In-Service Date | Status | Initial TEAC Cost ($M) | Latest TEAC Cost ($M) | Board Approval Date | Issue Category
PJM MA | b2752.1 | Tap the Peach Bottom – TMI 500 kV line & create new Furnace Run 500 kV & 230 kV stations. Install two 500/230 kV transformers, operated together. | Transource |  | 201415_1-9A | Congestion Relief - Economic | 6/1/2020 | Cancelled | 44.66 |  | 8/2/2016 | Scope/Cost Change
PJM MA | b2752.2 | Tie in new Furnace Run substation to Peach Bottom-TMI 500 kV | PECO |  | 201415_1-9A | Congestion Relief - Economic | 6/1/2020 | Cancelled | 5.5 |  | 8/2/2016 | Scope/Cost Change
PJM MA | b2752.3 | Upgrade terminal equipment and required relay communication at Peach Bottom 500 kV: on the Peach Bottom - TMI 500 kV circuit | PECO |  | 201415_1-9A | Congestion Relief - Economic | 6/1/2020 | Cancelled | 2 |  | 8/2/2016 | Scope/Cost Change
PJM MA | b2752.5 | Build new 230 kV double circuit line between Furnace Run and Conastone 230 kV, operated as a single circuit. | Transource |  | 201415_1-9A | Congestion Relief - Economic | 6/1/2020 | Cancelled | 39.72 |  | 8/2/2016 | Scope/Cost Change
PJM MA | b2752.6 | Conastone 230 kV substation tie-in work (install a new circuit breaker at Conastone 230 kV and upgrade any required terminal equipment to terminate the new circuit) | BGE |  | 201415_1-9A | Congestion Relief - Economic | 6/1/2020 | Cancelled | 4.12 |  | 8/2/2016 | Scope/Cost Change
PJM MA | b2752.7 | Reconductor/Rebuild the two Conastone - Northwest 230 kV lines and upgrade terminal equipment on both ends | BGE |  | 201415_1-9A | Congestion Relief - Economic | 6/1/2020 | Cancelled | 45.88 |  | 8/2/2016 | Scope/Cost Change
PJM MA | b2752.8 | Replace the Conastone 230kV '2322 B5' breaker with a 63kA breaker | BGE | X | 201415_1-9A | Short Circuit | 6/1/2020 | Cancelled | 0.537 |  | 12/5/2017 | Scope/Cost Change
PJM MA | b2752.9 | Replace the Conastone 230kV '2322 B6' breaker with a 63kA breaker | BGE | X | 201415_1-9A | Short Circuit | 6/1/2020 | Cancelled | 0.537 |  | 12/5/2017 | Scope/Cost Change
PJM WEST | b3333.1 | Rebuild Skeggs Branch substation in the clear as Mount Heron substation. Establish New 138 kV and 69 kV buses. Install 138/69 kV 130 MVA transformer, two 138 kV breakers, 138 kV circuit switcher, two 69 kV breaker. Retire existing Skeggs Branch substation. | AEP |  |  | Generator Deactivation | 6/1/2023 | EP | 6.315 | 9.935 | 9/22/2021 | Scope/Cost Change
PJM WEST | b3333.10 | At Whetstone Branch substation, replace 69 KV 600 A 2 way POP switch with 69 KV 1200 A 2 way POP switch. Remove 69 kV to Skeggs Branch (switch "22" POP). | AEP |  |  | Generator Deactivation | 6/1/2023 | EP | 0.568 | 1.695 | 9/22/2021 | Scope/Cost Change
PJM WEST | b3333.11 | At Garden Creek substation, remove 69 kV Richlands (via Coal Creek) line (circuit breaker F and disconnect switches) and update relay settings. | AEP |  |  | Generator Deactivation | 6/1/2023 | EP | 0.138 | 0.537 | 9/22/2021 | Scope/Cost Change
PJM WEST | b3333.14 | Install ~2.6 mi greenfield 69 kV line from greenfield Mount Heron station to the existing Horn Mountain S.S. | AEP |  |  | Generator Deactivation | 6/1/2023 | PL | 18.015 |  |  | Scope/Cost Change
PJM WEST | b3333.2 | New ~1.6 mi double circuit 138 kV extension to new Mount Heron substation location and work required to tap the Clinch River-Garden Creek 138 kV line. Retire the existing Skeggs Branch 138 kV tap. | AEP |  |  | Generator Deactivation | 6/1/2023 | EP | 4.62 | 19.144 | 9/22/2021 | Scope/Cost Change
PJM WEST | b3333.3 | Install a 57.6 MVAR cap bank at Whitewood substation along with a 138 kV breaker. | AEP |  |  | Generator Deactivation | 6/1/2023 | EP | 1.05 | 2.765 | 9/22/2021 | Scope/Cost Change
PJM WEST | b3333.4 | Rebuild ~9 mi 69 kV line from Horn Mountain SS to Permac switch. Rebuild from Str. 340-28 to Coal Creek station. 6-wire the short double circuit section between Whetstone Branch and Str. 340-28 to convert the line to single circuit. Retire the Garden Creek to Whetstone Branch 69 kV line section. | AEP |  |  | Generator Deactivation | 6/1/2023 | EP | 26.25 | 45.304 | 9/22/2021 | Scope/Cost Change
PJM WEST | b3333.6 | At Horn Mountain SS, replace 600 A switch and structure with a 3 way 1200 A POP pole switch and pole. | AEP |  |  | Generator Deactivation | 6/1/2023 | EP | 0.05 | 1.987 | 9/22/2021 | Scope/Cost Change
PJM WEST | b3333.7 | At Clell SS, replace two 600 A POP switches and poles with single 3 way 1200 A POP switch and pole. | AEP |  |  | Generator Deactivation | 6/1/2023 | EP | 0.34 | 1.796 | 9/22/2021 | Scope/Cost Change
PJM WEST | b3333.8 | At Permac, replace 600 A switch and structure with 2 Way 1200 A POP pole switch and pole. | AEP |  |  | Generator Deactivation | 6/1/2023 | EP | 0.31 | 2.503 | 9/22/2021 | Scope/Cost Change
PJM WEST | b3333.9 | At Marvin SS, Replace 600 A Switch and structure with 3 Way 1200 A POP pole switch and pole. | AEP |  |  | Generator Deactivation | 6/1/2023 | EP | 0.31 | 2.688 | 9/22/2021 | Scope/Cost Change
PJM MA | b3869.1 | Relocate the Bergen Gen #1 point of interconnection from Bergen 138kV to Bergen 345kV GIS through the existing 345/138kV transformer. | PSEG |  |  | Baseline Load Growth Deliverability & Reliability | 12/1/2029 | Cancelled | 6.8 |  | 2/26/2025 | Scope/Cost Change
PJM MA | b3869.2 | Remove and retire the two (2) existing Bergen 138kV Series Reactors and associated ancillary equipment. | PSEG |  |  | Baseline Load Growth Deliverability & Reliability | 12/1/2029 | Cancelled | 5.7 |  | 2/26/2025 | Scope/Cost Change
PJM MA | b3869.3 | Replace the two Bergen 138 kV series reactors with two new dry type 138 kV series reactors. | PSEG |  |  | Baseline Load Growth Deliverability & Reliability | 12/1/2029 | PL | 12.77 |  |  | Scope/Cost Change
PJM WEST | b3936.1 | AEP Zone 2024W1 P5 Solution #1: Install battery chargers & associated equipment at AEP substation. Addresses the following FGs: 2024-P5-AEP07, 2024-P5-AEP08. | AEP |  |  | Baseline Load Growth Deliverability & Reliability | 6/1/2029 | PL | 0.070874 | 0.070874 |  | New Upgrade
PJM WEST | b3936.2 | AEP Zone 2024W1 P5 Solution #2: Install battery chargers & associated equipment at AEP substation. Addresses the following FG's: 2024-P5-AEP03, 2024-P5-AEP04 | AEP |  |  | Baseline Load Growth Deliverability & Reliability | 6/1/2029 | PL | 0.10996 | 0.10996 |  | New Upgrade
PJM WEST | b3936.3 | AEP Zone 2024W1 P5 Solution #3: Install battery chargers & associated equipment at AEP substation. Addresses the following FG's: 2024-P5-AEP09, 2024-P5-AEP10, 2024-P5-AEP11, 2024-P5-AEP12. | AEP |  |  | Baseline Load Growth Deliverability & Reliability | 6/1/2029 | PL | 0.084516 | 0.084516 |  | New Upgrade
PJM WEST | b3936.4 | AEP Zone 2024W1 P5 Solution #4: Install battery chargers & associated equipment at AEP substation. Addresses the following FG's: 2024-P5-AEP05. | AEP |  |  | Baseline Load Growth Deliverability & Reliability | 6/1/2029 | PL | 0.121 | 0.121 |  | New Upgrade
PJM WEST | b3936.5 | AEP Zone 2024W1 P5 Solution #5: Install battery chargers & associated equipment at AEP substation. Addresses the following FG's: 2024-P5-AEP01. | AEP |  |  | Baseline Load Growth Deliverability & Reliability | 6/1/2029 | PL | 0.089118 | 0.089118 |  | New Upgrade
PJM WEST | b3936.6 | AEP Zone 2024W1 P5 Solution #6: Install battery chargers & associated equipment and upgrade protection equipment at OVEC substation. Addresses the following FG's: 2024-P5-AEP02. | AEP |  |  | Baseline Load Growth Deliverability & Reliability | 6/1/2029 | PL | 0.58203 | 0.58203 |  | New Upgrade
PJM WEST | b3936.7 | AEP Zone 2024W1 P5 Solution #7: Install battery chargers & associated equipment at AEP substation. Addresses the following FG's: 2024-P5-AEP06. | AEP |  |  | Baseline Load Growth Deliverability & Reliability | 6/1/2029 | PL | 0.14634 | 0.14634 |  | New Upgrade
PJM SOUTH | b3937.1 | 2024W1 DVP P5 Solution #1 - DC Supply Monitoring: Addressing FG # 2024-P5-DVP01 | Dominion |  |  | Baseline Load Growth Deliverability & Reliability | 6/1/2029 | PL | 0.02 | 0.02 |  | New Upgrade
PJM SOUTH | b3937.10 | 2024W1 DVP P5 Solution #10 - DC Supply Monitoring: Addressing FG # 2024-P5-DVP10 | Dominion |  |  | Baseline Load Growth Deliverability & Reliability | 6/1/2029 | PL | 0.02 | 0.02 |  | New Upgrade
PJM SOUTH | b3937.11 | 2024W1 DVP P5 Solution #11 - DC Supply Monitoring: Addressing FG # 2024-P5-DVP11 | Dominion |  |  | Baseline Load Growth Deliverability & Reliability | 6/1/2029 | PL | 0.02 | 0.02 |  | New Upgrade
PJM SOUTH | b3937.12 | 2024W1 DVP P5 Solution #12 - DC Supply Monitoring: Addressing FG # 2024-P5-DVP12 | Dominion |  |  | Baseline Load Growth Deliverability & Reliability | 6/1/2029 | PL | 0.02 | 0.02 |  | New Upgrade
PJM SOUTH | b3937.13 | 2024W1 DVP P5 Solution #13 - DC Supply Monitoring: Addressing FG # 2024-P5-DVP13 | Dominion |  |  | Baseline Load Growth Deliverability & Reliability | 6/1/2029 | PL | 0.02 | 0.02 |  | New Upgrade
PJM SOUTH | b3937.14 | 2024W1 DVP P5 Solution #14 - DC Supply Monitoring: Addressing FG # 2024-P5-DVP14 | Dominion |  |  | Baseline Load Growth Deliverability & Reliability | 6/1/2029 | PL | 0.02 | 0.02 |  | New Upgrade
PJM SOUTH | b3937.15 | 2024W1 DVP P5 Solution #15 - DC Supply Monitoring: Addressing FG # 2024-P5-DVP15 | Dominion |  |  | Baseline Load Growth Deliverability & Reliability | 6/1/2029 | PL | 0.02 | 0.02 |  | New Upgrade
PJM SOUTH | b3937.16 | 2024W1 DVP P5 Solution #16 - DC Supply Monitoring: Addressing FG # 2024-P5-DVP16 | Dominion |  |  | Baseline Load Growth Deliverability & Reliability | 6/1/2029 | PL | 0.02 | 0.02 |  | New Upgrade
PJM SOUTH | b3937.17 | 2024W1 DVP P5 Solution #17 - DC Supply Monitoring: Addressing FG # 2024-P5-DVP17 | Dominion |  |  | Baseline Load Growth Deliverability & Reliability | 6/1/2029 | PL | 0.02 | 0.02 |  | New Upgrade
PJM SOUTH | b3937.18 | 2024W1 DVP P5 Solution #18 - DC Supply Monitoring: Addressing FG # 2024-P5-DVP18 | Dominion |  |  | Baseline Load Growth Deliverability & Reliability | 6/1/2029 | PL | 0.02 | 0.02 |  | New Upgrade
PJM SOUTH | b3937.19 | 2024W1 DVP P5 Solution #19 - DC Supply Monitoring: Addressing FG # 2024-P5-DVP19 | Dominion |  |  | Baseline Load Growth Deliverability & Reliability | 6/1/2029 | PL | 0.02 | 0.02 |  | New Upgrade
PJM SOUTH | b3937.2 | 2024W1 DVP P5 Solution #2 - DC Supply Monitoring: Addressing FG # 2024-P5-DVP02 | Dominion |  |  | Baseline Load Growth Deliverability & Reliability | 6/1/2029 | PL | 0.02 | 0.02 |  | New Upgrade
PJM SOUTH | b3937.20 | 2024W1 DVP P5 Solution #20 - DC Supply Monitoring: Addressing FG # 2024-P5-DVP20 | Dominion |  |  | Baseline Load Growth Deliverability & Reliability | 6/1/2029 | PL | 0.02 | 0.02 |  | New Upgrade
PJM SOUTH | b3937.21 | 2024W1 DVP P5 Solution #21 - DC Supply Monitoring: Addressing FG # 2024-P5-DVP21 | Dominion |  |  | Baseline Load Growth Deliverability & Reliability | 6/1/2029 | PL | 0.02 | 0.02 |  | New Upgrade
PJM SOUTH | b3937.22 | 2024W1 DVP P5 Solution #22 - DC Supply Monitoring: Addressing FG # 2024-P5-DVP23 | Dominion |  |  | Baseline Load Growth Deliverability & Reliability | 6/1/2029 | PL | 0.02 | 0.02 |  | New Upgrade
PJM SOUTH | b3937.23 | 2024W1 DVP P5 Solution #23 - DC Supply Monitoring: Addressing FG # 2024-P5-DVP24 | Dominion |  |  | Baseline Load Growth Deliverability & Reliability | 6/1/2029 | PL | 0.02 | 0.02 |  | New Upgrade
PJM SOUTH | b3937.24 | 2024W1 DVP P5 Solution #24 - DC Supply Monitoring: Addressing FG # 2024-P5-DVP26 | Dominion |  |  | Baseline Load Growth Deliverability & Reliability | 6/1/2029 | PL | 0.02 | 0.02 |  | New Upgrade
PJM SOUTH | b3937.25 | 2024W1 DVP P5 Solution #25 - DC Supply Monitoring: Addressing FG # 2024-P5-DVP27 | Dominion |  |  | Baseline Load Growth Deliverability & Reliability | 6/1/2029 | PL | 0.02 | 0.02 |  | New Upgrade
PJM SOUTH | b3937.26 | 2024W1 DVP P5 Solution #26 - DC Supply Monitoring: Addressing FG # 2024-P5-DVP28 | Dominion |  |  | Baseline Load Growth Deliverability & Reliability | 6/1/2029 | PL | 0.02 | 0.02 |  | New Upgrade
PJM SOUTH | b3937.27 | 2024W1 DVP P5 Solution #27 - DC Supply Monitoring: Addressing FG # 2024-P5-DVP29 | Dominion |  |  | Baseline Load Growth Deliverability & Reliability | 6/1/2029 | PL | 0.02 | 0.02 |  | New Upgrade
PJM SOUTH | b3937.28 | 2024W1 DVP P5 Solution #28 - DC Supply Monitoring: Addressing FG # 2024-P5-DVP30 | Dominion |  |  | Baseline Load Growth Deliverability & Reliability | 6/1/2029 | PL | 0.02 | 0.02 |  | New Upgrade
PJM SOUTH | b3937.29 | 2024W1 DVP P5 Solution #29 - DC Supply Monitoring: Addressing FG # 2024-P5-DVP31 | Dominion |  |  | Baseline Load Growth Deliverability & Reliability | 6/1/2029 | PL | 0.02 | 0.02 |  | New Upgrade
PJM SOUTH | b3937.3 | 2024W1 DVP P5 Solution #3 - DC Supply Monitoring: Addressing FG # 2024-P5-DVP03 | Dominion |  |  | Baseline Load Growth Deliverability & Reliability | 6/1/2029 | PL | 0.02 | 0.02 |  | New Upgrade
PJM SOUTH | b3937.30 | 2024W1 DVP P5 Solution #30 - DC Supply Monitoring: Addressing FG # 2024-P5-DVP32 | Dominion |  |  | Baseline Load Growth Deliverability & Reliability | 6/1/2029 | PL | 0.02 | 0.02 |  | New Upgrade
PJM SOUTH | b3937.31 | 2024W1 DVP P5 Solution #31 - DC Supply Monitoring: Addressing FG # 2024-P5-DVP33 | Dominion |  |  | Baseline Load Growth Deliverability & Reliability | 6/1/2029 | PL | 0.02 | 0.02 |  | New Upgrade
PJM SOUTH | b3937.32 | 2024W1 DVP P5 Solution #32 - DC Supply Monitoring: Addressing FG # 2024-P5-DVP34 | Dominion |  |  | Baseline Load Growth Deliverability & Reliability | 6/1/2029 | PL | 0.02 | 0.02 |  | New Upgrade
PJM SOUTH | b3937.33 | 2024W1 DVP P5 Solution #33 - DC Supply Monitoring: Addressing FG # 2024-P5-DVP35 | Dominion |  |  | Baseline Load Growth Deliverability & Reliability | 6/1/2029 | PL | 0.02 | 0.02 |  | New Upgrade
PJM SOUTH | b3937.34 | 2024W1 DVP P5 Solution #34 - DC Supply Monitoring: Addressing FG # 2024-P5-DVP36 | Dominion |  |  | Baseline Load Growth Deliverability & Reliability | 6/1/2029 | PL | 0.02 | 0.02 |  | New Upgrade
PJM SOUTH | b3937.35 | 2024W1 DVP P5 Solution #35 - DC Supply Monitoring: Addressing FG # 2024-P5-DVP37 | Dominion |  |  | Baseline Load Growth Deliverability & Reliability | 6/1/2029 | PL | 0.02 | 0.02 |  | New Upgrade
PJM SOUTH | b3937.36 | 2024W1 DVP P5 Solution #36 - DC Supply Monitoring: Addressing FG # 2024-P5-DVP38 | Dominion |  |  | Baseline Load Growth Deliverability & Reliability | 6/1/2029 | PL | 0.02 | 0.02 |  | New Upgrade
PJM SOUTH | b3937.37 | 2024W1 DVP P5 Solution #37 - DC Supply Monitoring: Addressing FG # 2024-P5-DVP39 | Dominion |  |  | Baseline Load Growth Deliverability & Reliability | 6/1/2029 | PL | 0.02 | 0.02 |  | New Upgrade
PJM SOUTH | b3937.38 | 2024W1 DVP P5 Solution #38 - DC Supply Monitoring: Addressing FG # 2024-P5-DVP40 | Dominion |  |  | Baseline Load Growth Deliverability & Reliability | 6/1/2029 | PL | 0.02 | 0.02 |  | New Upgrade
PJM SOUTH | b3937.39 | 2024W1 DVP P5 Solution #39 - DC Supply Monitoring: Addressing FG # 2024-P5-DVP41 | Dominion |  |  | Baseline Load Growth Deliverability & Reliability | 6/1/2029 | PL | 0.02 | 0.02 |  | New Upgrade
PJM SOUTH | b3937.4 | 2024W1 DVP P5 Solution #4 - DC Supply Monitoring: Addressing FG # 2024-P5-DVP04 | Dominion |  |  | Baseline Load Growth Deliverability & Reliability | 6/1/2029 | PL | 0.02 | 0.02 |  | New Upgrade
PJM SOUTH | b3937.5 | 2024W1 DVP P5 Solution #5 - DC Supply Monitoring: Addressing FG # 2024-P5-DVP05 | Dominion |  |  | Baseline Load Growth Deliverability & Reliability | 6/1/2029 | PL | 0.02 | 0.02 |  | New Upgrade
PJM SOUTH | b3937.6 | 2024W1 DVP P5 Solution #6 - DC Supply Monitoring: Addressing FG # 2024-P5-DVP06 | Dominion |  |  | Baseline Load Growth Deliverability & Reliability | 6/1/2029 | PL | 0.02 | 0.02 |  | New Upgrade
PJM SOUTH | b3937.7 | 2024W1 DVP P5 Solution #7 - DC Supply Monitoring: Addressing FG # 2024-P5-DVP07 | Dominion |  |  | Baseline Load Growth Deliverability & Reliability | 6/1/2029 | PL | 0.02 | 0.02 |  | New Upgrade
PJM SOUTH | b3937.8 | 2024W1 DVP P5 Solution #8 - DC Supply Monitoring: Addressing FG # 2024-P5-DVP08 | Dominion |  |  | Baseline Load Growth Deliverability & Reliability | 6/1/2029 | PL | 0.02 | 0.02 |  | New Upgrade
PJM SOUTH | b3937.9 | 2024W1 DVP P5 Solution #9 - DC Supply Monitoring: Addressing FG # 2024-P5-DVP09 | Dominion |  |  | Baseline Load Growth Deliverability & Reliability | 6/1/2029 | PL | 0.02 | 0.02 |  | New Upgrade
PJM MA | b3939.1 | 2024W1 PSEG P5 Solution #1 - Battery monitoring upgrades at PSEG substation. Addresses FG #2024-P5-PSEG01 | PSEG |  |  | Baseline Load Growth Deliverability & Reliability | 6/1/2029 | PL | 0.075 | 0.075 |  | New Upgrade
PJM MA | b3939.2 | 2024W1 PSEG P5 Solution #2 - Battery monitoring upgrades at PSEG substation. Addresses FG #2024-P5-PSEG02 | PSEG |  |  | Baseline Load Growth Deliverability & Reliability | 6/1/2029 | PL | 0.075 | 0.075 |  | New Upgrade
PJM MA | b3939.3 | 2024W1 PSEG P5 Solution #3 - Battery monitoring upgrades at PSEG substation. Addresses FG #2024-P5-PSEG03 | PSEG |  |  | Baseline Load Growth Deliverability & Reliability | 6/1/2029 | PL | 0.075 | 0.075 |  | New Upgrade
PJM MA | b3939.4 | 2024W1 PSEG P5 Solution #4 - Battery monitoring upgrades at PSEG substation. Addresses FG #2024-P5DYN-PSEG01 | PSEG |  |  | Baseline Load Growth Deliverability & Reliability | 6/1/2029 | PL | 0.075 | 0.075 |  | New Upgrade
PJM MA | b3939.5 | 2024W1 PSEG P5 Solution #5 - Battery monitoring upgrades at PSEG substation. Addresses FG #2024-P5DYN-PSEG02 | PSEG |  |  | Baseline Load Growth Deliverability & Reliability | 6/1/2029 | PL | 0.075 | 0.075 |  | New Upgrade
PJM WEST | b4000.200 | Broadford 765 kV Upgrade: Replace Jackson's Ferry CB Q2 | AEP |  | 2024-W1-81 | Baseline Load Growth Deliverability & Reliability | 6/1/2029 | Cancelled | 4.5 |  | 2/26/2025 | Scope/Cost Change