## Order 2222 Work Plan
DRAFT - last updated March 10, 2022
DER Aggregation work streams / implementation items | Prioritization | PJM Stakeholder Body | Notes
Defining 'electric distribution company' |  | TBD | What is the appropriate venue for discussion? Probably need a broader audience than that DIRS
Registration and utility review process | Higher | DIRS | Compare this process with existing DR process.
DER locational data / Ops resource modeling |  | DIRS
Software functionality / implementation |  | DIRS
Timing of various activities / timelines / deadlines |  | DIRS
Utility reliability review studies - education |  | DIRS
DER and aggregator unit specific data and profile information |  | DIRS
Pre-registration coordination |  | DIRS | Discuss uniform approach to this process.
Recurring registration review |  | DIRS
Timing of registration process relative to market participation |  | DIRS
DER Aggregation Resource settlement process |  | Market Settlement Subcommittee (likely) | What is the appropriate venue for discussion?
Cyber security best practices coordination |  |  | Add to state coordination workshop.
State coordination / retail DER policy workshops
Additional and more detailed use cases |  |  | Highlight metering and telemetry requirements. Electric vehicle registration.
Planned DER Capacity Aggregation Resources - Sell Offer Plans | Higher, given timing of 23/24 BRA | DIRS
DER data for planning model
Coordination with NERC standard updates to TPL-001-5.1 and MOD-032-1 |  | Planning Committee?