## 2025 WORK PLAN
Distributed Resources Subcommittee (DISRS) - Work Plan
DISRS Working Items
FERC Order 2222 - Active
Wind & Solar Resource Dispatch in Real-Time Market Clearing Engines - Active
DER Regulation Market Only Participation at NEM Customer Sites - Under Stakeholder Review
Updated: April 21, 2025
Detailed Work Plan -- FERC Order 2222 Compliance | 1.10.2025 | 2.3.2025 | 3.3.2025 | 4.4.2025 | 5.5.2025 | 6.6.2025 | 7.7.2025 | 8.4.2025 | 9.8.2025 | 10.6.2025 | 11.3.2025 | 12.1.2025
DER Implementation Details |  | X | X | X | X | X | X | X | X
Manual Updates (M18, etc.) | [6 empty] | X | X | X | X | X | X
Key 28/29 BRA Activities (in 2026) | [11 empty] | X
Post DER Plan Template | [9 empty] | X
Submit DER Plans | [11 empty] | X
MOPR Certification | [11 empty] | X
Unit Specific MSOC & MOPR Request (in 2026)
28/29 BRA (in 2026)
Detailed Work Plan -- Wind and Solar Resource Dispatch in Real-Time Market Clearing Engines | 1.10.2025 | 2.3.2025 | 3.3.2025 | 4.4.2025 | 5.5.2025 | 6.2.2025 MIC | 7.9.2025 MIC | 7.23.2025 MRC | 8.20.2025 MRC | 9.25.2025 MC
Review Issue Charge and Problem Statement
Provide Education
Develop & Review Interests
Develop & Review Design Components & Status Quo | X
Develop & Refine Solution Options | X | X | X
Develop & Refine Solution Packages |  | X | X | X | X
Build Consensus |  |  | X | X | X
First Read - MIC | [5 empty] | X
Vote - MIC | [6 empty] | X
First Read - MRC | [7 empty] | X
Vote - MRC | [8 empty] | X
Vote - MC | [9 empty] | X
Detailed Work Plan -- DER Regulation Market Only Participaton at NEM Customer Sites | 1.10.2025 | 2.3.2025 | 3.3.2025 | 4.4.2025 | 5.7.2025 MIC | 6.2.2025 MIC | 6.18.2025 MRC | 7.23.2025 MRC | 8.20.2025 MC
Provide Education | X
Develop & Review Interests |  | X | X
Develop & Review Design Components & Status Quo |  | X | X
Develop & Refine Solution Options |  | X | X | X
Develop & Refine Solution Packages |  | X |  | X
Build Consensus |  |  |  | X
First Read - MIC |  |  |  |  | X
Vote - MIC | [5 empty] | X
First Read - MRC | [6 empty] | X
Vote - MRC | [7 empty] | X
Vote - MC | [8 empty] | X

## 2023-24 WORK PLAN
Distributed Resources Subcommittee (DISRS) - Work Plan
DISRS Working Items |  | 2023 |  |  |  | 2024
| Jan - Mar | Apr - Jun | Jul - Sep | Oct - Dec | Jan - Mar | Apr - Jun | Jul - Sep | Oct - Dec
FERC Order 2222 - Resumed
DR/PRD Compliance Construct for Weather Sensitive Load - Closed
Economic Demand Response Automate Bid Duration - Closed
Hybrid Resources Enhancements (Hybrid Phase 3) - Stakeholder Review & Endorsement
Wind & Solar Resource Dispatch in Real-Time Market Clearing Engines - Active
Updated: November 18, 2024
Detailed Work Plan -- FERC Order 2222 Compliance | Previous DIRS Meetings | 1.9.2023 | 2.6.2023 | 3.6.2023 | 4.10.2023 | 5.8.2023 | 5.25.2023 | 6.5.2023 | 6.23.2023 | 7.14.2023 | 7.31.2023 | 8.16.2023 | 10.10.2023 | 11.3.2023 | 12.4.2023 | 1.8.2024 | 2.5.2024 | 3.4.2024 | 4.1.2024 | 4.29.2024 | 6.3.2024 | 7.8.2024 | 8.5.2024 | 9.9.2024 | 10.7.2024 | 11.4.2024 | 12.2.2024
Overview of the Order | X
Education | X
Stakeholder Feedback and Discussion | X
EDC Coordination Workshop - 2 hour meetings | X
Straw Proposal Discussion | X
Compliance Proposal Development | X
Compliance Filing - Tariff Review | X
Compliance Filing Due Date - Feb 1, 2022 | X | Awaiting FERC Order
Order on Compliance Filing - issued Mar 1, 2023, due Sept 1, 2023 (extension requested and received) |  |  |  | X | X | X | X | X | X | X | X | X
Implementation Discussions | [14 empty] | X | X
Order 2222 - Compliance Order - topics by meeting date
Capacity mitigation |  |  |  |  | X
Utility review process; information and data; dispatch agent; electric distribution company definition; operational coordination; | [5 empty] | X
Net Energy Metering; double counting; Metering and Telemetry; + previous topics | [6 empty] | X
Locational requirements; + previous topics | [7 empty] | X
Information and Data; reliability criteria; dispute resolution; + previous topics | [8 empty] | X
Continuous model and participaton criteria; +previous topics | [9 empty] | X
DER Opt-In, DR Opt-Out, Locational Requirements and EDC Definition + previous topics | [10 empty] | X
Effective dates and Tariff redline review | [11 empty] | X
Compliance filing due to FERC by Sept 1, 2023 | [11 empty] | X
Clarification review on PJM's filing regarding effective dates | [12 empty] | X
Requirements on DER plan for the capacity aggregation resources | [14 empty] | X | X | X
Registration process | [14 empty] | X |  |  | Waiting on FERC's response
Overview of FERC's Response | [22 empty] | X | X | X |  | X
Detailed Work Plan -- Capacity Compliance Weather Sensitive Load | Previous DRS Meetings | 1.9.2023 | 2.6.2023 | 3.6.2022 | 4.10.2023 | 5.8.2023 | 5.25.2023 | 6.5.2023 | 6.23.2023 | 7.14.2023 | 7.31.2023 | 8.16.2023 | 10.10.2023 | 11.3.2023 | 12.4.2023 | 1.8.2024 | 2.5.2024 | 3.6.2024 MIC | 4.3.2024 MIC
Provide Education
Review Documented Interests | X
Review Developed Design Components | X
Develop & Refine Solution Options | X
Develop & Refine Solution Packages |  | X | X
Build Consensus |  |  |  | X
First Read - MIC |  |  |  |  | On Hold
Discuss next steps | [15 empty] | X | X
First Read - MIC | [17 empty] | X
Vote - MIC | [18 empty] | X
Issue is Closed | [18 empty] | X
Detailed Work Plan -- Economic Demand Response Automate Bid Duration |  | 1.9.2023 | 2.6.2023 | 3.6.2023 | 4.10.2023 | 5.8.2023 | 5.25.2023 | 6.5.2023 | 6.23.2023 | 7.14.2023 | 7.31.2023 | 8.16.2023 | 10.10.2023 | 11.3.2023 | 12.4.2023 | 1.8.2024 | 2.5.2024 | 3.4.2024 | 5.1.2024 MIC | 6.5.2024 MIC | 7.24.2024 MRC | 8.21.2024 MRC | 9.25.2024 MC
Review Initial Issue Charge and Problem Statement | [5 empty] | X
Provide Status Update | [7 empty] | X
Review Updated Issue Charge | [9 empty] | X |  |  |  |  | X
Provide Education | [10 empty] | On Hold due to MIC |  |  |  | X
Develop & Review Interests | [14 empty] | X | X
Develop & Review Design Components | [15 empty] | X | X
Develop & Refine Solution Options | [15 empty] | X | X | X
Develop & Refine Solution Packages | [16 empty] | X | X
Build Consensus | [16 empty] | X | X
First Read - MIC | [18 empty] | X
Vote - MIC | [19 empty] | X
First Read - MRC | [20 empty] | X
Vote - MRC | [21 empty] | X
Vote - MC | [22 empty] | X
Detailed Work Plan -- Hybrid Resources Enhancements (Hybrids Phase 3) |  | 1.9.2023 | 2.6.2023 | 3.6.2023 | 4.10.2023 | 5.8.2023 | 5.25.2023 | 6.5.2023 | 6.23.2023 | 7.14.2023 | 7.31.2023 | 8.16.2023 | 10.10.2023 | 11.3.2023 | 12.4.2023 | 1.8.2024 | 2.5.2024 | 3.4.2024 | 4.1.2024 | 4.29.2024 | 6.3.2024 | 7.8.2024 | 8.5.2024 | 9.11.2024 MIC | 9.26.2024 MIC Special | 10.9.2024 MIC | 10.30.2024 MRC | 11.20.2024 MRC | 12.18.2024 MC
Review Issue Charge and Problem Statement | [13 empty] | X | X
Provide Education | [15 empty] | X
Develop & Review Interests | [15 empty] | X | X | X
Develop & Review Design Components | [16 empty] | X | X | X
Develop & Refine Solution Options | [18 empty] | X | X | X | X
Develop & Refine Solution Packages | [20 empty] | X | X | X
Build Consensus | [20 empty] | X | X | X
First Read - MIC | [23 empty] | X
Special MIC Session: Hybrid Phase III Education | [24 empty] | X
Vote - MIC | [25 empty] | X
First Read - MRC | [26 empty] | X
Vote - MRC | [27 empty] | X
Vote - MC | [28 empty] | X
Detailed Work Plan -- Wind and Solar Resource Dispatch in Real-Time Market Clearing Engines |  | 1.9.2023 | 2.6.2023 | 3.6.2023 | 4.10.2023 | 5.8.2023 | 5.25.2023 | 6.5.2023 | 6.23.2023 | 7.14.2023 | 7.31.2023 | 8.16.2023 | 10.10.2023 | 11.3.2023 | 12.4.2023 | 1.8.2024 | 2.5.2024 | 3.4.2024 | 4.1.2024 | 4.29.2024 | 6.3.2024 | 7.8.2024 | 8.5.2024 | 9.9.2024 | 10.7.2024 | 11.4.2024 | 12.2.2024
Review Issue Charge and Problem Statement | [20 empty] | X | X
Provide Education | [22 empty] | X | X | X
Develop & Review Interests | [24 empty] | X | X
Develop & Review Design Components & Status Quo | [25 empty] | X | X
Develop & Refine Solution Options
Develop & Refine Solution Packages
Build Consensus
First Read - MIC
Vote - MIC
First Read - MRC
Vote - MRC
Vote - MC