Stakeholder Process Work Plan – Energy Price Formation Sr. Task Force

| TOPIC | 1/18 | 1/29 | 2/15 | 3/5 | 3/29 | 4/9 | 5/4 | 5/23 | 6/8 | 6/25 | 7/17 | 8/6 | 8/22 | 9/10 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Charter Draft & Approval | X | X |  |  |  |  |  |  |  |  |  |  |  |  |
| Develop Work Plan | X | X |  |  |  |  |  |  |  |  |  |  |  |  |
| Key Work Activity #2 – Education & Joint Fact-Finding (As Required) |  | X | X | X | X | X | X | X | X | X | X |  |  |  |
| Key Work Activity #3 – Design Criteria |  | X | X | X |  |  |  |  |  |  |  |  |  |  |
| Key Work Activity #4-8: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Interest Identification |  | X | X |  |  |  |  |  |  |  |  |  |  |  |
| Develop Design Components |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Price Setting |  | X | X | X |  |  |  |  |  |  |  |  |  |  |
| - Reserves & ORDC |  |  | X | X |  |  |  |  |  |  |  |  |  |  |
| Document Relative Importance of each Component |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Price Setting |  | X | X | X |  |  |  |  |  |  |  |  |  |  |
| - Reserves & ORDC |  |  | X | X |  |  |  |  |  |  |  |  |  |  |
| Develop Options for each Component |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Price Setting |  | X | X | X | X | X | X |  |  |  |  |  |  |  |
| - Reserves & ORDC |  |  | X | X | X | X | X |  |  |  |  |  |  |  |
| TOPIC | 1/18 | 1/29 | 2/15 | 3/5 | 3/29 | 4/9 | 5/4 | 5/23 | 6/8 | 6/25 | 7/17 | 8/6 | 8/22 | 9/10 |
| Narrow Options |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Price Setting |  |  |  | X | X | X | X |  |  |  |  |  |  |  |
| - Reserves & ORDC |  |  |  | X | X | X | X |  |  |  |  |  |  |  |
| Develop Packages |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Price Setting |  |  |  |  |  | X | X | X | X | X | X | X |  |  |
| - Reserves & ORDC |  |  |  |  |  | X | X | X | X | X | X | X |  |  |
| Narrow Packages (Compare Packages to Interests & Importance Ratings) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Price Setting |  |  |  |  |  |  |  | X | X | X | X | X | X |  |
| - Reserves & ORDC |  |  |  |  |  |  |  | X | X | X | X | X | X |  |
| Consensus Testing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Price Setting |  |  |  |  |  |  |  |  |  |  | X | X | X |  |
| - Reserves & ORDC |  |  |  |  |  |  |  |  |  |  | X | X | X |  |
| Tier 1/Tier 2 Decision Making |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Price Setting |  |  |  |  |  |  |  |  |  |  |  |  |  | X |
| - Reserves & ORDC |  |  |  |  |  |  |  |  |  |  |  |  |  | X |