## Draft Initial Workplan
|  | 2025 | [12 empty] | 2026
|  | Jan | Feb | Mar | Apr |  | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Track | Description | half-day meetings |  |  |  |  | Jul: full-day meetings
Day-Ahead Reserves | Day-ahead reserve product(s) to better align with day-ahead operational needs (DA energy gap) | Initial Conceptual Design |  |  | IMM Education plus Additional Requests Prior to Polling | Polling on conceptual designs | May: Matrix Design; Jul: Draft PJM Proposal; Aug: proposal refinements and alternatives; Dec: "Near Final" PJM Package; 2026 Jan: Package refinement and alternatives; 2026 Mar: RCSTF Voting; 2026 May: MRC Voting; 2026 Jun: MC Voting; 2026 Jul: Targeted Filing
ORDC | Evaluation of PJM’s ORDCs |  |  | Initial Conceptual Design |  |  | Jul: Matrix Design; Aug: Draft PJM Proposal; Sep: proposal refinements and alternatives
Uncertainty Reserves | Ramping/uncertainty reserve products to manage growing operational uncertainty |  | Initial Conceptual Design |  |  |  | Jun: Matrix Design; Sep: Draft PJM Proposal; Oct: proposal refinements and alternatives
Reserve Enhancements | Rules concerning which costs can be reflected in reserve market offers, market power mitigation rules, reserve requirement levels for existing reserve markets | [5 empty] | May: Matrix Design; Jun: Matrix Design; Jul: Matrix Design; Sep: Draft PJM Proposal; Oct: proposal refinements and alternatives
Perfomance and Incentives | Performance evaluation and incentives to ensure alignment with operational needs; Incentives to follow PJM dispatch as it relates to reserve products | [5 empty] | Jun: Matrix Design; Jul: Matrix Design; Sep: Draft PJM Proposal; Oct: proposal refinements and alternatives
Matrix Design:
PJM will bring a matrix populated with design components and initial solution options for stakeholder consideration and addition.
Draft PJM Proposal:
PJM will populate the matrix with their initial proposal for this design area.
Proposal refinements and alternatives:
PJM will refine the proposal based on stakeholder feedback. Alternative proposals from stakeholders are welcomed.
"Near Final" PJM Package:
PJM introduces their near final package tying the proposals across all the workstreams together.
Package refinements and alternatives:
PJM will refine the consolidated package based on input from stakeholder discussions.
Alternative packages from stakeholders are welcomed.

## Mapping to Dec 2024 Pres.
This chart maps the Summary slide (slide 36) from PJM's December 2024 RCSTF presentation to the solution tracks outlined in this workplan.
Challenges to be Addressed | Proposed Solutions to Explore | Solution Area(s)
• The Day-Ahead Energy Market does not procure sufficient reserves to manage operational risk, leading to out-of-market reliability actions. • PJM’s markets do not procure flexibility to manage forecast uncertainty (i.e., load, wind, solar, interchange and forced outage rates). • PJM’s real-time dispatch engine does not account for flexibility and ramping needs forecasted in future intervals. • The cost of advanced fuel arrangements and other availability measures to provide reserves may at times be unrecoverable through PJM’s existing market constructs. | Enhancements to Existing Reserve Markets
| • Updates to PJM’s ORDCs | ORDC
| • Changes to resource offer rules into reserve markets to enable cost recovery | Reserve Enhancements
| • IT SCED enhancements to better manage upcoming flexibility needs | Spans multiple solution areas
| • Performance evaluation and incentives to ensure alignment with operational needs | Perfomance and Incentives
| • Incentives to follow PJM dispatch | Perfomance and Incentives
| • Locational procurement of reserves for reliability | Day-Ahead Reserves, Uncertainty Reserves
New Reserve Products
| • Day-ahead reserve product(s) to better align with day-ahead operational needs | Day-Ahead Reserves
| • Ramping/uncertainty reserve products to manage growing operational uncertainty | Uncertainty Reserves