## Revised Draft Workplan
2026
|  | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Track | Description | May: 1/2 day meeting; Jun: full-day meetings; Aug: 2 meetings per month, alternating full-day and half-day meetings
Day-Ahead Reserves | Day-ahead only reserve product(s) to better align with day-ahead forecasted operational needs | Matrix Design | Solution Options | Solution Options | Solution Options | Draft Proposals | proposal refinements and alternatives |  | "Near Final" PJM Package | Package refinement and alternatives |  | RCSTF Voting |  | MRC Voting | MC Voting | Targeted Filing
10 Minute Reserves | Reserve product(s) used to manage short-term uncertainty and ramping needs, such as renewable intermittency and to meet forecasted net load ramps | May: Matrix Design; Jun: Solution Options; Jul: Solution Options; Aug: Solution Options; Sep: Draft Proposals; Oct: proposal refinements and alternatives
30 Minute Reserves | Replacement reserve product(s) for contingency events and for capturing uncertainty | May: Matrix Design; Jun: Solution Options; Jul: Solution Options; Aug: Solution Options; Sep: Draft Proposals; Oct: proposal refinements and alternatives
Synchronized & Primary Reserves | Rules concerning existing Synchronized Reserve & Primary Reserve/NSR requirements and products | Aug: Matrix Design; Sep: Solution Options; Oct: Draft Proposals; Nov: proposal refinements and alternatives
Matrix Design & Solution Options:
PJM will bring a matrix populated with design components and initial solution options for stakeholder consideration and addition.
Draft Proposals:
PJM will populate the matrix with their initial proposal for this design area. Stakeholders are welcome to offer proposals at this time as well.
Proposal refinements and alternatives:
PJM and stakeholders will refine the proposals based on feedback.
"Near Final" PJM Package:
PJM introduces their near final package tying the proposals across all the workstreams together.
Package refinements and alternatives:
PJM will refine the consolidated package based on input from stakeholder discussions.
Alternative packages from stakeholders are welcomed.

## Initial Draft Workplan
|  | 2025 | [12 empty] | 2026
|  | Jan | Feb | Mar | Apr |  | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Track | Description | half-day meetings |  |  |  |  | Jul: full-day meetings
Day-Ahead Reserves | Day-ahead reserve product(s) to better align with day-ahead operational needs (DA energy gap) | Initial Conceptual Design |  |  | IMM Education plus Additional Requests Prior to Polling | Polling on conceptual designs | May: Matrix Design; Jul: Draft PJM Proposal; Aug: proposal refinements and alternatives; Dec: "Near Final" PJM Package; 2026 Jan: Package refinement and alternatives; 2026 Mar: RCSTF Voting; 2026 May: MRC Voting; 2026 Jun: MC Voting; 2026 Jul: Targeted Filing
ORDC | Evaluation of PJM’s ORDCs |  |  | Initial Conceptual Design |  |  | Jul: Matrix Design; Aug: Draft PJM Proposal; Sep: proposal refinements and alternatives
Uncertainty Reserves | Ramping/uncertainty reserve products to manage growing operational uncertainty |  | Initial Conceptual Design |  |  |  | Jun: Matrix Design; Sep: Draft PJM Proposal; Oct: proposal refinements and alternatives
Reserve Enhancements | Rules concerning which costs can be reflected in reserve market offers, market power mitigation rules, reserve requirement levels for existing reserve markets | [5 empty] | May: Matrix Design; Jun: Matrix Design; Jul: Matrix Design; Sep: Draft PJM Proposal; Oct: proposal refinements and alternatives
Perfomance and Incentives | Performance evaluation and incentives to ensure alignment with operational needs; Incentives to follow PJM dispatch as it relates to reserve products | [5 empty] | Jun: Matrix Design; Jul: Matrix Design; Sep: Draft PJM Proposal; Oct: proposal refinements and alternatives
Matrix Design:
PJM will bring a matrix populated with design components and initial solution options for stakeholder consideration and addition.
Draft PJM Proposal:
PJM will populate the matrix with their initial proposal for this design area.
Proposal refinements and alternatives:
PJM will refine the proposal based on stakeholder feedback. Alternative proposals from stakeholders are welcomed.
"Near Final" PJM Package:
PJM introduces their near final package tying the proposals across all the workstreams together.
Package refinements and alternatives:
PJM will refine the consolidated package based on input from stakeholder discussions.
Alternative packages from stakeholders are welcomed.