## Updated Jun 2026 Work Plan
[5 empty] | 2025 |  |  |  |  | 2026
|  | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Sep | Oct | Nov | Dec
Track | Description | May: 1/2 day meeting; Jun: full-day meetings; 2025 Aug: 2 meetings per month, alternating full-day and half-day meetings; 2026 Jul: Thurs. June 25 - Fri. July 10 (2 weeks); 2026 Aug: Aug. 19; 2026 Sep: early Sept.; 2026 Sep: Sep. 24; 2026 Oct: Oct. 28
Day-Ahead Reserves | Day-ahead only reserve product(s) to better align with day-ahead forecasted operational needs | Matrix Design | Solution Options | Solution Options | Solution Options | Draft Proposals | proposal refinements and alternatives |  | proposal refinements and alternatives |  |  | "Near Final" PJM Package | Package refinement and alternatives |  |  | RCSTF Voting | MRC First Read | Tariff Page Turn Review | MRC Voting | MC Voting | Targeted Filing
10 Minute Reserves | Reserve product(s) used to manage short-term uncertainty and ramping needs, such as renewable intermittency and to meet forecasted net load ramps | May: Matrix Design; Jun: Solution Options; Jul: Solution Options; 2025 Aug: Solution Options; 2025 Sep: Draft Proposals; 2025 Oct: proposal refinements and alternatives
30 Minute Reserves | Replacement reserve product(s) for contingency events and for capturing uncertainty | May: Matrix Design; Jun: Solution Options; Jul: Solution Options; 2025 Aug: Solution Options; 2025 Sep: Draft Proposals; 2025 Oct: proposal refinements and alternatives
Synchronized & Primary Reserves | Rules concerning existing Synchronized Reserve & Primary Reserve/NSR requirements and products | 2025 Aug: Matrix Design; 2025 Sep: Solution Options; 2025 Oct: Draft Proposals; 2025 Nov: proposal refinements and alternatives
Matrix Design & Solution Options:
PJM will bring a matrix populated with design components and initial solution options for stakeholder consideration and addition.
Draft Proposals:
PJM will populate the matrix with their initial proposal for this design area. Stakeholders are welcome to offer proposals at this time as well.
Proposal refinements and alternatives:
PJM and stakeholders will refine the proposals based on feedback.
"Near Final" PJM Package:
PJM introduces their near final package tying the proposals across all the workstreams together.
Package refinements and alternatives:
PJM will refine the consolidated package based on input from stakeholder discussions.
Alternative packages from stakeholders are welcomed.

## Jan 2026 Draft Work Plan
[5 empty] | 2025 |  |  |  |  | 2026
|  | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Track | Description | May: 1/2 day meeting; Jun: full-day meetings; 2025 Aug: 2 meetings per month, alternating full-day and half-day meetings
Day-Ahead Reserves | Day-ahead only reserve product(s) to better align with day-ahead forecasted operational needs | Matrix Design | Solution Options | Solution Options | Solution Options | Draft Proposals | proposal refinements and alternatives |  | proposal refinements and alternatives |  |  | "Near Final" PJM Package | Package refinement and alternatives |  | RCSTF Voting | MRC First Read | MRC Voting | MC Voting | Targeted Filing
10 Minute Reserves | Reserve product(s) used to manage short-term uncertainty and ramping needs, such as renewable intermittency and to meet forecasted net load ramps | May: Matrix Design; Jun: Solution Options; Jul: Solution Options; 2025 Aug: Solution Options; 2025 Sep: Draft Proposals; 2025 Oct: proposal refinements and alternatives
30 Minute Reserves | Replacement reserve product(s) for contingency events and for capturing uncertainty | May: Matrix Design; Jun: Solution Options; Jul: Solution Options; 2025 Aug: Solution Options; 2025 Sep: Draft Proposals; 2025 Oct: proposal refinements and alternatives
Synchronized & Primary Reserves | Rules concerning existing Synchronized Reserve & Primary Reserve/NSR requirements and products | 2025 Aug: Matrix Design; 2025 Sep: Solution Options; 2025 Oct: Draft Proposals; 2025 Nov: proposal refinements and alternatives
Matrix Design & Solution Options:
PJM will bring a matrix populated with design components and initial solution options for stakeholder consideration and addition.
Draft Proposals:
PJM will populate the matrix with their initial proposal for this design area. Stakeholders are welcome to offer proposals at this time as well.
Proposal refinements and alternatives:
PJM and stakeholders will refine the proposals based on feedback.
"Near Final" PJM Package:
PJM introduces their near final package tying the proposals across all the workstreams together.
Package refinements and alternatives:
PJM will refine the consolidated package based on input from stakeholder discussions.
Alternative packages from stakeholders are welcomed.