## Sheet1
| AES Ohio | b | c | d | e | f | g | h | i | j | k | l | m
| Project | Project | Project | Project | Transformer | Need for |  | Need by | Explanation of no "Need by | Project | Project | Overtime/
Complex | Number | Name | Description | Scope | Information | Project | ISD | Date | Date" in previous column | Estimate | Cost | Premium Pay Charges | Comments
Airport | TUSDY01050103 | Airport Sub - Union Sub Circuit 138 | Install new 138kV transmission line, 13856, to customer, Pioneer | Install structures and conductor | N/A | Reliability Improvement | 2024-08-09 | 2022-12-31 | ISD adjusted by customer, Pioneer | 1608932 | 1193035 | 35283
Crystal - New Lebanon | TUSDY01050105 | Crystal - N Lebanon Dbl Cir -6611 | Reconductor approximately one mile of double circuit 69kV transmission line from the existing New Lebanon Substation to Clayton Rd. This was the final phase of the project to install a new 69kV transmission line between New Lebanon and Crystal Substations. New Lebanon Substation was previously fed from a radial transmission line. | Replace existing structures and conductor | N/A | Reliability Improvement | 2024-04-29 | 2023-10-31 | NA | 2975097 | 2781820 | N/A
Fayette | TUSDY01050134 | 138kV Fayette-Customer 2 | Install new 138kV transmission line to customer - approximatley .25 miles for service to a new customer | Install structures and conductor | N/A | New Service | 2024-08-29 | 2024-08-01 | NA | 1500000 | 1329991 | 29214
Fayette | TUSDY01050133 | 138kV Fayette-Customer 1 | Install new 138kV transmission line to customer - approximatley .25 miles for service to a new customer | Install structures and conductor | N/A | New Service | 2024-08-29 | 2024-08-01 | NA | 1500000 | 1352957 | 26061
Fayette | TUSDY01050127 | New Substation - Fayette | Install a new 345/138/69kV substation for service to a new customer | Install structures, equipment and protection to provide a new 138kV source for a new customer and a new 69kV source for a substation to constructed at a future date in an effort to improve reliability. The source for this project orginates at the new Madison Substation and is connected through the new Fayette - Madison transmission lines, 34512/34514. | 345/138kV - 120/450 kva 345/138/kV - 120/450 kva 138/69kV - 120/200 kva | Relibability Improvement/New Service | 2024-11-20 | 2024-08-01 | NA | 44400000 | 39793125 | 11241
Fayette | TUSDY01050130 | Fayette to Madison - 34512 | Install 13.5 miles of 345kV transmission line from Madison Substation to Fayette Substation | Install structures and conductor to complete a new transmission line, 34512 | N/A | Relibability Improvement/New Service | 2024-07-24 | 2024-08-01 | NA | 63250000 | 21793614 | 2157808
Fayette | TUSDY01050131 | Fayette to Madison - 34514 | Install 13.5 miles of 345kV transmission line from Madison Substation to Fayette Substation | Install structures and conductor to complete a new transmission line, 34514 | N/A | Relibability Improvement/New Service | 2024-07-24 | 2024-08-01 | NA |  | 72257678 | 2149318
Franklin | TUSDY01050091 | 13861 Franklin to Honda Anna II | Install new 138kV transmission line to Honda Anna - 13861. Length of the transmission line is approximately .6 miles. This project is one project of a larger complex including the Sidney Sub Expansion, 13854 Sidney - Franklin Transmission Line and Franklin Substation Projects. | Install structures and conductor | N/A | Reliability Improvement | 2024-12-23 | 2025-03-01 | NA | 1536838 | 1047301 | 11088
Franklin | TUSDY01050087 | Sidney I/S 138kv Ring Bus & 13854 | Expand existing substation to provide a source for a new 138kV line - 13854. This project is one project of a larger complex including the Honda Anna 13861, Sidney - Franklin 13854 and Franklin Substation Projects. | Install structures, equipment and protection to accommodate a new 138kV transmission line, 13854, connecting Sidney Substation to Franklin Substation. | N/A | Reliability Improvement | 2024-09-13 | 2024-09-13 | NA | 1930243 | 2110114 | 74295
Franklin | TUSDY01050074 | 6628 Partial Rebuild Sidney to Kuth | Reconductor existing 69kV transmission line, 6628. | Replace existing structures and conductor | N/A | Relibaility Improvement | 2024-04-10 | 2024-06-01 | NA | 2500000 | 3201118 | 9231
Franklin | TUSDY01050046 | Franklin Sub I/S New Substation | Switchyard to provide two, 138kV transmission lines to Honda Anna - 13860 and 13861. This project is one projet of a larger complex including the Honda Ana 13861, Sidney Substation and Sidney - Franklin 13854 Projects | Install switchyard with appropriate structures, bus, switches and protections | N/A | Reliability Improvement | 2024-07-09 | 2024-06-10 | NA | 4017135 | 7826737 | 23626
Franklin | TUSDY01050076 | 13854 Sidney- Franklin | Install new 138kV transmission line from Sidney Substation to Franklin Switchyard - 13854. The length of the transmission line was 7.5 miles. This project is one of a larger complex incuding Honda Anna 13861, Sidney Substation and Franklin Substation Projects. | Install structures, conductor and protection | N/A | Reliability Improvement | 2024-07-09 | 2024-06-10 | NA | 12300000 | 9637504 | 89543
Greene Storage | TUSDY01010021 | Greene Storage Yard | Secure Storage Facility for AES Ohio's BES transformers, breakers and anxilliary equipment. | Storage facility includes 10 pads for the storage of new/spare transformers, indoor storage for spare BES breakers and anxilliary components. Secure and monitored site to ensure equipment is properly stored. | N/A | Reliability/Resliliency | 2024-09-30 | 2024-05-24 | NA | 19500000 | 20120542 | 1301
Greenfield | TUSDY01010020 | 6649/6662 Greenfield cut in realign | Relocate existing transmission facilities to support the Greenfield Substation Expansion Project. This project was completed in conjunction with a customer IPP Project. | Remove/install transmission facilities to align with Greenfield Substation Expansion circuit breaker positions. | N/A | Reliability Improvement | 2024-11-14 | 2024-05-31 | NA | 1000000 | 1099002 | 8421
Greenfield | TUSDY01010018 | Greenfield Substation expansion | Expand the existing substation to accommodate additional circuit breakers to form a ring bus. The project was completed in conjunction with a customer IPP Project. | Expand existing substation, install circuit breakers, bus and protection to improve reliability. | N/A | Reliability Improvement | 2024-11-14 | 2024-05-31 | NA | 1474374 | 1952344 | 8667
Jackson Center | TUSDY01050097 | Jackson Center Trans 6614 | Move existing 69kV transmission line, 6614, to a separate breaker position to serve an existing substation. This was completed in conjuction with a separate transmission line, 6910, to provide a source to Jason Center Municiple, eliminating the previous connection to 6614. | Install structures and conductor | N/A | Reliability Improvement | 2024-12-18 | 2023-12-31 | NA | 542800 | 951279 | 36506
KTH (customer) | TUSDY01050080 | Urbana Sub Expansion | Expand existing substation to provide a source for a new 69kV line, 6943, to improve reliability for customer, KTH. | Install structures, equipment and protection. The project is one of a larger complex of projects including the Urbana to St. Paris 6943 transmission line and St. Paris Substation Expansion. | N/A | Reliability Improvement | 2024-05-29 | 2023-12-31 | NA | 2245139 | 2318630 | 11649
KTH (customer) | TUSDY01050081 | St Paris Sub Expansion | Expand existing substation to eliminate the radial source and provide an improved tie capability for customer, KTH. | Install structures, equipment and protection. The project is one of a larger complex of projects including the Urbana to St. Paris 6943 transmission line and Urbana Substation Expansion. | N/A | Reliability Improvement | 2024-12-19 | 2023-12-31 | NA | 3711092 | 2976024 | 15452
KTH (customer) | TUSDY01050061 | 6943 - Urbana to St. Paris | Install a new 69kV transmission line, 6943, to provide another source for a customer, KTH. The length of the transmission line is approximatley 12.6 miles. | Install new structures and conductor for a new transmission line. Multiple issues with ROW required adjustments to pole locations and ISD. The project is one of a larger complex of projects including the St. Paris Substation Expansion and Urbana Substation Expansion. | N/A | Reliability Improvement | 2024-12-10 | 2023-12-31 | NA | 16919764 | 18241166 | 25538
Madison | TUSDY01050186 | Panther Laydown Yard Phase I | Install laydown yard to support material handling for multiple projects in the area. The installation will reduce travel time and improve safety associated with moving materials to the job site. | Install driveway, yard surfacing and fencing for an area approximately 10 acres in size | N/A | Efficiency improvement | 2024-12-04 |  | The Need by Date was dictated by material delivery. That date was met, but additional work was completed by the ISD. | 5200000 | 4037521 | 0
Madison | TUSDY01050082 | Madison Sub - 34506 Reconfiguration | Reconfigure existing 34506 transmission line to provide source for Madison Substation | Install structures and conductor to provide source for the new Madision Substation | N/A | Relibability Improvement/New Service | 2024-05-29 | 2024-08-01 | NA | 4227844 | 4227844 | 497
Madison | TUSDY01050035 | Madison Sub -I/S New 345/69kv Sub ( | Install new substation to with a 345/69kV transformer and switchyard to provide a source for 34512 and 34514 | Install structures, equipment and protection to provide a new 69kV source that will connect to an existing substation to improve reliability. The station also serves as a switchyard to provide a source for two new 345kV transmission lines, 34512/34514. These transmission lines will connect Madison Substation to Fayette Substation. | 345/ 69kV - 150/250 kva | Relibability Improvement/New Service | 2024-07-24 | 2024-08-01 | NA | 26072156 | 25627730 | 11829
ROW | TUSDY01090008 | Transmission ROW | Purchase Right of Way to support the execution of transmission line installations | This is a blanket project that accumulates Right of Ways costs for many transmission projects. | N/A | Support execution of transmission line projects | 2024-01-31 | This is made up of many projects. | NA |  | 12178435 | 0
ROW | TUSDY01090029 | Transmission ROW Q2-24 | Purchase Right of Way to support the execution of transmission line installations | This is the movement to Unitize Right of Way costs for 2024, quarter 2. This includes many projects. | N/A | Support execution of transmission line projects | 2024-05-31 | This is made up of many projects. | NA |  | 6589470 | 0
Russia | TUSDY01050111 | Russia - Covington - Rossburg Line | Rebuild approximately 1.2 miles of existing transmission line, 6625. | Replace existing structures and conductor | N/A | Reliability Improvement | 2024-12-18 | 2023-12-31 | NA | 3063794 | 3791119 | 85957
Russia | TUSDY01050088 | Russia Sub Expansion | Expand existing Russia Substation to create a ring bus configuration. | Separate the existing transmission line, 6625, into three lines, Russia to Minster, 6938 - Russia to Covington, 6949 - Russia to Rossburg, 6625 | N/A | Reliability Improvement | 2024-12-18 | 2023-12-31 | NA | 3053845 | 3483372 | 26535
Static Wire | TUSDY01120057 | Hutchings - Crown Substation 13808 Static Wire Replacement | Replace existing static line on transmission line 13808 | Install structures and conductor | N/A | Reliability Improvement | 2023-12-14 | 2023-09-30 | NA | 1035000 | 2273270 | 17155