## Sheet1
Project ID | Project Name | Developer Name | Company Name | Request type | Facility Name | Status | TO | County | State | MW/MVA/MVAR increase | LDA(s) (For ICTR requests) | IARR MW (If IARR requested) | Source Location (if IARR requests) | Sink Location (if IARR requests) | Submission Date | Requested In service date | SIS Report | Agreement | Not completion Remark | Revised Estimated Completion Date | Revised Date Reason
UR23-0001 | Olive-University Park 345 kV | Northern Illinois Municipal Power Agency (NIMPA) | Northern Illinois Municipal Power Agency (NIMPA) | Merchant Network Upgrade | Olive - University Park 345 kV | Withdrawn | AEP | Adam | Indiana | 24 MVA | COMED |  |  |  | 2023-09-29 | 2026-06-01 |  |  |  | 2026-03-01 | Delays in receiving equipment ratings
UR23-0002 | Granite 115 kV | Mercuria Energy America, LLC | Mercuria Energy America, LLC | Merchant Network Upgrade | Granite 115 kV | Withdrawn | BGE | Allegnay | Maryland | 40 MVAR | BGE |  |  |  | 2023-09-29 | 2026-06-01 | UR23-0002 SIS report
UR23-0003 | Vienna 138 kV | Boston Energy Trading and Marketing | Boston Energy Trading and Marketing | Merchant Network Upgrade | Vienna - Vienna 8 138 kV Ckt 1 | Withdrawn | DPL | N/A | Maryland | 180 MVA | DPL South, EMAAC, MAAC |  |  |  | 2023-09-28 | 2024-10-01 | UR23-0003 SIS report
UR24-0004 | Smithburg-East Windsor 230 kV | Chesapeake Transmission LLC | Chesapeake Transmission LLC | Merchant Network Upgrade | Smithburg-East Windsor 230 kV line (E2005) | Active | JCPL | Monmouth | New Jersey | 20 MVA | JCPL, PS, EMAAC |  |  |  | 2024-08-27 | 2025-06-01 | UR24-0004 SIS report
UR25-0005 | Crane Clean Energy Center Restart | Constellation Energy Generation, LLC | Constellation Energy Generation, LLC | Merchant Network Upgrade | Three Mile Island 230 kV | Active | MAIT | Dauphin | Pennsylvania | [5 empty] | 2025-12-09 | 2027-06-01 | UR25-0005 SIS report
UR26-0006 | Lackawanna 115 kV | Lackawanna Energy Center LLC | Lackawanna Energy Center LLC | Fund Network Upgrade | Lackawanna 115 kV | Active | PPL | Lackawanna | Pennsylvania |  |  | 100 MW | LACKAENG 24 KV CTG1 (1369011078) | .I.NYIS (5413134) | 2025-01-06 | 2026-07-01