## 2020 WORK PLAN
DER and Inverter-based Resources Subcommittee - Work Plan
Updated: July 28, 2020 | [10 empty] | 2020 |  |  |  | 2021
[10 empty] | Jan - Mar | Apr - Jun | Jul - Sep | Oct - Dec | Jan - Mar | Apr - Jun | Jul - Sep | Oct - Dec
DER Aggregation - Postponed | [9 empty] | On hold pending FERC action in RM18-9
Triennial Review Timing | 2012-07-01 | 2012-08-01 | 2012-09-01 | 2012-10-01 | 2012-11-01 | 2012-12-01 | 2013-01-01
üProvide Education
üProblem Investigation
üProposal Development
üBuild Consensus
üFirst Read @ MRC |  |  |  |  | 2012-11-29
üVote at MRC | [5 empty] | 2012-12-20
üVote at MC
Multi-Year Pricing Mechanism | 2012-07-01 | 2012-08-01 | 2012-09-01 | 2012-10-01 | 2012-11-01 | 2012-12-01 | 2013-01-01 | 2013-02-01 | 2013-03-01
üProvide Education
üRefine Interests
üDevelop & Refine Design Components | bar: 2012-10-01
üDevelop & Refine Component Options | bar: 2012-10-01 to 2012-12-01
üDevelop & Refine Solution Packages | bar: 2012-11-01 to 2012-12-01
üBuild Consensus | bar: 2013-01-01
üFirst Read @ MRC |  |  |  | 2013-01-01: 2013-01-31
Vote at MRC |  |  |  | 2013-02-01: 2013-02-28
Vote at MC |  |  |  | 2013-02-01: 2013-02-28
FERC Filing |  |  |  | 2013-03-01: 2013-03-01
Utility Microgrids - Active
Hybrid Resources - Active
Detailed Work Plan -- Utility Microgrids | [9 empty] | DIRS 08.03.2020 | DIRS 09.10.2020 | DIRS 10.02.2020 | DIRS 11.02.2020 | DIRS 12.07.2020
Provide Education
Document Interests
Develop & Refine Design Components
Develop & Refine Component Options
Develop & Refine Solution Packages | [9 empty] | X
Build Consensus | [9 empty] | X
Report Recommended Solutions to MIC | [9 empty] | X
Detailed Work Plan -- Hybrid Resources | [9 empty] | DIRS 08.03.2020 | DIRS 09.10.2020 | DIRS 10.02.2020 | DIRS 11.02.2020 | DIRS 12.07.2020
Provide Education | [9 empty] | X | X | X
Document Interests | [10 empty] | X
Develop & Refine Design Components | [11 empty] | X | X
Develop & Refine Component Options | [11 empty] | X | X
Develop & Refine Solution Packages | [12 empty] | X | X
Build Consensus | [13 empty] | X
Report Recommended Solutions to MIC | [13 empty] | X