## Sheet1
DRAFT Schedule - this is subject to stakeholder endorsement and FERC decision outcome(s)
| Sep | Oct | Nov | Dec | Jan | Feb | March | April | May | June | Jul | Aug
SODRSTF proposal
MRC first read | bar: Sep
MC read/approval | bar: Oct
MC approval | bar: Oct
Board Approval | bar: Dec
FERC filing* | Jan: early
FERC approval | March: early
LFA plan submission | Feb: 2019-02-01
Updated load forecast with LFA | March: 2019-03-15
PRD M&V proposal
MRC reminder, first read | bar: Oct
MC read/approval | bar: Dec
MC approval | bar: Dec
Board Approval | bar: Dec
FERC filing | Jan: early
FERC approval | March: early
PRD plan CURRENT Submission Date | Jan: 2019-01-15
*PRD plan proposed update/withdraw date | April: 2019-04-15
RPM Date
Planning parameters post date | May: 2019-05-01
BRA | bar: Aug