## 2021-22 WORK PLAN
Energy Price Formation Senior Task Force - Work Plan
Updated: March 31, 2022 | 2021 |  |  |  | 2022
Working Items | Jan - Mar | Apr - Jun | Jul - Sep | Oct - Dec | Jan - Mar | Apr - Jun | Jul - Sep | Oct - Dec
Circuit Breaker - KWA 1 and 2
Circuit Breaker - KWA 3
Application of TCPF - Hill Default Lessons Learned
Detailed Work Plan -- Circuit Breaker KWA 1 & 2 | 8.9.2021 | 8.26.2021 | 9.23.2021 | 10.13.2021 | 10.27.2021 | 11.16.2021 | 12.10.2021 | 1.25.2022 | 2.16.2022 | 3.16.2022 | 4.5.2022 | 4.20.2022 | 5.4.2022 | 5.23.2022 | 6.3.2022 | 6.30.2022 (all day) | 7.20.2022 | 8.15.2022 (all day)
Provide Education | x | x |  | x | x |  | x | Canceled due to FERC Remand | x | x | TCPF |  | TCPF |  | TCPF
Document Interests | x | x | [6 empty] | x | x
Develop & Refine Design Components |  |  | x | x | x |  | x |  | x | x
Develop & Refine Component Options |  |  | x | x | x |  | x |  |  | x
Develop & Refine Solution Packages |  |  | x |  |  |  | x |  |  | x |  | x |  | x
Build Consensus |  |  |  |  | x | x | [7 empty] | x |  | x
Report Recommended Solutions to MIC (& OC) | [16 empty] | x
Detailed Work Plan - Circuit Breaker - KWA 3 | 8.9.2021 | 8.26.2021 | 9.23.2021 | 10.13.2021 | 10.27.2021 | 11.16.2021 | 12.10.2021 | 1.25.2022 | 2.16.2022 | 3.16.2022 | 4.5.2022 | 4.20.2022 | 5.4.2022 | 5.23.2022 | 6.3.2022 | 6.30.2022 (all day) | 7.20.2022 | 8.15.2022 (all day)
Provide Education | [10 empty] | TCPF |  | TCPF |  | TCPF |  | x
Document Interests | [16 empty] | x | x
Develop & Refine Design Components | [17 empty] | x
Develop & Refine Component Options | [17 empty] | x
Develop & Refine Solution Packages | [17 empty] | x
Build Consensus | [17 empty] | x
Report Recommended Solutions to MIC (& OC)
Detailed Work Plan - Application of TCPF - Hill Default Lessons Learned | 8.9.2021 | 8.26.2021 | 9.23.2021 | 10.13.2021 | 10.27.2021 | 11.16.2021 | 12.10.2021 | 1.25.2022 | 2.16.2022 | 3.16.2022 | 4.5.2022 | 4.20.2022 | 5.4.2022 | 5.23.2022 | 6.3.2022 | 6.30.2022 (all day) | 7.20.2022 | 8.15.2022 (all day)
Provide Education | [10 empty] | x | Circuit Breaker |  | Circuit Breaker
Document Interests | [10 empty] | x |  | x
Develop & Refine Design Components | [10 empty] | x |  | x
Develop & Refine Component Options | [10 empty] | x |  | x
Develop & Refine Solution Packages | [12 empty] | x |  | x | x
Build Consensus | [14 empty] | x | x
Report Recommended Solutions to MIC (& OC)