## Sheet3
2019 Market Efficiency Process Enhancement Task Force (MEPETF) Phase 2 Work Plan
Topic | 2019-06-07 | 2019-07-01 | 2019-07-29 | 2019-08-26 | 2019-09-27 | 2019-10-10 | 2019-12-03 | 2019-12-12 | 2019-12-19 | TBD | TBD | TBD | TBD | TBD
Charter Review | bar: 2019-06-07
Develop Work Plan | bar: 2019-06-07
Education & Joint Fact-Finding | bar: 2019-06-07 to 2019-07-01
Document Interests | bar: 2019-07-01
Develop Design Components | bar: 2019-07-01
Develop Options for each Component | bar: 2019-07-29
Narrow Options | bar: 2019-07-29
Develop Packages | bar: 2019-07-29
Narrow Packages (Compare Packages to Interests & Importance Ratings) | bar: 2019-08-26
Build Consensus | bar: 2019-08-26
Package Strawman Poll | bar: 2019-08-26
Review Strawman Poll | bar: 2019-09-27
Tier 1 Decision Making | bar: 2019-09-27 to 2019-12-03
1st Read PC | bar: 2019-12-12
1st Read MRC | bar: 2019-12-19
2nd Read PC | [9 empty] | X
2nd Read MRC | [10 empty] | X
MC Vote | [11 empty] | X
Finalize and submit FERC Filing | [12 empty] | X
Receive FERC direction and implement changes | [13 empty] | X