## 21-22 Annual Outages
2021/2022 Annual ARR/FTR Outages
Zone | Facility Name | Type | Modeled Period | Scheduled Start Day | Scheduled End Day
AE | BECKETT 69 KV BEC-PAU | LINE | All | 12/17/2021 | 3/7/2022
AE | CARNEYPT69 KV CAR-CHU | LINE | All | 1/5/2022 | 5/6/2022
AE | CARNEYPT69 KV CAR-PENN | LINE | All | 1/5/2022 | 5/6/2022
AE | CEDAR 230 KV CEDAR T8 | XFRM | All | 9/24/2021 | 12/6/2021
AE | CORSON 138 KV COR-MER | LINE | All | 10/25/2021 | 4/18/2022
AE | ENGLAND 138 KV ENG-MDT | LINE | All | 9/24/2021 | 5/9/2022
AE | ENGLAND 138 KV ENG-MER | LINE | All | 9/24/2021 | 4/6/2022
AE | MONR AE 230 KV MON #3 | XFRM | All | 9/20/2021 | 3/6/2022
AE | OLDMAN 69 KV OLD-PEN | LINE | All | 1/5/2022 | 5/6/2022
AE | SECONDST69 KV SEC-SHE2 | LINE | All | 10/25/2021 2/22/2022 | 10/28/2021 5/6/2022
AEP-AP | AMOS 138 KV 7-S | XFRM | All | 10/25/2021 | 11/19/2021
AEP-AP | AMOS 34 KV 7-T | XFRM | All | 10/25/2021 | 11/19/2021
AEP-AP | AMOS 345 KV 7-P | XFRM | All | 10/25/2021 | 11/19/2021
AEP-AP | AXTONAEP765 KV . 1 | XFRM | All | 12/1/2021 3/22/2022 | 12/1/2021 4/28/2022
AEP-AP | AXTONAEP765 KV AXT-JAC1 | LINE | All | 12/1/2021 3/22/2022 | 12/1/2021 4/28/2022
AEP-AP | CHEMICAL138 KV . 1 | XFRM | All | 9/30/2017 | 12/31/2022
AEP-AP | CHEMICAL138 KV . 2 | XFRM | All | 8/14/2019 | 12/31/2022
AEP-AP | GALAX 69 KV GAL-JUB1 | LINE | All | 9/8/2021 | 2/11/2022
AEP-AP | JUBALEAR138 KV . 1 | XFRM | All | 9/8/2021 | 2/11/2022
AEP-AP | KAMMER2 765 KV KAM-SCA1 | LINE | All | 9/20/2021 | 12/31/2021
AEP-AP | KAMMER2 765 KV KAM-VAS | LINE | All | 4/5/2021 9/15/2021 3/15/2022 | 6/11/2021 11/9/2021 5/6/2022
AEP-AP | MULLENS 138 KV MUL-PIE | LINE | All | 9/21/2021 | 12/9/2021
AEP-AP | WYOMING2765 KV 1 | XFRM | All | 3/15/2022 | 4/26/2022
AEP-IM | ALLENIM 138 KV ALL-DAW | LINE | All | 8/17/2021 10/23/2021 | 9/14/2021 2/15/2022
AEP-IM | ALLENIM 138 KV ALL-LIN3 | LINE | All | 8/17/2021 10/19/2021 | 9/28/2021 4/26/2022
AEP-IM | BENTONHA138 KV BEN-CRY1 | LINE | All | 3/15/2021 | 9/10/2021
AEP-IM | BENTONHA138 KV BEN-RIV2 | LINE | All | 3/15/2021 | 11/5/2021
AEP-IM | BLUFFPOI138 KV BLU-JAY1 | LINE | All | 3/15/2021 9/20/2021 10/12/2021 | 6/15/2021 10/1/2021 12/17/2021
AEP-IM | COLLINGW345 KV COL-HIP | LINE | All | 9/1/2021 | 12/1/2021
AEP-IM | COLLINGW345 KV COL-ROB1 | LINE | All | 6/15/2021 | 12/1/2021
AEP-IM | COLLINGW345 KV COL-SBU1 | LINE | All | 9/1/2021 | 12/1/2021
AEP-IM | DEERCREE138 KV DEE-MUL1 | LINE | All | 11/29/2021 2/14/2022 | 12/6/2021 6/2/2022
AEP-IM | DELAWAIM138 KV DEL-HOG1 | LINE | All | 3/8/2021 8/16/2021 9/13/2021 3/4/2022 5/21/2022 | 6/4/2021 8/20/2021 12/18/2021 4/24/2022 5/22/2022
AEP-IM | DELAWAIM138 KV DEL-LAN1 | LINE | All | 9/13/2021 3/4/2022 5/21/2022 | 12/18/2021 4/24/2022 5/22/2022
AEP-IM | DEQUINE 345 KV DEQ-WES1 | LINE | All | 7/19/2021 | 10/22/2021
AEP-IM | DESOTO 138 KV DES-JAY1 | LINE | All | 3/15/2021 9/15/2021 10/12/2021 | 6/15/2021 10/1/2021 12/17/2021
AEP-IM | DUMONT2 765 KV DUM-GRE1 | LINE | All | 9/1/2021 | 4/1/2022
AEP-IM | HACIENDA138 KV HAC-HAR1 | LINE | All | 2/21/2022 | 6/2/2022
AEP-IM | HARPER 138 KV HAR-MIL1 | LINE | All | 9/15/2021 10/19/2021 2/28/2022 | 9/28/2021 2/18/2022 4/26/2022
AEP-IM | ILLINOIS138 KV ILL-IND1 | LINE | All | 1/24/2022 | 5/13/2022
AEP-IM | ILLINOIS138 KV ILL-SOR1 | LINE | All | 1/24/2022 | 5/13/2022
AEP-IM | ILLINOIS138 KV XF1 | XFRM | All | 1/24/2022 | 5/13/2022
AEP-IM | KENZIECR138 KV KEN-RIV1 | LINE | All | 2/4/2020 9/13/2021 | 9/10/2021 11/5/2021
AEP-IM | NICKERSO138 KV NIC-SOD1 | LINE | All | 4/27/2021 | 8/26/2021
AEP-IM | PIPECREE138 KV PIP-STR | LINE | All | 1/3/2022 | 11/3/2023
AEP-IM | RICHMOND138 KV 2 | XFRM | All | 8/9/2021 11/29/2021 | 9/3/2021 12/1/2021
AEP-IM | RICHMOND138 KV RIC-SEL1 | LINE | All | 7/12/2021 8/9/2021 11/29/2021 | 7/16/2021 9/3/2021 12/1/2021
AEP-KY | BAKER 765 KV BAK-BRO1 | LINE | All | 9/21/2021 | 10/27/2021
AEP-KY | HAZARD 161 KV 3 | XFRM | All | 6/1/2021 | 12/17/2021
AEP-KY | HAZARD 161 KV HAZ-WOO | LINE | All | 6/1/2021 | 12/17/2021
AEP-KY | JOHNSCRE138 KV JOH-CED1 | LINE | All | 9/20/2021 9/27/2021 10/4/2021 10/25/2021 | 9/24/2021 10/1/2021 10/8/2021 11/17/2021
AEP-OH | ADAMSAEP138 KV ADA-SEA1 | LINE | All | 6/1/2021 | 11/9/2021
AEP-OH | BEATTY 138 KV 4-S | XFRM | All | 2/2/2022 | 5/26/2022
AEP-OH | BEATTY 138 KV BEA-MCC1 | LINE | All | 9/22/2021 2/2/2022 5/11/2022 | 11/16/2021 2/8/2022 5/24/2022
AEP-OH | BEATTY 345 KV 4-P | XFRM | All | 2/2/2022 | 5/26/2022
AEP-OH | BIXBY 138 KV BIX-BUC1 | LINE | All | 3/16/2022 | 6/7/2022
AEP-OH | BRITTON 138 KV BRI-DUB | LINE | All | 9/15/2021 | 12/7/2021
AEP-OH | BUCKEYE 138 KV BUC-GAY1 | LINE | All | 1/5/2022 | 6/7/2022
AEP-OH | CARROLLT138 KV CAR-SUN1 | LINE | All | 7/6/2020 | 6/30/2021
AEP-OH | ELEIPSIC138 KV ELE-RIC1 | LINE | All | 3/7/2022 | 11/20/2022
AEP-OH | ELIMA 138 KV ELI-NWO1 | LINE | All | 9/8/2021 | 5/24/2022
AEP-OH | FISHER 138 KV FIS-TRA1 | LINE | All | 9/27/2021 1/6/2022 | 12/7/2021 1/7/2022
AEP-OH | HARRISCS138 KV 1 | XFRM | All | 9/8/2021 | 11/29/2021
AEP-OH | HARRISCS69 KV HAR-SOU1 | LINE | All | 9/8/2021 | 11/29/2021
AEP-OH | HILLSBOR138 KV HIL-MIDS | LINE | All | 3/29/2021 3/8/2022 | 6/24/2021 5/26/2022
AEP-OH | HOLLOWAY138 KV HOL-NOT1 | LINE | All | 5/24/2021 | 9/10/2021
AEP-OH | HOLLOWAY138 KV HOL-NOT2 | LINE | All | 5/24/2021 | 9/10/2021
AEP-OH | ISABELLA138 KV ISA-NNEW | LINE | All | 7/14/2021 2/15/2022 | 7/14/2021 9/16/2022
AEP-OH | KIRK 345 KV T4 | XFRM | All | 4/6/2020 | 12/30/2021
AEP-OH | MADDOXCR345 KV ELI-MAD | LINE | All | 9/15/2021 | 11/30/2021
AEP-OH | NEWCOMER138 KV 1-P | XFRM | All | 9/8/2021 | 12/14/2021
AEP-OH | NFINDLAY138 KV NFI-NWO1 | LINE | All | 9/8/2021 | 5/24/2022
AEP-OH | NNEWARK 138 KV NNE-CRO1 | LINE | All | 2/15/2022 | 9/16/2022
AEP-OH | NNEWARK 138 KV NNE-SHA1 | LINE | All | 9/7/2021 | 4/28/2022
AEP-OH | NWOODCOC138 KV 1-P | XFRM | All | 9/8/2021 | 5/24/2022
AEP-OH | NWOODCOC34 KV 1-T | XFRM | All | 9/8/2021 | 5/24/2022
AEP-OH | NWOODCOC69 KV 1-S | XFRM | All | 9/8/2021 | 5/24/2022
AEP-OH | SCANTON234 KV 3-T | XFRM | All | 9/20/2021 | 12/31/2021
AEP-OH | SCANTON2345 KV 3-S | XFRM | All | 9/20/2021 | 12/31/2021
AEP-OH | SCANTON2765 KV 3-P | XFRM | All | 9/20/2021 | 12/31/2021
APSS | BELMONT 500 KV BEL-HAR | LINE | All | 9/13/2021 | 10/12/2021
APSS | CATOCTIN138 KV CAT-GAR | LINE | All | 9/1/2021 1/4/2022 3/7/2022 4/11/2022 | 9/6/2021 1/12/2022 3/27/2022 6/1/2022
APSS | DOUBS 500 KV 583 | LINE | All | 9/20/2021 | 10/15/2021
APSS | FROSTOWN230 KV FRO-RIN | LINE | All | 9/1/2021 | 3/16/2022
APSS | GARFLD_T138 KV GAR-RIN | LINE | All | 9/1/2021 4/5/2022 | 3/13/2022 6/1/2022
APSS | HATFIRES138 KV HATR-LAR | LINE | All | 3/21/2020 | 12/31/2099
APSS | MEADOWBR500 KV LOU-MEA | LINE | All | 7/12/2021 | 8/13/2021
APSS | RINGGOLD230 KV T4 | XFRM | All | 9/3/2021 3/21/2022 | 3/16/2022 4/4/2022
APSS | YUKON 500 KV TR6 | XFRM | All | 10/4/2021 | 12/31/2021
APSS | YUKON 500 KV TRAN 2 | XFRM | All | 9/13/2021 | 12/31/2021
APSS | YUKON 500 KV TRAN 3 | XFRM | All | 9/23/2021 | 12/31/2021
BC | BRANDONS230 KV BRA-RIV5 | LINE | All | 9/20/2021 12/14/2021 | 10/4/2021 12/17/2021
BC | BUENAVIS230 KV 230-2 | XFRM | All | 9/9/2021 | 2/4/2022
BC | BUENAVIS230 KV 230-5 | XFRM | All | 9/9/2021 | 2/4/2022
BC | CONASTON230 KV CNS-NOR1 | LINE | All | 9/13/2021 12/16/2021 3/1/2022 | 10/28/2021 12/21/2021 4/22/2022
BC | CONASTON230 KV CNS-OTT | LINE | All | 9/27/2021 | 10/26/2021
BC | EDGEWOO1115 KV EDG-JOP0 | LINE | All | 9/20/2021 10/11/2021 11/3/2021 3/28/2022 | 10/1/2021 10/22/2021 11/16/2021 4/26/2022
BC | GENMOTOR115 KV 110-2 | XFRM | All | 1/15/2020 | 12/31/2021
BC | GRACETON230 KV GRA-SAF | LINE | All | 10/26/2021 3/23/2022 | 12/15/2021 5/1/2022
BC | JERICHOP230 KV JER-WAU1 | LINE | All | 9/9/2021 | 2/4/2022
BC | NORTHWES115 KV FIN-NOR | LINE | All | 10/4/2021 12/3/2021 5/22/2022 | 10/29/2021 12/6/2021 5/28/2022
BC | NORTHWES115 KV NOR-NOR2 | LINE | All | 10/4/2021 11/29/2021 5/29/2022 | 10/29/2021 12/10/2021 6/4/2022
BC | NORTHWES115 KV NOR-WHIT | LINE | All | 10/4/2021 | 10/29/2021
BC | NORTHWES230 KV 230-2 | XFRM | All | 10/4/2021 | 10/29/2021
BC | PERRYMAN115 KV EDG-PER0 | LINE | All | 9/20/2021 10/11/2021 11/3/2021 3/28/2022 | 10/1/2021 10/22/2021 11/16/2021 4/26/2022
COMED | 103 LISL138 KV TR83CT-S | XFRM | All | 11/8/2021 | 1/27/2022
COMED | 103 LISL345 KV TR83CT-P | XFRM | All | 11/8/2021 | 1/27/2022
COMED | 108 LOCK345 KV 10805 | LINE | All | 9/13/2021 | 1/30/2022
COMED | 108 LOCK345 KV 10806 | LINE | All | 9/13/2021 | 1/30/2022
COMED | 11609 138 KV 11609 9 | LINE | All | 8/30/2021 11/1/2021 | 10/15/2021 12/3/2021
COMED | 12 DRESD345 KV 1202 | LINE | All | 11/1/2021 4/4/2022 | 11/17/2021 5/5/2022
COMED | 12 DRESD345 KV 1227 | LINE | All | 11/1/2021 2/28/2022 | 12/17/2021 3/31/2022
COMED | 150 CALU345 KV 17723 2 | LINE | All | 10/25/2021 | 12/19/2021
COMED | 150 CALU345 KV 17723 3 | LINE | All | 10/25/2021 | 12/19/2021
COMED | 153 TAYL345 KV 17723 1 | LINE | All | 10/25/2021 | 12/19/2021
COMED | D438 138 KV 5104 13 | LINE | All | 11/3/2021 | 1/19/2022
CPL | PERSON4 230 KV 296C | LINE | All | 10/25/2021 3/23/2022 4/25/2022 | 11/23/2021 4/19/2022 5/23/2022
DAYTON | 09GRNVIL138 KV BK-7 | XFRM | All | 9/7/2021 | 10/26/2021
DAYTON | STUART2 345 KV STU-CLI1 | LINE | All | 10/1/2021 | 11/1/2021
DAYTON | WMILTON 138 KV WMI-09G1 | LINE | All | 9/7/2021 | 10/26/2021
DEOK | 08TBSCO1138 KV 08T-PIE1 | LINE | All | 11/8/2021 | 12/17/2021
DEOK | BUFFINGT345 KV BUF-PIE1 | LINE | All | 10/25/2021 | 12/17/2021
DEOK | CLINTONC138 KV CLI-HIL | LINE | All | 3/29/2021 3/8/2022 | 6/24/2021 5/26/2022
DEOK | CLINTONC138 KV CLI-WAR | LINE | All | 10/4/2021 3/7/2022 | 12/17/2021 5/20/2022
DEOK | MIAMIFOR138 KV MIA-CLI1 | LINE | All | 2/28/2022 | 4/1/2022
DEOK | SILVERGR138 KV BEC-SIL | LINE | All | 11/8/2021 5/16/2022 | 12/17/2021 5/27/2022
DEOK | SILVERGR345 KV SIL-ZIM1 | LINE | All | 11/1/2021 3/7/2022 4/25/2022 | 11/12/2021 3/18/2022 5/27/2022
DEOK | TODDHUNT345 KV 17 | XFRM | All | 7/27/2021 | 8/19/2021
DOM-C | ALTAVSTA138 KV TX4 | XFRM | All | 10/12/2021 | 3/3/2022
DOM-C | BRIERY 230 KV 235A1 | LINE | All | 2/15/2022 4/15/2022 | 3/1/2022 5/14/2022
DOM-C | BRISTERS500 KV 552 | LINE | All | 9/16/2021 3/1/2022 | 12/31/2021 6/14/2022
DOM-C | CARSON4 500 KV TX1H | XFRM | All | 8/16/2021 | 12/16/2021
DOM-C | CHICKHOM230 KV 287A | LINE | All | 6/28/2021 10/28/2021 | 7/1/2021 11/8/2021
DOM-C | CLARKVIL115 KV 127C | LINE | All | 6/1/2021 | 7/31/2021
DOM-C | CRSTLHDP115 KV CRY-HUBE | LINE | All | 10/4/2021 3/1/2022 | 11/1/2021 3/29/2022
DOM-C | DAVISDRV230 KV 2033 | LINE | All | 6/1/2021 | 9/3/2021
DOM-C | FARMVILL230 KV TX4 | XFRM | All | 8/30/2021 | 10/17/2021
DOM-C | HARMONYV230 KV TX2 | XFRM | All | 5/11/2021 9/28/2021 | 7/2/2021 11/12/2021
DOM-C | HARMONYV230 KV TX4 | XFRM | All | 5/11/2021 9/28/2021 | 6/9/2021 11/12/2021
DOM-C | KINDERTN115 KV 127D | LINE | All | 6/1/2021 | 7/31/2021
DOM-C | NANNA4 230 KV RSS3 | XFRM | All | 9/13/2021 | 10/7/2021
DOM-C | NANNA4 500 KV TX6 | XFRM | All | 9/13/2021 | 10/7/2021
DOM-C | NEWROAD 115 KV 49 | LINE | All | 5/3/2021 | 11/30/2021
DOM-C | PAPERMIL230 KV 2016C | LINE | All | 5/11/2021 9/28/2021 | 6/9/2021 11/12/2021
DOM-C | REEDYCRK115 KV 127B | LINE | All | 6/1/2021 | 10/31/2021
DOM-C | TURNER4 115 KV 92B | LINE | All | 10/4/2021 1/10/2022 | 11/5/2021 2/11/2022
DOM-C | WALTHALL115 KV 100A1 | LINE | All | 3/7/2022 | 6/3/2022
DOM-E | COMNATGS115 KV 74CB | LINE | All | 1/10/2022 1/15/2022 | 1/13/2022 6/15/2022
DOM-E | FTEUSTIS115 KV 34B1 | LINE | All | 6/28/2021 12/14/2021 | 11/1/2021 2/14/2022
DOM-E | GRAFTON4115 KV 34C | LINE | All | 6/28/2021 | 12/30/2022
DOM-E | GREENWCH230 KV 2038A | LINE | All | 7/21/2021 | 10/12/2021
DOM-E | LANEXA 230 KV 224A | LINE | All | 1/4/2022 | 6/9/2023
DOM-E | LEEHALL 115 KV 34A2 | LINE | All | 6/28/2021 11/5/2021 2/1/2022 | 11/1/2021 12/14/2021 12/30/2022
DOM-E | SEPTA4 500 KV 578A | LINE | All | 4/5/2022 | 5/2/2022
DOM-E | THOMPSCR115 KV 120B | LINE | All | 2/2/2021 | 10/28/2021
DOM-E | YORKTOW4115 KV 34D | LINE | All | 7/5/2021 | 1/31/2022
DOM-E | YORKTOW4115 KV 61C | LINE | All | 7/5/2021 | 1/31/2022
DOM-N | ASHBURN 230 KV 227A | LINE | All | 1/1/2022 | 6/15/2022
DOM-N | ASHBURN 230 KV 227B | LINE | All | 1/1/2022 | 6/15/2022
DOM-N | ASHBURN 230 KV TX2 | XFRM | All | 1/1/2022 | 6/15/2022
DOM-N | BEAUMEAD230 KV TX2 | XFRM | All | 1/1/2022 | 6/15/2022
DOM-N | BULLRUN 230 KV 295C | LINE | All | 3/14/2022 | 5/26/2022
DOM-N | BULLRUN 230 KV TX3 | XFRM | All | 3/14/2022 | 5/26/2022
DOM-N | CHANCELR500 KV TX1 | XFRM | All | 9/16/2021 3/1/2022 | 12/31/2021 6/14/2022
DOM-N | ELKRUNDP230 KV 2114B | LINE | All | 7/12/2021 11/15/2021 | 10/1/2021 1/28/2022
DOM-N | EPG 230 KV WOO-EPG | LINE | All | 9/8/2021 9/30/2021 | 9/14/2021 12/31/2021
DOM-N | HAYMARKT230 KV HAY-HEA1 | LINE | All | 1/15/2021 | 3/30/2022
DOM-N | HAYMARKT230 KV HAY-HEA2 | LINE | All | 1/15/2021 | 3/30/2022
DOM-N | MIDDLEBG115 KV TX1 | XFRM | All | 5/3/2021 | 11/30/2021
DOM-N | MIDDLEBG115 KV TX2 | XFRM | All | 5/3/2021 | 11/30/2021
DOM-N | MIDDLEBG115 KV TX5 | XFRM | All | 5/3/2021 | 11/30/2021
DOM-N | PLEASNTV230 KV 274D | LINE | All | 9/15/2021 3/1/2022 | 12/31/2021 6/14/2022
DOM-N | WALNEY 230 KV 265B | LINE | All | 3/14/2022 | 5/26/2022
DOM-N | WOODBRGE230 KV 2001A | LINE | All | 11/15/2021 3/1/2022 5/2/2022 | 12/31/2021 4/18/2022 5/18/2022
DOM-N | WOODBRGE230 KV 2001B | LINE | All | 9/15/2021 | 1/14/2022
DOM-N | WOODBRGE230 KV TX1 | XFRM | All | 11/15/2021 | 12/31/2021
DOM-S | CAROLINA230 KV 2141 | LINE | All | 3/1/2022 | 5/31/2022
DOM-S | SUNBURY4230 KV 247B | LINE | All | 1/4/2021 | 3/17/2022
DOM-W | LEXINGTN230 KV 2084A | LINE | All | 9/20/2021 | 10/15/2021
DOM-W | LOCUSTDP115 KV 153C | LINE | All | 10/15/2021 12/6/2021 1/31/2022 | 11/14/2021 12/17/2021 3/4/2022
DOM-W | LOWMOOR 230 KV TX3 | XFRM | All | 9/20/2021 | 10/15/2021
DOM-W | LOWMOOR 230 KV TX4 | XFRM | All | 9/25/2019 | 1/25/2022
DOM-W | MTSTORM4500 KV 550A | LINE | All | 3/1/2021 9/13/2021 3/1/2022 | 6/15/2021 12/17/2021 6/15/2022
DOM-W | MTSTORM4500 KV MTS-PRU | LINE | All | 10/18/2021 | 11/19/2021
DOM-W | WEYERSCV115 KV 43B | LINE | All | 10/18/2021 3/15/2022 | 2/28/2022 3/24/2022
DOM-W | WEYERSCV115 KV 43C | LINE | All | 5/2/2021 | 11/2/2021
DOM-W | WEYERSCV115 KV TX1 | XFRM | All | 10/18/2021 | 11/2/2021
DPL | CHESWOLD138 KV CHE-FEL | LINE | All | 3/1/2022 | 5/14/2022
DPL | ENEWMARK69 KV ENE-ENE | LINE | All | 9/8/2021 11/15/2021 2/14/2022 | 10/8/2021 11/19/2021 5/20/2022
DPL | ENEWMARK69 KV ENE-JAC | LINE | All | 9/8/2021 2/14/2022 | 10/8/2021 5/20/2022
DPL | FELTON 138 KV FEL-SHA | LINE | All | 9/20/2021 11/8/2021 3/1/2022 | 10/8/2021 11/24/2021 4/8/2022
DPL | INDIANRI230 KV IND-PIN | LINE | All | 11/8/2021 3/14/2022 | 12/17/2021 4/22/2022
DPL | KEENEY 230 KV KEE-STE9 | LINE | All | 10/25/2021 | 11/12/2021
DPL | PINEYGRO230 KV AT20 | XFRM | All | 11/8/2021 3/14/2022 | 12/17/2021 4/22/2022
DUQU | BOCGASES138 KV BOC-DRA | LINE | All | 9/20/2021 10/4/2021 | 9/24/2021 1/24/2022
DUQU | BOCGASES138 KV BOC-LOG | LINE | All | 9/20/2021 10/4/2021 | 9/24/2021 1/24/2022
DUQU | CARS DUQ345 KV T1 | XFRM | All | 9/20/2021 10/4/2021 | 9/23/2021 10/22/2021
DUQU | CHESWICK138 KV CHE-SPR | LINE | All | 5/28/2020 | 12/31/2021
DUQU | DRAVOSBU138 KV DRA-USS | LINE | All | 10/4/2021 | 1/10/2022
DUQU | DRAVOSBU138 KV DRA-WIL7 | LINE | All | 10/4/2021 | 1/24/2022
DUQU | PRTPERRY138 KV PER-DRA | LINE | All | 10/22/2021 | 1/24/2022
DUQU | PRTPERRY138 KV PER-WIL | LINE | All | 10/22/2021 | 1/24/2022
EKPC | FAWKES 138 KV FAW-WBER | LINE | All | 9/6/2021 | 12/17/2021
EKPC | GRANTSLK69 KV GRA-GRIF | LINE | All | 5/3/2021 | 11/5/2021
EKPC | JELLCRKJ69 KV JEL-MCRE | LINE | All | 3/29/2021 | 12/31/2021
EKPC | PINEKNOT69 KV PIN-REVE | LINE | All | 3/29/2021 | 12/31/2021
EKPC | ROWAN_CO138 KV ROW-SKAG | LINE | All | 4/13/2021 3/14/2022 | 12/13/2021 5/9/2022
EKPC | SKAGGS 138 KV XF1810 | XFRM | All | 4/13/2021 3/14/2022 | 12/13/2021 5/9/2022
EKPC | W_BEREA 138 KV XF187 | XFRM | All | 9/6/2021 | 12/17/2021
FECL | 02FABER 138 KV 02F-02F8 | LINE | All | 9/7/2021 | 11/8/2021
FECL | 02FABER 138 KV 02F-02P2 | LINE | All | 9/7/2021 | 11/8/2021
FECL | 02GARFLD138 KV 02G-GAR2 | LINE | All | 6/17/2020 | 12/31/2021
FECL | ASHTABUL345 KV ASH-ERI | LINE | All | 5/31/2021 10/4/2021 | 6/3/2021 11/14/2021
FECL | ASHTABUL345 KV TR-8 | XFRM | All | 5/31/2021 10/4/2021 | 6/3/2021 11/14/2021
FECL | EASTLAKE138 KV EAS-02L1 | LINE | All | 9/7/2021 | 12/2/2021
FECL | EASTLAKE138 KV EAS-04M1 | LINE | All | 9/7/2021 | 12/2/2021
FECL | HARDING2345 KV 1 | XFRM | All | 10/4/2021 | 12/11/2021
FECL | HARDING2345 KV 2 | XFRM | All | 10/4/2021 | 12/11/2021
FECL | JENNING 138 KV JEN-CLA1 | LINE | All | 5/28/2020 | 12/31/2021
FECL | JENNING 138 KV JEN-LTV7 | LINE | All | 1/24/2020 | 12/31/2025
FECL | LLOYD 138 KV 2 | XFRM | All | 8/23/2019 | 12/31/2021
FECL | PERRY_FE345 KV PER-ASH1 | LINE | All | 5/31/2021 10/4/2021 | 6/3/2021 11/14/2021
FEOE | BLUEBELL138 KV BLU-02A1 | LINE | All | 1/12/2019 | 12/30/2021
FEOE | CHAMBROE345 KV CHA-HAR2 | LINE | All | 10/4/2021 | 12/11/2021
FEOE | LAKVEW 138 KV LAK-OTT1 | LINE | All | 9/13/2021 | 11/23/2021
FEPA | CEDAROE 138 KV TR1 | XFRM | All | 9/7/2021 10/11/2021 1/4/2022 | 10/1/2021 11/12/2021 2/18/2022
FETE | WFREMONT138 KV WFR-WOO1 | LINE | All | 3/21/2022 | 4/29/2022
ILL_EQ | LANESVL 345 KV 2101 1 | LINE | All | 4/12/2022 | 5/12/2022
JC-N | EFLEMING230 KV BK 3TR | XFRM | All | 9/15/2021 | 6/1/2022
JC-N | EFLEMING230 KV EFL-PLV | LINE | All | 9/15/2021 | 6/1/2022
JC-N | ELASTIMO230 KV ELA-POH | LINE | All | 9/13/2021 12/13/2021 3/14/2022 | 10/29/2021 12/17/2021 4/22/2022
JC-N | KITTATIN230 KV KIT-POH | LINE | All | 10/25/2021 3/14/2022 | 10/29/2021 4/22/2022
JC-N | PEQUESTR115 KV PEQ-POR | LINE | All | 9/17/2021 9/27/2021 | 9/17/2021 12/17/2021
JC-N | POHATCON230 KV TR1 | XFRM | All | 10/25/2021 3/14/2022 | 10/29/2021 4/22/2022
JC-N | READINGT230 KV BK 2TR | XFRM | All | 9/15/2021 | 6/1/2022
JC-N | READINGT230 KV REA-ROS | LINE | All | 9/15/2021 | 6/1/2022
JC-N | TRAYNOR 230 KV TRA-WHIY | LINE | All | 11/18/2021 | 12/17/2021
JC-S | LAKEWOOD230 KV LAK-LEI | LINE | All | 9/16/2021 11/1/2021 | 10/30/2021 12/17/2021
JC-S | NEWPROSP230 KV NEW-SMI | LINE | All | 11/4/2021 | 12/3/2021
JC-S | SMITHBUR230 KV BK 2TR | XFRM | All | 11/4/2021 | 12/3/2021
ME | ALBURTME230 KV ALB-LYO | LINE | All | 9/15/2021 | 12/17/2021
ME | HUNTERST115 KV HUN-LIN | LINE | All | 9/20/2021 2/28/2022 | 12/18/2021 5/13/2022
ME | HUNTERST500 KV HUN-VIN | LINE | All | 11/1/2021 4/4/2022 | 12/4/2021 5/13/2022
ME | PORTLAND230 KV 3 BANK | XFRM | All | 9/13/2021 10/21/2021 | 10/19/2021 10/26/2021
ME | YORKANA 230 KV BANK 1 | XFRM | All | 10/4/2021 | 10/29/2021
PE | BUCKINGH230 KV BUC-LIN | LINE | All | 9/8/2021 | 10/5/2021
PE | BUCKINGH230 KV BUCK-ROC | LINE | All | 6/8/2021 9/8/2021 | 6/8/2021 10/5/2021
PE | CHICHEST230 KV CHI-EDD | LINE | All | 10/19/2021 | 11/1/2021
PE | GRAYSFER230 KV GRA-PAS | LINE | All | 6/10/2021 9/13/2021 | 6/11/2021 10/1/2021
PE | JARRET 230 KV JAR-WHI | LINE | All | 11/29/2021 12/17/2021 2/26/2022 4/25/2022 5/11/2022 | 12/1/2021 12/18/2021 3/7/2022 4/27/2022 5/11/2022
PE | PASSYUNK230 KV PAS 9TR | XFRM | All | 6/10/2021 9/13/2021 | 6/11/2021 10/1/2021
PE | PASSYUNK69 KV PAS-SWA | LINE | All | 6/10/2021 9/13/2021 | 6/11/2021 10/1/2021
PE | PLYMOUTH230 KV PLY-WHI4 | LINE | All | 9/21/2021 10/4/2021 11/29/2021 12/17/2021 2/26/2022 | 9/21/2021 10/7/2021 12/1/2021 12/18/2021 3/7/2022
PE | SWARK 69 KV SWK 3TR | XFRM | All | 6/10/2021 9/13/2021 | 6/11/2021 10/1/2021
PE | WHITEMAR230 KV WHI-WHI | LINE | All | 6/26/2021 7/24/2021 11/29/2021 12/17/2021 2/26/2022 | 6/27/2021 7/25/2021 12/1/2021 12/18/2021 3/7/2022
PE | WHITPAIN500 KV WHT 3TR | XFRM | All | 11/19/2021 11/29/2021 12/17/2021 2/26/2022 | 11/19/2021 12/1/2021 12/18/2021 3/7/2022
PEP | BELLSMIL230 KV 121-12T | XFRM | All | 10/1/2021 | 3/4/2022
PEP | BELLSMIL230 KV 121-3T | XFRM | All | 10/1/2021 | 3/4/2022
PEP | BELLSMIL230 KV BEL-QUI0 | LINE | All | 10/1/2021 | 3/4/2022
PEP | BOWIE 230 KV 162-2T | XFRM | All | 9/9/2021 | 2/4/2022
PEP | BOWIE 230 KV BOW-BUR3 | LINE | All | 9/9/2021 | 2/4/2022
PEP | BOWIE 230 KV BOW-JER1 | LINE | All | 9/9/2021 | 2/4/2022
PEP | BOWIE 230 KV BOW-OAK1 | LINE | All | 9/9/2021 | 2/4/2022
PEP | CHALKPT 230 KV CHA-OAKG | LINE | All | 9/9/2021 | 2/4/2022
PEP | DICKERSO230 KV DIC-QUI5 | LINE | All | 10/1/2021 | 3/4/2022
PEP | LANHAM 115 KV LAN-TUX4 | LINE | All | 8/10/2021 | 10/28/2021
PEP | MTZION 230 KV MTZ-QUI2 | LINE | All | 9/11/2021 | 6/4/2022
PEP | MTZION 230 KV MTZ-QUI4 | LINE | All | 9/11/2021 | 6/4/2022
PEP | MTZION 230 KV MTZ-QUI5 | LINE | All | 10/1/2021 | 3/4/2022
PEP | QUINCEOR230 KV 118-3T | XFRM | All | 10/1/2021 | 3/4/2022
PL-N | FISHBACH69 KV FIS-FRA3 | LINE | All | 3/22/2021 6/28/2021 7/19/2021 8/16/2021 11/29/2021 | 6/25/2021 7/14/2021 8/13/2021 11/19/2021 12/15/2021
PL-N | FRACKVIL230 KV 2 | XFRM | All | 8/3/2021 | 10/27/2021
PL-N | HAUTO 69 KV HAU-SIE1 | LINE | All | 6/7/2021 | 9/13/2021
PL-N | JENKINS 230 KV 1 | XFRM | All | 6/2/2021 | 7/14/2021
PL-N | JENKINS 230 KV JEN-STA | LINE | All | 6/2/2021 | 7/14/2021
PL-N | STANTON 230 KV 3 | XFRM | All | 6/2/2021 | 7/14/2021
PL-N | SUSQUEHA500 KV SUS-WES | LINE | All | 6/4/2021 | 6/18/2021
PL-S | BRUNNERI230 KV BRU-YOR | LINE | All | 10/4/2021 | 10/29/2021
PL-S | EPALMERT69 KV EPA-HAU2 | LINE | All | 6/7/2021 | 9/13/2021
PL-S | FACEROCK115 KV 1 | XFRM | All | 9/8/2021 | 12/22/2021
PL-S | FACEROCK115 KV 2 | XFRM | All | 9/8/2021 | 12/22/2021
PL-S | FACEROCK115 KV FAC-FIV1 | LINE | All | 9/8/2021 | 12/22/2021
PL-S | FACEROCK115 KV FAC-FIV2 | LINE | All | 9/8/2021 | 12/22/2021
PL-S | HUMMELST230 KV 1 | XFRM | All | 2/25/2021 4/11/2022 | 3/1/2022 4/14/2022
PL-S | HUMMELST230 KV 3 | XFRM | All | 6/7/2021 9/16/2021 | 7/30/2021 10/15/2021
PL-S | JUNIATA 500 KV 2 | XFRM | All | 11/1/2021 | 12/17/2021
PL-S | MANOR 230 KV 3 | XFRM | All | 10/22/2021 3/1/2022 | 1/11/2022 4/25/2022
PL-S | MANOR 230 KV MAN-SAF1 | LINE | All | 10/11/2021 | 11/13/2021
PL-S | OTTCRKPL230 KV OTT-SAF | LINE | All | 10/11/2021 | 11/13/2021
PL-S | QUARRY 230 KV QUA-STE2 | LINE | All | 9/15/2021 | 10/12/2021
PL-S | SAFEHARB230 KV 2301 | XFRM | All | 10/11/2021 | 11/13/2021
PL-S | SAFEHARB230 KV 2302 | XFRM | All | 10/11/2021 | 11/13/2021
PL-S | WHEMPFIE230 KV 1 | XFRM | All | 8/30/2021 | 11/18/2021
PL-S | WHEMPFIE230 KV 3 | XFRM | All | 7/19/2021 10/11/2021 | 8/26/2021 11/18/2021
PN | CANYON 230 KV CAN-NME | LINE | All | 11/1/2021 | 12/17/2021
PN | ERIEE 230 KV ERI-SRI | LINE | All | 6/1/2021 | 6/15/2021
PN | ERIEW 345 KV NO1 TX | XFRM | All | 9/13/2021 | 12/31/2021
PN | ETOWANDA115 KV 5TX | XFRM | All | 3/2/2020 | 10/28/2021
PN | FOREST 115 KV FOR-RID | LINE | All | 9/13/2021 3/1/2022 | 12/23/2021 6/14/2022
PN | FOREST 230 KV 1 TX | XFRM | All | 9/13/2021 3/1/2022 | 12/23/2021 6/14/2022
PN | FOREST 230 KV FOR-SQU | LINE | All | 9/13/2021 12/17/2021 3/1/2022 | 9/20/2021 12/23/2021 3/18/2022
PN | GLADE 230 KV FOR-GLA1 | LINE | All | 9/13/2021 12/17/2021 3/1/2022 | 9/20/2021 12/23/2021 3/18/2022
PN | GROVER 230 KV 1TX | XFRM | All | 3/14/2022 5/16/2022 | 4/1/2022 6/10/2022
PN | GROVER 230 KV GRO-MARS | LINE | All | 3/14/2022 5/16/2022 | 4/1/2022 6/10/2022
PN | GROVER 230 KV GRO-SCO | LINE | All | 3/14/2022 5/16/2022 | 4/1/2022 6/10/2022
PN | HOMERCIT23 KV N.AUTO-T | XFRM | All | 11/10/2021 3/1/2022 | 12/3/2021 5/27/2022
PN | HOMERCIT230 KV N.AUTO-S | XFRM | All | 8/23/2021 11/10/2021 3/1/2022 | 9/10/2021 12/3/2021 5/27/2022
PN | HOMERCIT345 KV HOM-MAI | LINE | All | 9/18/2021 3/1/2022 | 11/5/2021 5/27/2022
PN | HOMERCIT345 KV N.AUTO-P | XFRM | All | 11/10/2021 3/1/2022 | 12/3/2021 5/27/2022
PN | NMESHOPP230 KV 4 TX | XFRM | All | 11/1/2021 | 12/17/2021
PN | NMESHOPP230 KV NME-OXB | LINE | All | 9/13/2021 11/1/2021 | 10/29/2021 12/17/2021
PS-N | ATHENIA 230 KV ATH-COO | LINE | All | 9/13/2021 1/4/2022 | 9/16/2021 1/14/2022
PS-N | BAYONNE 345 KV BYO-MAR1 | LINE | All | 9/20/2021 | 11/3/2021
PS-N | BERGEN 230 KV BER-LEO | LINE | All | 9/20/2021 | 10/10/2021
PS-N | FOUNDRY 138 KV FOU-NEW | LINE | All | 3/2/2022 | 5/17/2022
PS-N | HUDSON 345 KV 345-1 | XFRM | All | 1/15/2018 | 12/31/2021
PS-S | HOPECREE500 KV HOP-RED | LINE | All | 9/28/2021 11/16/2021 | 10/31/2021 12/17/2021
PS-S | KUSERRD 230 KV KUS-LAW | LINE | All | 9/20/2021 | 11/3/2021
SENY | FARRAGUT345 KV FAR-HUDB | LINE | All | 1/15/2018 | 12/31/2021
SENY | FARRAGUT345 KV FAR-MAR | LINE | All | 1/15/2018 | 12/31/2021
SENY | FARRAGUT345 KV FAR-MAR2 | LINE | All | 1/15/2018 | 12/31/2021