## 27-28 BRA Post
The 27/28 BRA activity dates based on Docket No. ER23-1609-000 and ER25-118 approved by the FERC.
**All Auctions will open at 12:01 AM EPT
**All Auctions will close at 5:00 PM EPT
**All Results will be posted no earlier than 4:00 PM EPT
The provisions of the OATT shall govern in the event of any conflict between this timeline and provisions of the Tariff.
Delivery Year | Auction | Activity Type | Activity | Responsible Party | Date
2027/2028 | BRA | Must Offer | Last day for Capacity Market Sellers to request preliminary must-offer exception for the reason specified under OATT Attachment M-Appendix § II.C.4.A (Deactivation) | GEN | N/A
2027/2028 | BRA | Removal of Capacity Status | Last day for Capacity Market Sellers to provide preliminary request to remove a resource from Capacity Resource status | Gen | N/A
2027/2028 | BRA | PSA | Last day for Seller Peak-Shaving Adjustment Plans | PSA | 2024-09-16
2027/2028 | BRA | Planned Generation | Last day for Capacity Market Seller to provide binding offer notification (also known as "notice of intent") for Planned Generation Capacity Resources | GEN | 2025-06-07
2027/2028 | BRA | MOPR | PJM posts preliminary MOPR screen prices | PJM | 2025-07-07
2027/2028 | BRA | MOPR | Last day for a Capacity Market Seller to certify if subject to State Conditioned Support and/or Buyer Side Market Power | GEN | 2025-07-07
2027/2028 | BRA | Sell Offer Caps | IMM posts preliminary unit specific historical EAS offset | IMM | 2025-07-07
2027/2028 | BRA | Sell Offer Caps | PJM posts gross ACR for seller offer cap | PJM | 2025-07-07
2027/2028 | BRA | Winter CIRs | PJM solicits requests for Winter CIRs | PJM | 2025-07-12
2027/2028 | BRA | Demand Resource | PJM posts the Zones and sub-Zones, if any, for which end-use customer site-specific information shall be required for DR sell offers under the conditions specified in RAA Schedule 6 subsection A-1(1)(c)(iv). | PJM | 2025-07-22
2027/2028 | BRA | MOPR | PJM/IMM notifies Capacity Market Seller of bases for inquiry and intiation of fact specific review | GEN | 2025-07-22
2027/2028 | BRA | Must Offer | Last day for Capacity Market Sellers to request must-offer exception for the reason specified under OATT Attachment M-Appendix § II.C.4.A (Deactivation) | GEN | 2025-07-22
2027/2028 | BRA | Removal of Capacity Status | Last day for Capacity Market Sellers to request to remove a resource from Capacity Resource status | GEN | 2025-07-22
2027/2028 | BRA | Sell Offer Caps | IMM post final unit specific EAS offset | IMM | 2025-07-22
2027/2028 | BRA | Winter CIRs | Last day for Seller request for Winter CIRs | GEN | 2025-07-22
2027/2028 | BRA | Planning Parameters | Preliminary ELCC Class Rating and Accredited UCAP Factors | Gen/DR | 2025-08-04
2027/2028 | BRA | FRR | Last day for first time election of FRR Alternative starting with DY | FRR | 2025-08-05
2027/2028 | BRA | MOPR | Last day for Capacity Market Seller resource-specific MOPR exception request | GEN | 2025-08-06
2027/2028 | BRA | Must Offer | Last day for Capacity Market Sellers to request must-offer exception for reasons other than Deactivation as outlined in OATT Attachment M - Appendix § II.C.4.A (e.g. external sale of capacity, significant physical operational restriction, ongoing regulatory proceedings related to environmental restrictions and delay in achieving full commercial operation.) | GEN | 2025-08-06
2027/2028 | BRA | Sell Offer Caps | Last day for Capacity Market Sellers to request unit specific sell offer cap price | GEN | 2025-08-06
2027/2028 | BRA | PRD | Last day to submit PRD Plan for BRA | PRD | 2025-08-09
2027/2028 | BRA | Planning Parameters | Post Planning Parameters | PJM | 2025-08-26
2027/2028 | BRA | MOPR | IMM provides participant with determination on resource-specific MOPR exception request | IMM | 2025-09-05
2027/2028 | BRA | Must Offer | IMM provides participant with determination on must offer exception | IMM | 2025-09-05
2027/2028 | BRA | Removal of Capacity Status | IMM provides participant with determination on removal of capacity status | IMM | 2025-09-05
2027/2028 | BRA | Sell Offer Caps | IMM provides participant with determination of offer cap | IMM | 2025-09-05
2027/2028 | BRA | Must Offer | Last day for Capacity Market Sellers to notify PJM/IMM of agreement with IMM determination of its request for must offer exception | GEN | 2025-09-15
2027/2028 | BRA | Removal of Capacity Status | Last day for Capacity Market Sellers to notify PJM/IMM of agreement with IMM determination of its request to remove a resource from Capacity Resource status | GEN | 2025-09-15
2027/2028 | BRA | Sell Offer Caps | Last day for Capacity Market Sellers to notify PJM/IMM of agreement with IMM determination of offer cap | GEN | 2025-09-15
2027/2028 | BRA | MOPR | PJM notifies participant/IMM with determination on resource-specific MOPR exception request | PJM | 2025-09-30
2027/2028 | BRA | Must Offer | PJM notifies participant/IMM of its determination on must offer exception | PJM | 2025-09-30
2027/2028 | BRA | Must Offer | Last day for Capacity Market Sellers to notify PJM/IMM whether it intends to exclude from its Sell Offer some or all capacity from its generation resource on the basis of an identified exception to the RPM Must Offer Obligation | GEN | 2025-09-30
2027/2028 | BRA | Removal of Capacity Status | PJM notifies participant/IMM of its determination on removal of Capacity Resource status | PJM | 2025-09-30
2027/2028 | BRA | Sell Offer Caps | PJM notifies participant/IMM of determination on proposed offer cap | PJM | 2025-09-30
2027/2028 | BRA | FRR | Last day for FRR termination of election ( Last day for election of FRR termination) | FRR | 2025-10-04
2027/2028 | BRA | FRR | Last day for election of FRR Alternative starting with DY | FRR | 2025-10-04
2027/2028 | BRA | FRR | Last day for DR Pre-registration Required for FRR Capacity Plan | FRR | 2025-10-05
2027/2028 | BRA | MOPR | Participant provides commitment on MOPR price to be used | GEN | 2025-10-05
2027/2028 | BRA | FRR | Last day for DR Plan Template and Officer Certification for FRR Capacity Plan | FRR | 2025-10-16
2027/2028 | BRA | Demand Resource | Last day to request a CSP switch for DR pre-registration process | DR | 2025-10-20
2027/2028 | BRA | ICTR/QTU | Last day for ICTR/QTU Certification of Increase in Import Capability due | QTU | 2025-10-20
2027/2028 | BRA | Demand Resource | DR Pre-registration Window opens | DR | 2025-10-21
2027/2028 | BRA | Demand Resource | Last day for DR Sell Offer Plan and Officer Certification Required | DR | 2025-11-04
2027/2028 | BRA | Demand Resource | DR Pre-registration Window closes | DR | 2025-11-04
2027/2028 | BRA | FRR | Last day for submission of FRR Capacity Plan due | FRR | 2025-11-04
2027/2028 | BRA | Demand Resource | DR Setup Window opens | DR | 2025-11-05
2027/2028 | BRA | Aggregation | Last day to submit request for aggregate resource | GEN/DR | 2025-11-20
2027/2028 | BRA | Demand Resource | DR Setup Window closes | DR | 2025-12-01
2027/2028 | BRA | Auction | Auction window opens | All | 2025-12-04
2027/2028 | BRA | Auction | Auction window closes | All | 2025-12-10
2027/2028 | BRA | Auction | Auction results posted | PJM | 2025-12-17

## 26-27 3rd IA Post
The 26/27 3rd IA activity dates based on Docket No. ER23-1609-000 and ER25-118 approved by the FERC.
**All Auctions will open at 12:01 AM EPT
**All Auctions will close at 5:00 PM EPT
**All Results will be posted no earlier than 4:00 PM EPT
The provisions of the OATT shall govern in the event of any conflict between this timeline and provisions of the Tariff.
Delivery Year | Auction | Activity Type | Activity | Responsible Party | Date
2026/2027 | 3rd IA | Removal of Capacity Status | Last day for Capacity Market Sellers to provide preliminary request to remove a resource from Capacity Resource status | GEN | N/A
2026/2027 | 3rd IA | Must Offer | Last day for Capacity Market Sellers to request preliminary must-offer exception for the reason specified under OATT Attachment M-Appendix § II.C.4.A (Deactivation) | GEN | N/A
2026/2027 | 3rd IA | PSA | Last day for Seller Peak-Shaving Adjustment Plans | PSA | 2025-09-16
2026/2027 | 3rd IA | MOPR | Last day for a Capacity Market Seller to certify if subject to State Conditioned Support and/or Buyer Side Market Power | GEN | 2025-09-27
2026/2027 | 3rd IA | Sell Offer Caps | IMM posts preliminary unit specific historical EAS offset | IMM | 2025-09-27
2026/2027 | 3rd IA | Sell Offer Caps | PJM posts gross ACR for seller offer cap | PJM | 2025-09-27
2026/2027 | 3rd IA | Sell Offer Caps | IMM post final unit specific EAS offset | IMM | 2025-10-12
2026/2027 | 3rd IA | MOPR | PJM/IMM notifies Capacity Market Seller of bases for inquiry and intiation of fact specific review | PJM/IMM | 2025-10-12
2026/2027 | 3rd IA | Must Offer | Last day for Capacity Market Sellers to request must-offer exception for the reason specified under OATT Attachment M-Appendix § II.C.4.A (Deactivation) | GEN | 2025-10-27
2026/2027 | 3rd IA | MOPR | Last day for Capacity Market Seller resource-specific MOPR exception request | GEN | 2025-10-27
2026/2027 | 3rd IA | Sell Offer Caps | Last day for Capacity Market Sellers to submit sell offer cap data | GEN | 2025-10-27
2026/2027 | 3rd IA | Must Offer | Last day for Capacity Market Sellers to request must-offer exception for reasons other than Deactivation as outlined in OATT Attachment M - Appendix § II.C.4.A (e.g. external sale of capacity, significant physical operational restriction, ongoing regulatory proceedings related to environmental restrictions and delay in achieving full commercial operation.) | GEN | 2025-10-27
2026/2027 | 3rd IA | Removal of Capacity Status | Last day for Capacity Market Sellers to request to remove a resource from Capacity Resource status | GEN | 2025-10-27
2026/2027 | 3rd IA | Planned Generation | Last day for Planned Generation Owners to Provide Notification of Intent to Offer | GEN | 2025-11-26
2026/2027 | 3rd IA | MOPR | IMM provides participant with determination on resource-specific MOPR exception request | IMM | 2025-11-26
2026/2027 | 3rd IA | Sell Offer Caps | IMM provides participant with determination of offer cap | IMM | 2025-11-26
2026/2027 | 3rd IA | Must Offer | IMM provides participant with determination on must offer exception | IMM | 2025-11-26
2026/2027 | 3rd IA | Removal of Capacity Status | IMM provides participant with determination on removal of capacity status | IMM | 2025-11-26
2026/2027 | 3rd IA | Sell Offer Caps | Last day for Capacity Market Sellers to notify PJM/IMM of agreement with IMM determination of offer cap | GEN | 2025-12-06
2026/2027 | 3rd IA | Must Offer | Last day for Capacity Market Sellers to notify PJM/IMM of agreement with IMM determination of its request to remove a resource from Capacity Resource status or must offer exception | GEN | 2025-12-06
2026/2027 | 3rd IA | MOPR | PJM notifies participant/IMM with determination on resource-specific MOPR exception request | PJM | 2025-12-21
2026/2027 | 3rd IA | Sell Offer Caps | PJM notifies participant/IMM of determination on proposed offer cap | PJM | 2025-12-21
2026/2027 | 3rd IA | Must Offer | PJM notifies participant/IMM of its determination on must offer exception | PJM | 2025-12-21
2026/2027 | 3rd IA | Removal of Capacity Status | PJM notifies participant/IMM of its determination on removal of capacity status | PJM | 2025-12-21
2026/2027 | 3rd IA | Must Offer | Last day for Capacity Market Sellers to notify PJM/IMM whether it intends to exclude from its Sell Offer some or all capacity from its generation resource on the basis of an identified exception to the RPM Must Offer Obligation | GEN | 2025-12-21
2026/2027 | 3rd IA | PRD | Last day to submit PRD Plan for 3IA | PRD | 2026-01-15
2026/2027 | 3rd IA | MOPR | Participant provides commitment on MOPR price to be used | GEN | 2025-12-26
2026/2027 | 3rd IA | ICTR/QTU | Last day for ICTR/QTU Certification of Increase in Import Capability due | QTU | 2026-01-10
2026/2027 | 3rd IA | Demand Resource | Last day to request a CSP switch for DR pre-registration process | DR | 2025-12-30
2026/2027 | 3rd IA | Demand Resource | DR Pre-registration Window opens | DR | 2025-12-31
2026/2027 | 3rd IA | Planning Parameters | Final ELCC Class Rating and Accredited UCAP Factors | Gen/DR | 2025-12-31
2026/2027 | 3rd IA | Planning Parameters | Post Planning Parameters | PJM | 2026-01-25
2026/2027 | 3rd IA | Demand Resource | Last day for DR Sell Offer Plan and Officer Certification Required | DR | 2026-01-25
2026/2027 | 3rd IA | Demand Resource | DR Pre-registration Window closes | DR | 2026-01-25
2026/2027 | 3rd IA | Demand Resource | DR Setup Window opens | DR | 2026-01-31
2026/2027 | 3rd IA | Aggregation | Last day to submit request for aggregate resource | GEN/DR | 2026-02-10
2026/2027 | 3rd IA | Demand Resource | DR Setup Window closes | DR | 2026-02-21
2026/2027 | 3rd IA | Auction | Auction window opens | ALL | 2026-02-24
2026/2027 | 3rd IA | Auction | Auction window closes | ALL | 2026-03-02
2026/2027 | 3rd IA | Auction | Auction results posted | PJM | 2026-03-09

## 28-29 BRA Post
The 28/29 BRA activity dates based on Docket No. ER23-1609-000 and ER25-118 approved by the FERC.
**All Auctions will open at 12:01 AM EPT
**All Auctions will close at 5:00 PM EPT
**All Results will be posted no earlier than 4:00 PM EPT
The provisions of the OATT shall govern in the event of any conflict between this timeline and provisions of the Tariff.
Delivery Year | Auction | Activity Type | Activity | Responsible Party | Date
2028/2029 | BRA | Must Offer | Last day for Capacity Market Sellers to request preliminary must-offer exception for the reason specified under OATT Attachment M-Appendix § II.C.4.A (Deactivation) | GEN | N/A
2028/2029 | BRA | Removal of Capacity Status | Last day for Capacity Market Sellers to provide preliminary request to remove a resource from Capacity Resource status | Gen | N/A
2028/2029 | BRA | PSA | Last day for Seller Peak-Shaving Adjustment Plans | PSA | 2025-09-16
2028/2029 | BRA | Planned Generation | Last day for Capacity Market Seller to provide binding offer notification (also known as "notice of intent") for Planned Generation Capacity Resources | GEN | 2025-12-01
2028/2029 | BRA | DER | Requested DER Plan and Officer Certification submission date for DER resources subject to MOPR and/or MSOC | DER | 2026-01-21
2028/2029 | BRA | MOPR | PJM posts preliminary MOPR screen prices | PJM | 2026-01-31
2028/2029 | BRA | MOPR | Last day for a Capacity Market Seller to certify if subject to State Conditioned Support and/or Buyer Side Market Power | GEN | 2026-01-31
2028/2029 | BRA | Sell Offer Caps | IMM posts preliminary unit specific historical EAS offset | IMM | 2026-01-31
2028/2029 | BRA | Sell Offer Caps | PJM posts gross ACR for seller offer cap | PJM | 2026-01-31
2028/2029 | BRA | Winter CIRs | PJM solicits requests for Winter CIRs | PJM | 2026-02-05
2028/2029 | BRA | Demand Resource | PJM posts the Zones and sub-Zones, if any, for which end-use customer site-specific information shall be required for DR sell offers under the conditions specified in RAA Schedule 6 subsection A-1(1)(c)(iv). | PJM | 2026-02-15
2028/2029 | BRA | MOPR | PJM/IMM notifies Capacity Market Seller of bases for inquiry and intiation of fact specific review | GEN | 2026-02-15
2028/2029 | BRA | Must Offer | Last day for Capacity Market Sellers to request must-offer exception for the reason specified under OATT Attachment M-Appendix § II.C.4.A (Deactivation) | GEN | 2026-02-15
2028/2029 | BRA | Removal of Capacity Status | Last day for Capacity Market Sellers to request to remove a resource from Capacity Resource status | Gen | 2026-02-15
2028/2029 | BRA | Sell Offer Caps | IMM post final unit specific EAS offset | IMM | 2026-02-15
2028/2029 | BRA | Winter CIRs | Last day for Seller request for Winter CIRs | GEN | 2026-02-15
2028/2029 | BRA | Planning Parameters | Preliminary ELCC Class Rating and Accredited UCAP Factors | Gen/DR | 2026-02-27
2028/2029 | BRA | FRR | Last day for first time election of FRR Alternative starting with DY | FRR | 2026-03-01
2028/2029 | BRA | MOPR | Last day for Capacity Market Seller resource-specific MOPR exception request | GEN | 2026-03-02
2028/2029 | BRA | Must Offer | Last day for Capacity Market Sellers to request must-offer exception for reasons other than Deactivation as outlined in OATT Attachment M - Appendix § II.C.4.A (e.g. external sale of capacity, significant physical operational restriction, ongoing regulatory proceedings related to environmental restrictions and delay in achieving full commercial operation.) | GEN | 2026-03-02
2028/2029 | BRA | Sell Offer Caps | Last day for Capacity Market Sellers to request unit specific sell offer cap price | GEN | 2026-03-02
2028/2029 | BRA | PRD | Last day to submit PRD Plan for BRA | PRD | 2026-03-05
2028/2029 | BRA | Planning Parameters | Post Planning Parameters | PJM | 2026-03-22
2028/2029 | BRA | MOPR | IMM provides participant with determination on resource-specific MOPR exception request | IMM | 2026-04-01
2028/2029 | BRA | Must Offer | IMM provides participant with determination on must offer exception | IMM | 2026-04-01
2028/2029 | BRA | Removal of Capacity Status | IMM provides participant with determination on removal of capacity status | IMM | 2026-04-01
2028/2029 | BRA | Sell Offer Caps | IMM provides participant with determination of offer cap | IMM | 2026-04-01
2028/2029 | BRA | Must Offer | Last day for Capacity Market Sellers to notify PJM/IMM of agreement with IMM determination of its request for must offer exception | GEN | 2026-04-11
2028/2029 | BRA | Removal of Capacity Status | Last day for Capacity Market Sellers to notify PJM/IMM of agreement with IMM determination of its request to remove a resource from Capacity Resource status | GEN | 2026-04-11
2028/2029 | BRA | Sell Offer Caps | Last day for Capacity Market Sellers to notify PJM/IMM of agreement with IMM determination of offer cap | GEN | 2026-04-11
2028/2029 | BRA | MOPR | PJM notifies participant/IMM with determination on resource-specific MOPR exception request | PJM | 2026-04-27
2028/2029 | BRA | Must Offer | PJM notifies participant/IMM of its determination on must offer exception | PJM | 2026-04-27
2028/2029 | BRA | Must Offer | Last day for Capacity Market Sellers to notify PJM/IMM whether it intends to exclude from its Sell Offer some or all capacity from its generation resource on the basis of an identified exception to the RPM Must Offer Obligation | GEN | 2026-04-27
2028/2029 | BRA | Removal of Capacity Status | PJM notifies participant/IMM of its determination on removal of Capacity Resource status | PJM | 2026-04-27
2028/2029 | BRA | Sell Offer Caps | PJM notifies participant/IMM of determination on proposed offer cap | PJM | 2026-04-27
2028/2029 | BRA | FRR | Last day for FRR termination of election ( Last day for election of FRR termination) | FRR | 2026-04-30
2028/2029 | BRA | FRR | Last day for election of FRR Alternative starting with DY | FRR | 2026-04-30
2028/2029 | BRA | FRR | Last day for DR Pre-registration Required for FRR Capacity Plan | FRR | 2026-05-01
2028/2029 | BRA | MOPR | Participant provides commitment on MOPR price to be used | GEN | 2026-05-01
2028/2029 | BRA | FRR | Last day for DR Plan Template and Officer Certification for FRR Capacity Plan | FRR | 2026-05-12
2028/2029 | BRA | Demand Resource | Last day to request a CSP switch for DR pre-registration process | DR | 2026-05-16
2028/2029 | BRA | ICTR/QTU | Last day for ICTR/QTU Certification of Increase in Import Capability due | QTU | 2026-05-16
2028/2029 | BRA | Demand Resource | DR Pre-registration Window opens | DR | 2026-05-17
2028/2029 | BRA | FRR | Last day for submission of FRR Capacity Plan due | FRR | 2026-05-31
2028/2029 | BRA | Demand Resource | Last day for DR Sell Offer Plan and Officer Certification Required | DR | 2026-05-31
2028/2029 | BRA | Demand Resource | DR Pre-registration Window closes | DR | 2026-05-31
2028/2029 | BRA | DER | Last day for Final DER Plan and Officer Certification | DER | 2026-05-31
2028/2029 | BRA | Demand Resource | DR Setup Window opens | DR | 2026-06-01
2028/2029 | BRA | Aggregation | Last day to submit request for aggregate resource | GEN/DR | 2026-06-16
2028/2029 | BRA | Demand Resource | DR Setup Window closes | DR | 2026-06-27
2028/2029 | BRA | Auction | Auction window opens | All | 2026-06-30
2028/2029 | BRA | Auction | Auction window closes | All | 2026-07-07
2028/2029 | BRA | Auction | Auction results posted | PJM | 2026-07-14

## Future Schedule Post
Capacity Market Auction Schedule based on Docket No. ER23-1609-000 and ER25-118 approved by the FERC
Delivery Year | Auction | Schedule
2026/27 | 3rd IA | 2026-02-24
2027/28 | BRA | 2025-12-04
2027/28 | 2nd IA | cancelled
2027/28 | 3rd IA | 2027-02-24
2028/29 | BRA | 2026-06-23
2028/29 | 2nd IA | 2027-07-14
2028/29 | 3rd IA | 2028-02-23
2029/30 | BRA | 2026-12-10
2029/30 | 1rst IA | cancelled
2029/30 | 2nd IA | 2028-07-19
2029/30 | 3rd IA | 2029-02-21
2030/31 | BRA (back to normal schedule under proposed schedule) | 2027-05-10
Note - Actual dates will be published with detailed schedules